## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Pathankhali PWSS Zone-II for Providing Functional Household Tap Connection (FHTC) Block - Gosaba | SM/15968 | Augmentation | Development of tube well no-1 at Pathankhali W/S Scheme (Zone-II), Block-Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division |  | ORD/000859/2022-2023 | 288/CSD | 19/05/2022 | 28/06/2022 | S.P. CONSTRUCTION (I) | 0.67 | 0.67 | 100 | 100
2 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Pathankhali PWSS Zone-II for Providing Functional Household Tap Connection (FHTC) Block - Gosaba | SM/15968 | Augmentation | Sinking of 250mm x 150mm dia. 360 mtr. deep replacement tubewell by Direct Rotary Rig Method using UPVC pipe and pre-packed Resin Bonded Gravel Filter at Tube Well No. - 4, Chandipur of Pathankhali Water Supply Scheme Block - Gosaba under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division |  | ORD/001574/2021-2022 | 6955/AD | 29/03/2022 | 28/04/2022 | AQUATECH ENGINEER | 20.64 | 19 | 92.08 | 0
3 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Pathankhali PWSS Zone-II for Providing Functional Household Tap Connection (FHTC) Block - Gosaba | SM/15968 | Augmentation | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Pathankhali W/S Scheme (Zone-II), Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-I] | Assistant Engineer, Canning sub division |  | ORD/001952/2022-2023 | 12688/AD | 14/03/2023 | 28/04/2023 | RAJLAKSHMI ENTERPRISE | 8.92 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Pathankhali PWSS Zone-II for Providing Functional Household Tap Connection (FHTC) Block - Gosaba | SM/15968 | Augmentation | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Pathankhali W/S Scheme (Zone-II), Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-II] | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001953/2022-2023 | 12689/AD | 14/03/2023 | 28/04/2023 | PODDER ENTERPRISE | 8.61 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Pathankhali PWSS Zone-II for Providing Functional Household Tap Connection (FHTC) Block - Gosaba | SM/15968 | Augmentation | Construction of 300 m³ capacity 20 M. staging height R.C.C. Over Head Water Reservoir, Laying distribution system & Providing FHTC etc of Ground Water Based Augmentation of Pathankhali (Zone- II) piped water supply scheme of Gosaba Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. [No. of FHTC = 1153] | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000040/2023-2024 | 175/AD | 19/04/2023 | 13/02/2024 | SAMSUL ENTERPRISE | 483.35 | 237.55 | 49.15 | 60
6 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Pathankhali PWSS Zone-II for Providing Functional Household Tap Connection (FHTC) Block - Gosaba | SM/15968 | Augmentation | Sinking of 02 (Two) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Pathankhali (Zone - II) W/S Scheme, Block - Gosaba under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division |  | ORD/000141/2023-2024 | 277/AD | 24/04/2023 | 08/06/2023 | MONDAL CONSTRUCTION (MADHYAMGRAM) | 43.98 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Pathankhali PWSS Zone-II for Providing Functional Household Tap Connection (FHTC) Block - Gosaba | SM/15968 | Augmentation | Inter connection and rising main with supply of specials of Augmentation of Pathankhali (Zone-II) W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000137/2023-2024 | 692/AD | 18/05/2023 | 02/06/2023 | HI TECH ENTERPRISE | 10.48 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Augmentation of Pathankhali PWSS Zone-II for Providing Functional Household Tap Connection (FHTC) Block - Gosaba | SM/15968 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2, Zone-II for Augmentation of Pathankhali supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Gosaba] | Assistant Engineer | Junior Engineer | ORD/000278/2023-2024 | 1137/SMD | 24/04/2023 | 23/07/2023 | JAL PRAVAHIKA PVT. LTD. | 19.55 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Pathankhali PWSS Zone-II for Providing Functional Household Tap Connection (FHTC) Block - Gosaba | SM/15968 | Augmentation | Conducting route survey, design distribution network and preparation & submission of DPR for Pathankhali (Zone-II) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Gosaba Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division |  | ORD/001927/2022-2023 | 11800/AD | 22/02/2023 | 08/04/2023 | M/S R.DUTTA & CO. | 5.74 | 5.74 | 100 | 95
10 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Pathankhali PWSS Zone-II for Providing Functional Household Tap Connection (FHTC) Block - Gosaba | SM/15968 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000011/2023-2024 | 118/AD | 13/04/2023 | 13/04/2023 | Resource Division | 0.34 | 0 | 0 | 0
11 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Pathankhali PWSS Zone-II for Providing Functional Household Tap Connection (FHTC) Block - Gosaba | SM/15968 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000138/2023-2024 | 857/AD | 27/05/2023 | 27/05/2023 | Resource Division | 1.72 | 0 | 0 | 0
12 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Pathankhali PWSS Zone-II for Providing Functional Household Tap Connection (FHTC) Block - Gosaba | SM/15968 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000050/2023-2024 | 257/AD | 24/04/2023 | 24/04/2023 | Resource Division | 48.14 | 0 | 0 | 0
13 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Pathankhali PWSS Zone-II for Providing Functional Household Tap Connection (FHTC) Block - Gosaba | SM/15968 | Augmentation | Construction of boundary wall at Head Work for Augmentation of Pathakhali (Zone-II) Piped Water Supply Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000731/2024-2025 | 4389/AD | 05/11/2024 | 20/12/2024 | SAMSUL ENTERPRISE | 44.02 | 0 | 0 | 0
14 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Pathankhali PWSS Zone-II for Providing Functional Household Tap Connection (FHTC) Block - Gosaba | SM/15968 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000411/2023-2024 | 367/AD | 19/01/2024 | 19/01/2024 | Resource Division | 7.1 | 0 | 0 | 0
15 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Pathankhali PWSS Zone-II for Providing Functional Household Tap Connection (FHTC) Block - Gosaba | SM/15968 | Augmentation | Construction of boundary wall at Head Work Site for Ground Water Based at Pathankhali (Zone-III) Piped Water Supply Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/002200/2024-2025 | 471/AD | 06/02/2025 | 07/04/2025 | MOUSUMI ENTERPRISE | 29.17 | 0 | 0 | 0
16 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Augmentation of Pathankhali PWSS Zone-II for Providing Functional Household Tap Connection (FHTC) Block - Gosaba | SM/15968 | Augmentation | Quotation for new service( power) connection at Pathankhali Zone-II PH-1 (H/W) Water supply scheme under Gosaba block. Reference ID:-106862453, Application No :-1008269707 |  |  | BILL/02511/2024-2025 | BP-2024-25-550 | 27/01/2025 | 27/01/2025 | WBSEDCL | 11.38 | 0 | 0 | 0
17 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Augmentation of Pathankhali PWSS Zone-II for Providing Functional Household Tap Connection (FHTC) Block - Gosaba | SM/15968 | Augmentation | Quotation for new service( power) connection at Pathankhali Zone-II PH-2 Water supply scheme under Gosaba block. Reference ID:-107071574, Application No :-10085911101 |  |  | BILL/00501/2025-2026 | 42151 | 01/08/2025 | 01/08/2025 | WBSEDCL | 6.8 | 0 | 0 | 0
Total | [13 empty] | 750.61 | 262.96 | 35.03