## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF PURBA RADHANAGAR (ZONE-II) PWSS FOR PROVIDING FHTC, BLOCK - GOSABA | SM/15969 | Augmentation | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Purba Radhanagar W/S Scheme (Zone-II), Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-I] | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001983/2022-2023 | 12644/AD | 13/03/2023 | 27/04/2023 | M/S MA KALI ELECTRIC LIGHT CORPORATION. | 8.83 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF PURBA RADHANAGAR (ZONE-II) PWSS FOR PROVIDING FHTC, BLOCK - GOSABA | SM/15969 | Augmentation | Construction of 350 m³ capacity R.C.C OHR (based on Departmental Design &. Drawing) with 20 mtr. staging height, Laying Distribution System, Providing Functional Household Tap Connection etc. for augmentation of Purba Radhanagar (Zone-II) piped water supply scheme of Gosaba Block under Canning Sub- Division of Alipore Division, PHE Dte. [No. of FHTC = 1296] | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000031/2023-2024 | 124/AD | 13/04/2023 | 13/03/2025 | M N J ENTERPRISES | 492.25 | 198.54 | 40.33 | 52
3 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION AND RETROFITTING OF PURBA RADHANAGAR (ZONE-II) PWSS FOR PROVIDING FHTC, BLOCK - GOSABA | SM/15969 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2, Zone-II for Augmentation of Purba Radhanagar supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Gosaba] | Assistant Engineer | Junior Engineer | ORD/000272/2023-2024 | 1132/SMD | 24/04/2023 | 23/07/2023 | AMIT DAS | 19.54 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF PURBA RADHANAGAR (ZONE-II) PWSS FOR PROVIDING FHTC, BLOCK - GOSABA | SM/15969 | Augmentation | Sinking of 02 (two) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Purba Radhanagar W/S Scheme (Zone-II), Block - Gosaba under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/002032/2022-2023 | 13028/AD | 24/03/2023 | 08/05/2023 | NILAVA GHOSHAL | 43.98 | 0 | 0 | 100
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF PURBA RADHANAGAR (ZONE-II) PWSS FOR PROVIDING FHTC, BLOCK - GOSABA | SM/15969 | Augmentation | Conducting route survey, design distribution network and preparation & submission of DPR for Purba Radhanagar (Zone-II) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Gosaba Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division |  | ORD/001929/2022-2023 | 11802/AD | 22/02/2023 | 08/04/2023 | M/S R.DUTTA & CO. | 4.43 | 4.43 | 100 | 95
6 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF PURBA RADHANAGAR (ZONE-II) PWSS FOR PROVIDING FHTC, BLOCK - GOSABA | SM/15969 | Augmentation | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Purba Radhanagar W/S Scheme (Zone-II), Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-II] | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/002011/2022-2023 | 12917/AD | 21/03/2023 | 01/05/2025 | MISTRY CONSTRUCTION | 8.61 | 0 | 0 | 100
7 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION AND RETROFITTING OF PURBA RADHANAGAR (ZONE-II) PWSS FOR PROVIDING FHTC, BLOCK - GOSABA | SM/15969 | Augmentation | Supply, delivery and installation of 15 KVA servo motor operated Copper wound line voltage stabilizer at P.H. No. 1 of Purba Radhanagar Water Supply Scheme under SMD, PHE Dte. [Block: Gosaba] |  |  | ORD/000298/2023-2024 | 2148/SMD | 06/06/2023 | 21/06/2023 | SHIVAM ENTERPRISE | 2.56 | 2.56 | 100 | 100
8 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF PURBA RADHANAGAR (ZONE-II) PWSS FOR PROVIDING FHTC, BLOCK - GOSABA | SM/15969 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000046/2023-2024 | 253/AD | 23/04/2023 | 23/04/2023 | Resource Division | 17.55 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF PURBA RADHANAGAR (ZONE-II) PWSS FOR PROVIDING FHTC, BLOCK - GOSABA | SM/15969 | Augmentation | Inter connection and rising main with supply of specials of Augmentation of Purba Radhnagar (Zone-II) W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. (3rd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/002350/2023-2024 | 1165/AD | 27/02/2024 | 01/02/2025 | A.K. ENTERPRISE | 6.98 | 0 | 0 | 90
10 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION AND RETROFITTING OF PURBA RADHANAGAR (ZONE-II) PWSS FOR PROVIDING FHTC, BLOCK - GOSABA | SM/15969 | Augmentation | Quotation for new service( power) connection at Aug of Purbaradhanagar Zone-II PH-2 Water supply scheme under Gosaba block. Reference ID:-107071568, Application No :-1008591306 |  |  | BILL/00498/2025-2026 |  | 19/05/2025 | 19/05/2025 | WBSEDCL | 15.47 | 0 | 0 | 0
11 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION AND RETROFITTING OF PURBA RADHANAGAR (ZONE-II) PWSS FOR PROVIDING FHTC, BLOCK - GOSABA | SM/15969 | Augmentation | Quotation for new service( power) connection at Aug of Purbaradhanagar Zone-II PH-1 Water supply scheme under Gosaba block. Reference ID:-107071570, Application No :-1008591277 |  |  | BILL/00497/2025-2026 | 42151 | 01/08/2025 | 01/08/2025 | WBSEDCL | 12.03 | 0 | 0 | 0
Total | [13 empty] | 632.22 | 205.53 | 32.51