## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF BASANTI (ZONE-VII) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15972 | Augmentation | Sinking of 02 (two) Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Basanti W/S Scheme (Zone-VII), Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001919/2022-2023 | 12461/AD | 10/03/2023 | 24/04/2023 | SANDIP SARKAR | 39.12 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF BASANTI (ZONE-VII) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15972 | Augmentation | Conducting route survey, design distribution network and preparation & submission of DPR for Basanti (Zone-VII) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Basanti Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division |  | ORD/001937/2022-2023 | 11808/AD | 22/02/2023 | 08/04/2023 | INDRANIL DUTTA & ASSOCIATES | 4.64 | 4.64 | 100 | 0
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF BASANTI (ZONE-VII) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15972 | Augmentation | Inter connection and rising main with supply of specials of Augmentation of Basanti (Zone-VII) W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000102/2023-2024 | 505/AD | 11/05/2023 | 26/05/2023 | SURYA ENTERPRISE | 7.71 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF BASANTI (ZONE-VII) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15972 | Augmentation | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Basanti W/S Scheme (Zone-VII), Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-I] | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000496/2023-2024 | 1797/AD | 26/07/2023 | 09/09/2023 | MONDAL ENTERPRISE (SALTLAKE) | 7.35 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF BASANTI (ZONE-VII) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15972 | Augmentation | Construction of 250 m³ capacity R.C.C OHR (based on Departmental Design & Drawing) with 20 mtr. staging height including Geo- Technical investigation, foundation, pipeline connection and cost of pipes, specials etc. for augmentation of Basanti (Zone-VII) piped water supply scheme of Basanti Block under Canning Sub- Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000625/2023-2024 | 4327/AD | 01/12/2023 | 26/09/2024 | R.S.CONSTRUCTION CO. | 105.35 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF BASANTI (ZONE-VII) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15972 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000027/2023-2024 | 232/AD | 24/04/2023 | 24/04/2023 | Resource Division | 36.13 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF BASANTI (ZONE-VII) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15972 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000156/2023-2024 | 1049/AD | 15/06/2023 | 15/06/2023 | Resource Division | 5.86 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF BASANTI (ZONE-VII) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15972 | Augmentation | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) of Augmentation of Basanti (Zone-III and VII) W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [No. of FHTC = 1767] | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD | ORD/000257/2023-2024 | 1445/AD | 13/07/2023 | 11/09/2023 | M/S SWAPAN KUMAR PRADHAN | 103.39 | 0 | 0 | 35
9 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF BASANTI (ZONE-VII) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15972 | Augmentation | RESTORATION OF KOLKATA BASANTI ROAD FROM 68.00 TO 96.255 KM BLOCK CANNING I UNDER SOUTH 24 PARGANAS HIGHWAY DIVISION, DAMAGED CAUSED DUE TO LAYING OF WATER PIPE LINE BY PHED UNDER CSD |  |  | BILL/01320/2024-2025 | BP-2024-25-684 | 04/10/2024 | 04/10/2024 | EXECUTIVE ENGNEER, 24 PGS. HIGHWAY DIVN, P.W.(ROADS) DEPTT. | 416.07 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION & RETROFITTING OF BASANTI (ZONE-VII) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15972 | Augmentation | Charges for new service connection at pump house no- 1 of Basanti (Zone-VII) |  |  | BILL/01839/2024-2025 | BP-2024-25-466 | 18/11/2024 | 18/11/2024 | WBSEDCL | 19.02 | 0 | 0 | 0
11 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF BASANTI (ZONE-VII) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15972 | Augmentation | Laying Distribution system for Augmentation of Basanti W/S Scheme (Zone - VII), Block - Basanti under Canning Sub - Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000127/2023-2024 | 145/AD | 17/04/2023 | 13/08/2025 | ARISTOCON ENGINEERS'CO-OP. SOCIETY LTD. | 161.26 | 144.18 | 89.41 | 95
12 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION & RETROFITTING OF BASANTI (ZONE-VII) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15972 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 Zone-VII of Basanti water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Basanti] | Assistant Engineer | Junior Engineer | ORD/001505/2022-2023 | 874/SMD | 23/03/2023 | 01/01/2026 | WESTERN ENGINEERING CO. | 21.14 | 0 | 0 | 45
13 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION & RETROFITTING OF BASANTI (ZONE-VII) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15972 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at PH-1 of Basanti (Zone-VII) W/S Scheme under SMD, P.H.E. Dte.(Block-Basanti)(SM/15972) | Assistant Engineer | Junior Engineer | ORD/002225/2024-2025 | 396/SMSD | 19/03/2025 | 03/04/2025 | WESTERN ENGINEERING CO. | 0.92 | 0 | 0 | 0
14 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF BASANTI (ZONE-VII) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15972 | Augmentation | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Basanti W/S Scheme (Zone-VII) , Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-II] | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000498/2023-2024 | 1798/AD | 26/07/2023 | 04/04/2025 | B.S.ENTERPRISE | 7.09 | 0 | 0 | 100
Total | [13 empty] | 935.03 | 148.81 | 15.92