## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF SATJELIA (ZONE-II) PWSS FOR PROVIDING FHTC, BLOCK - GOSABA | SM/15973 | Augmentation | Conducting route survey, design distribution network and preparation & submission of DPR for Satjelia (Zone-II) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Gosaba Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division |  | ORD/001849/2022-2023 | 11815/AD | 23/02/2023 | 09/04/2023 | TECH VISION | 3.89 | 3.89 | 100 | 0
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF SATJELIA (ZONE-II) PWSS FOR PROVIDING FHTC, BLOCK - GOSABA | SM/15973 | Augmentation | Construction of 150 m³ capacity 20 M. staging height R.C.C. Over Head Water Reservoir, Laying distribution system & Providing FHTC etc of Ground Water Based Augmentation Piped W/S Scheme for Satjelia (Zone-II) Block - Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. [No. of FHTC = 1076] | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000039/2023-2024 | 1289/AD | 06/07/2023 | 01/05/2025 | PATHIK PABAN NANDI | 429.73 | 206.56 | 48.07 | 56
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF SATJELIA (ZONE-II) PWSS FOR PROVIDING FHTC, BLOCK - GOSABA | SM/15973 | Augmentation | Sinking of 02 (two) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Satjelia W/S Scheme (Zone - II), Block - Gosaba under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/002036/2022-2023 | 13032/AD | 24/03/2023 | 08/05/2023 | TAPAN DAS (NEW) | 43.96 | 34.27 | 77.96 | 25
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF SATJELIA (ZONE-II) PWSS FOR PROVIDING FHTC, BLOCK - GOSABA | SM/15973 | Augmentation | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Satjelia W/S Scheme (Zone-II), Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-I] | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/002009/2022-2023 | 12915/AD | 21/03/2023 | 05/05/2023 | MONDAL CONSTRUCTION (SANDESHKHALI) | 8.92 | 8.18 | 91.79 | 98
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF SATJELIA (ZONE-II) PWSS FOR PROVIDING FHTC, BLOCK - GOSABA | SM/15973 | Augmentation | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Satjelia W/S Scheme (Zone-II), Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-II] | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001979/2022-2023 | 12640/AD | 13/03/2023 | 27/04/2023 | R.G. ENTERPRISE (I) | 8.59 | 8.29 | 96.44 | 100
6 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION AND RETROFITTING OF SATJELIA (ZONE-II) PWSS FOR PROVIDING FHTC, BLOCK - GOSABA | SM/15973 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 Zone-II for Augmentation of Satjelia water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Gpsaba] | Assistant Engineer | Junior Engineer | ORD/000275/2023-2024 | 1135/SMD | 24/04/2023 | 05/06/2025 | UNIVERSAL ENTERPRISES | 22.53 | 21.36 | 94.81 | 90
7 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF SATJELIA (ZONE-II) PWSS FOR PROVIDING FHTC, BLOCK - GOSABA | SM/15973 | Augmentation | Inter connection and rising main with supply of specials of Augmentation of Satjelia (Zone-II) W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. (2nd call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000235/2023-2024 | 1388/AD | 12/07/2023 | 01/08/2024 | S.S.COMSULTANCY & CONSTRUCTION | 21.99 | 0 | 0 | 90
8 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF SATJELIA (ZONE-II) PWSS FOR PROVIDING FHTC, BLOCK - GOSABA | SM/15973 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000052/2023-2024 | 259/AD | 24/04/2023 | 24/04/2023 | Resource Division | 42.97 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION AND RETROFITTING OF SATJELIA (ZONE-II) PWSS FOR PROVIDING FHTC, BLOCK - GOSABA | SM/15973 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/04079/2023-2024 | BP-2023-24-416 | 16/12/2023 | 16/12/2023 | WBSEDCL | 3.62 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION AND RETROFITTING OF SATJELIA (ZONE-II) PWSS FOR PROVIDING FHTC, BLOCK - GOSABA | SM/15973 | Augmentation | Improvement of outdoor illumination arrangement with allied works at Satjelia Zone-II PH-2, under Gosaba Block water supply sche under SMD,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001855/2024-2025 | 1084/SMSD | 31/07/2024 | 15/08/2024 | SARVATAH PROJECTS PRIVATE LIMITED | 0.88 | 0 | 0 | 100
11 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION AND RETROFITTING OF SATJELIA (ZONE-II) PWSS FOR PROVIDING FHTC, BLOCK - GOSABA | SM/15973 | Augmentation | Improvement of outdoor illumination arrangement with allied works at Satjelia Zone-II PH-1, under Gosaba Block water supply sche under SMD,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001854/2024-2025 | 1085/SMSD | 31/07/2024 | 15/08/2024 | SARVATAH PROJECTS PRIVATE LIMITED | 0.88 | 0 | 0 | 100
12 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF SATJELIA (ZONE-II) PWSS FOR PROVIDING FHTC, BLOCK - GOSABA | SM/15973 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000414/2023-2024 | 370/AD | 19/01/2024 | 19/01/2024 | Resource Division | 6.62 | 0 | 0 | 0
13 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION AND RETROFITTING OF SATJELIA (ZONE-II) PWSS FOR PROVIDING FHTC, BLOCK - GOSABA | SM/15973 | Augmentation | PAYMENT OF ELECTRICITY BILL FOR NEW SERVICE CONNECTION UNDER SMD PHE DTE. |  |  | BILL/04682/2023-2024 | BP-2023-24-504 | 12/02/2024 | 12/02/2024 | WBSEDCL | 8.16 | 0 | 0 | 0
Total | [13 empty] | 602.75 | 282.55 | 46.88