## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF PURBA RADHANAGAR (ZONE-III) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15974 | Augmentation | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Purba Radhanagar W/S Scheme (Zone-III), Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-II] | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/002013/2022-2023 | 12919/AD | 21/03/2023 | 05/05/2023 | M/S JAHANGIR SARDAR | 8.61 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF PURBA RADHANAGAR (ZONE-III) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15974 | Augmentation | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Purba Radhanagar W/S Scheme (Zone-III), Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-III] | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/002038/2022-2023 | 13034/AD | 24/03/2023 | 08/05/2023 | MAA SOLAR ENTERPRISE | 8.61 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF PURBA RADHANAGAR (ZONE-III) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15974 | Augmentation | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Purba Radhanagar W/S Scheme (Zone-III), Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-I] | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/002012/2022-2023 | 12918/AD | 21/03/2023 | 05/05/2023 | M/S JAHANGIR SARDAR | 8.92 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF PURBA RADHANAGAR (ZONE-III) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15974 | Augmentation | Construction of 350 m³ capacity R.C.C OHR (based on Departmental Design &. Drawing) with 20 mtr. staging height, Laying Distribution System, Providing Functional Household Tap Connection etc. for augmentation of Purba Radhanagar (Zone-III) piped water supply scheme of Gosaba Block under Canning Sub- Division of Alipore Division, PHE Dte. [No. of FHTC = 1382] | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000133/2023-2024 | 757/AD | 23/05/2023 | 26/02/2026 | M N J ENTERPRISES | 519.69 | 217.25 | 41.8 | 53
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF PURBA RADHANAGAR (ZONE-III) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15974 | Augmentation | Sinking of 03 (three) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Purba Radhanagar W/S Scheme (Zone-III), Block - Gosaba under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000139/2023-2024 | 199/AD | 19/04/2023 | 18/06/2023 | M/S ABDUL BARIK | 65.94 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF PURBA RADHANAGAR (ZONE-III) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15974 | Augmentation | Inter connection and rising main with supply of specials of Augmentation of Purba Radhanagar (Zone-III) W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000096/2023-2024 | 452/AD | 08/05/2023 | 23/05/2023 | M/S ARIYAN ENTERPRISE | 13.19 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION & RETROFITTING OF PURBA RADHANAGAR (ZONE-III) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15974 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2, Zone-III for Augmentation of Purba Radhanagar supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Gosaba] | Assistant Engineer | Junior Engineer | ORD/000271/2023-2024 | 1131/SMD | 24/04/2023 | 23/07/2023 | SHIVAM ENTERPRISE | 19.55 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF PURBA RADHANAGAR (ZONE-III) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15974 | Augmentation | Conducting route survey, design distribution network and preparation & submission of DPR for Purba Radhanagar (Zone-III) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Gosaba Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division |  | ORD/001930/2022-2023 | 11803/AD | 22/02/2023 | 08/04/2023 | M/S R.DUTTA & CO. | 4.65 | 4.65 | 100 | 95
9 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF PURBA RADHANAGAR (ZONE-III) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15974 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000047/2023-2024 | 254/AD | 24/04/2023 | 24/04/2023 | Resource Division | 60.78 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION & RETROFITTING OF PURBA RADHANAGAR (ZONE-III) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15974 | Augmentation | Quotation for new service( power) connection at Aug of Purbaradhanagar Zone-III PH-1 Water supply scheme under Gosaba block. Reference ID:-107071571, Application No :-1008591154 |  |  | BILL/00500/2025-2026 |  | 19/05/2025 | 19/05/2025 | WBSEDCL | 6.4 | 0 | 0 | 0
11 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION & RETROFITTING OF PURBA RADHANAGAR (ZONE-III) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15974 | Augmentation | Quotation for new service( power) connection at Aug of Purbaradhnagar Zone-III PH-2 Water supply scheme under Gosaba block. Reference ID:-107071572, Application No :-1008591246 |  |  | BILL/00499/2025-2026 | 42151 | 01/08/2025 | 01/08/2025 | WBSEDCL | 11.45 | 0 | 0 | 0
Total | [13 empty] | 727.78 | 221.9 | 30.49