## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF BASANTI (ZONE-IV) PWSS FOR PROVIDING FHTC, BLOCK - BASANTI | SM/15975 | Augmentation | Conducting route survey, design distribution network and preparation & submission of DPR for Basanti (Zone-IV) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Basanti Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division |  | ORD/001934/2022-2023 | 11806/AD | 22/02/2023 | 08/04/2023 | INDRANIL DUTTA & ASSOCIATES | 6.33 | 6.33 | 100 | 99
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF BASANTI (ZONE-IV) PWSS FOR PROVIDING FHTC, BLOCK - BASANTI | SM/15975 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000153/2023-2024 | 1057/AD | 15/06/2023 | 15/06/2023 | Resource Division | 9.36 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF BASANTI (ZONE-IV) PWSS FOR PROVIDING FHTC, BLOCK - BASANTI | SM/15975 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000024/2023-2024 | 230/AD | 24/04/2023 | 24/04/2023 | Resource Division | 32.96 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF BASANTI (ZONE-IV) PWSS FOR PROVIDING FHTC, BLOCK - BASANTI | SM/15975 | Augmentation | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Basanti W/S Scheme (Zone-IV), Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-I] | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/001990/2022-2023 | 12681/AD | 14/03/2023 | 28/04/2023 | GOUTAM HALDAR (I) | 7.36 | 7.23 | 98.22 | 98
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF BASANTI (ZONE-IV) PWSS FOR PROVIDING FHTC, BLOCK - BASANTI | SM/15975 | Augmentation | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Basanti W/S Scheme (Zone-IV) , Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-II] | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/001991/2022-2023 | 12682/AD | 14/03/2023 | 28/04/2023 | GOUTAM HALDAR (I) | 7.11 | 6.49 | 91.32 | 99
6 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF BASANTI (ZONE-IV) PWSS FOR PROVIDING FHTC, BLOCK - BASANTI | SM/15975 | Augmentation | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Basanti W/S Scheme (Zone-IV) , Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-III] | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/001992/2022-2023 | 12683/AD | 14/03/2023 | 12/06/2023 | NATH CONSTRUCTION | 7.08 | 6.51 | 91.98 | 98
7 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF BASANTI (ZONE-IV) PWSS FOR PROVIDING FHTC, BLOCK - BASANTI | SM/15975 | Augmentation | Sinking of 03 (three) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Augmentation of Basanti (Zone-IV) W/S Scheme, Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/001869/2022-2023 | 12522/AD | 10/03/2023 | 09/05/2023 | G.B. CONSTRUCTION (TW) | 59.73 | 57.62 | 96.47 | 100
8 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION AND RETROFITTING OF BASANTI (ZONE-IV) PWSS FOR PROVIDING FHTC, BLOCK - BASANTI | SM/15975 | Augmentation | Charges for new service connection at pump house no-1 of Basanti (Zone-IV) |  |  | BILL/00565/2024-2025 | BP-2024-25-133 | 26/06/2024 | 26/06/2024 | WBSEDCL | 10.08 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION AND RETROFITTING OF BASANTI (ZONE-IV) PWSS FOR PROVIDING FHTC, BLOCK - BASANTI | SM/15975 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/04393/2023-2024 | BP-2023-24-442 | 05/01/2024 | 05/01/2024 | WBSEDCL | 4.05 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION AND RETROFITTING OF BASANTI (ZONE-IV) PWSS FOR PROVIDING FHTC, BLOCK - BASANTI | SM/15975 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/04392/2023-2024 | BP-2023-24-441 | 05/01/2024 | 05/01/2024 | WBSEDCL | 6.52 | 0 | 0 | 0
11 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF BASANTI (ZONE-IV) PWSS FOR PROVIDING FHTC, BLOCK - BASANTI | SM/15975 | Augmentation | Construction of OHR, Laying of Distribution System, Providing Functional Household Tap Connection of Augmentation Piped Water Supply Scheme for Basanti (Zone-I, II, IV, V & VI), Block-Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [No of FHTC=9052] | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000349/2023-2024 | 1659/AD | 20/07/2023 | 05/01/2026 | M/S PATH MAKERS | 2061.38 | 176.97 | 8.59 | 78
12 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF BASANTI (ZONE-IV) PWSS FOR PROVIDING FHTC, BLOCK - BASANTI | SM/15975 | Augmentation | Inter connection and rising main with supply of specials of Augmentation of Basanti (Zone-IV) W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000731/2023-2024 | 2892/AD | 19/09/2023 | 04/10/2023 | SURYA ENTERPRISE | 9.53 | 0 | 0 | 97
13 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION AND RETROFITTING OF BASANTI (ZONE-IV) PWSS FOR PROVIDING FHTC, BLOCK - BASANTI | SM/15975 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2 & 3 Zone-IV of Basanti water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Basanti] | Assistant Engineer | Junior Engineer | ORD/001507/2022-2023 | 883/SMD | 24/03/2023 | 01/04/2025 | M/S. DILIP MITRA | 31.71 | 19.58 | 61.74 | 100
14 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION AND RETROFITTING OF BASANTI (ZONE-IV) PWSS FOR PROVIDING FHTC, BLOCK - BASANTI | SM/15975 | Augmentation | Supply & Fixing main switch & Bus bar at Pump House no-2 of Basanti (Zone-II) W/S Scheme under SMD, P.H.E. Dte.(Block-Basanti) | Assistant Engineer | Junior Engineer | ORD/001283/2024-2025 | 27/SMSD | 07/01/2025 | 22/01/2025 | JAI BHARAT COMMERCIAL CORPORATION | 0.29 | 0 | 0 | 100
15 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF BASANTI (ZONE-IV) PWSS FOR PROVIDING FHTC, BLOCK - BASANTI | SM/15975 | Augmentation | Additional laying of pipeline at Augmentation of Basanti (Zone-I, II, IV, V & VI) W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. (SM/15053, SM/15959, SM/15975, SM/15052 & SM/15976) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/001223/2024-2025 | 5181/AD | 13/12/2024 | 11/02/2025 | ARNAB ENTERPRISE (HABRA) | 113.4 | 28.35 | 25 | 99
16 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF BASANTI (ZONE-IV) PWSS FOR PROVIDING FHTC, BLOCK - BASANTI | SM/15975 | Augmentation | Laying pipe line at Augmentation of Basanti (Zone-IV) W/S Scheme Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000408/2024-2025 | 3197/AD | 01/08/2024 | 29/11/2024 | MONDAL ENTERPRISE (MURSHIDABAD) | 36.59 | 26.98 | 73.74 | 99
17 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION AND RETROFITTING OF BASANTI (ZONE-IV) PWSS FOR PROVIDING FHTC, BLOCK - BASANTI | SM/15975 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no-2 of Basanti (Zone-II) W/S Scheme under SMD, P.H.E. Dte.(Block-Basanti) | Assistant Engineer | Junior Engineer | ORD/001282/2024-2025 | 28/SMSD | 07/01/2025 | 22/01/2025 | JAI BHARAT COMMERCIAL CORPORATION | 0.91 | 0 | 0 | 100
18 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION AND RETROFITTING OF BASANTI (ZONE-IV) PWSS FOR PROVIDING FHTC, BLOCK - BASANTI | SM/15975 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no.1 of Basanti (Zone-IV) W/S Scheme under SMD, P.H.E. Dte. (Block-Basanti)(SM/15975) | Assistant Engineer | Junior Engineer | ORD/003079/2023-2024 | 378/SMSD | 21/03/2024 | 01/01/2025 | M/S. DILIP MITRA | 0.9 | 0 | 0 | 100
19 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION AND RETROFITTING OF BASANTI (ZONE-IV) PWSS FOR PROVIDING FHTC, BLOCK - BASANTI | SM/15975 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no.2 of Basanti (Zone-IV) W/S Scheme under SMD, P.H.E. Dte. (Block-Basanti)(SM/15975) | Assistant Engineer | Junior Engineer | ORD/003080/2023-2024 | 379/SMSD | 21/03/2024 | 01/06/2024 | M/S. DILIP MITRA | 0.9 | 0 | 0 | 100
20 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION AND RETROFITTING OF BASANTI (ZONE-IV) PWSS FOR PROVIDING FHTC, BLOCK - BASANTI | SM/15975 | Augmentation | Supply & installation of LED board at P.H. No-3 of Basanti (Zone-IV) & BASANTI (Zone-V) water supply scheme, under South 24-Pgs Mechanical Division PHE Dte.[Block-Basanti] | Assistant Engineer | Junior Engineer | ORD/001762/2024-2025 | 259/SMSD | 20/02/2025 | 07/03/2025 | KARUNAMOY ENGINEERING | 0.78 | 0 | 0 | 100
21 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION AND RETROFITTING OF BASANTI (ZONE-IV) PWSS FOR PROVIDING FHTC, BLOCK - BASANTI | SM/15975 | Augmentation | Supply & installation of LED board at P.H. No-2 & 3 of Basanti (Zone-IV) water supply scheme, under South 24-Pgs Mechanical Division PHE Dte.[Block-Basanti] | Assistant Engineer | Junior Engineer | ORD/000821/2024-2025 | 1596/SMSD | 04/12/2024 | 19/12/2024 | MONOSEBA CONSTRUCTION | 0.78 | 0 | 0 | 100
22 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION AND RETROFITTING OF BASANTI (ZONE-IV) PWSS FOR PROVIDING FHTC, BLOCK - BASANTI | SM/15975 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no. 3 of Basanti (Zone-IV) W/S Scheme under SMD, P.H.E. Dte. (Block-Basanti)(SM/15975) | Assistant Engineer | Junior Engineer | ORD/003081/2023-2024 | 380/SMSD | 21/03/2024 | 01/01/2025 | M/S. DILIP MITRA | 0.9 | 0 | 0 | 100
23 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION AND RETROFITTING OF BASANTI (ZONE-IV) PWSS FOR PROVIDING FHTC, BLOCK - BASANTI | SM/15975 | Augmentation | Supply & Fixing main switch & Bus bar at Pump House no-1 ,2 & 3 of Basanti (Zone-IV) W/S Scheme under SMD, P.H.E. Dte.(Block-Basanti)(SM/15975) | Assistant Engineer | Junior Engineer | ORD/003078/2023-2024 | 377/SMSD | 21/03/2024 | 01/01/2025 | M/S. DILIP MITRA | 0.87 | 0 | 0 | 100
Total | [13 empty] | 2409.52 | 336.05 | 13.95