## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF BASANTI (ZONE-VI) PWSS FOR PROVIDING FHTC, BLOCK - BASANTI | SM/15976 | Augmentation | Conducting route survey, design distribution network and preparation & submission of DPR for Basanti (Zone-VI) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Basanti Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division |  | ORD/001936/2022-2023 | 11807/AD | 22/02/2023 | 08/04/2023 | INDRANIL DUTTA & ASSOCIATES | 5.26 | 5.26 | 100 | 0
2 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION AND RETROFITTING OF BASANTI (ZONE-VI) PWSS FOR PROVIDING FHTC, BLOCK - BASANTI | SM/15976 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 Zone-VI of Basanti water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Basanti] | Assistant Engineer | Junior Engineer | ORD/001508/2022-2023 | 884/SMD | 24/03/2023 | 22/06/2023 | BHUNIA BUILDERS | 10.41 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF BASANTI (ZONE-VI) PWSS FOR PROVIDING FHTC, BLOCK - BASANTI | SM/15976 | Augmentation | Inter connection and rising main with supply of specials of Augmentation of Basanti (Zone-VI) W/S Scheme , Block-Canning- I under Canning Sub-Division of Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000728/2023-2024 | 2889/AD | 19/09/2023 | 04/10/2023 | A.K. ENTERPRISE (II) | 11.16 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF BASANTI (ZONE-VI) PWSS FOR PROVIDING FHTC, BLOCK - BASANTI | SM/15976 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000026/2023-2024 | 232/AD | 24/04/2023 | 24/04/2023 | Resource Division | 63.43 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF BASANTI (ZONE-VI) PWSS FOR PROVIDING FHTC, BLOCK - BASANTI | SM/15976 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000155/2023-2024 | 1044/AD | 15/06/2023 | 15/06/2023 | Resource Division | 7.03 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF BASANTI (ZONE-VI) PWSS FOR PROVIDING FHTC, BLOCK - BASANTI | SM/15976 | Augmentation | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Basanti W/S Scheme (Zone-VI) , Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/001993/2022-2023 | 12684/AD | 14/03/2023 | 28/04/2023 | NATH CONSTRUCTION | 7.08 | 0 | 0 | 1
7 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF BASANTI (ZONE-VI) PWSS FOR PROVIDING FHTC, BLOCK - BASANTI | SM/15976 | Augmentation | Construction of 1 (one) no. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Basanti W/S Scheme (Zone-VI), Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House No. III] | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000317/2024-2025 | 2698/AD | 24/06/2024 | 08/08/2024 | MOSTAFIZUR HAQUE GAINE | 7.08 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF BASANTI (ZONE-VI) PWSS FOR PROVIDING FHTC, BLOCK - BASANTI | SM/15976 | Augmentation | Sinking of 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Basanti W/S Scheme (Zone-VI), Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. (Tube well no. - III) (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000786/2024-2025 | 4486/AD | 11/11/2024 | 11/12/2024 | SNEHA CONSTRUCTION | 19.59 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF BASANTI (ZONE-VI) PWSS FOR PROVIDING FHTC, BLOCK - BASANTI | SM/15976 | Augmentation | Construction of 1 (one) no. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Basanti W/S Scheme (Zone-VI), Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House No. II] | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000316/2024-2025 | 2697/AD | 24/06/2024 | 08/08/2024 | MOSTAFIZUR HAQUE GAINE | 7.08 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF BASANTI (ZONE-VI) PWSS FOR PROVIDING FHTC, BLOCK - BASANTI | SM/15976 | Augmentation | Construction of OHR, Laying of Distribution System, Providing Functional Household Tap Connection of Augmentation Piped Water Supply Scheme for Basanti (Zone-I, II, IV, V & VI), Block-Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [No of FHTC=9052] | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000349/2023-2024 | 1659/AD | 20/07/2023 | 05/01/2026 | M/S PATH MAKERS | 2061.38 | 189.92 | 9.21 | 78
11 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF BASANTI (ZONE-VI) PWSS FOR PROVIDING FHTC, BLOCK - BASANTI | SM/15976 | Augmentation | Additional laying of pipeline at Augmentation of Basanti (Zone-I, II, IV, V & VI) W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. (SM/15053, SM/15959, SM/15975, SM/15052 & SM/15976) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/001223/2024-2025 | 5181/AD | 13/12/2024 | 11/02/2025 | ARNAB ENTERPRISE (HABRA) | 113.4 | 28.35 | 25 | 99
12 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF BASANTI (ZONE-VI) PWSS FOR PROVIDING FHTC, BLOCK - BASANTI | SM/15976 | Augmentation | Sinking of 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Basanti W/S Scheme (Zone-VI), Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. (Tube well no. - II) (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000784/2024-2025 | 4485/AD | 11/11/2024 | 30/06/2025 | SNEHA CONSTRUCTION | 19.59 | 0 | 0 | 98
13 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION AND RETROFITTING OF BASANTI (ZONE-VI) PWSS FOR PROVIDING FHTC, BLOCK - BASANTI | SM/15976 | Augmentation | Charges for new service connection at pump house no- 1 of Basanti (Zone-VI) water supply scheme under Basanti block. |  |  | BILL/03086/2024-2025 | BP-2024-25-625 | 29/03/2025 | 29/03/2025 | WBSEDCL | 5.87 | 0 | 0 | 0
Total | [13 empty] | 2338.35 | 223.52 | 9.56