## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF SATJELIA (ZONE-III) PWSS FOR PROVIDING FHTC, BLOCK - GOSABA | SM/15992 | Augmentation | Conducting route survey, design distribution network and preparation & submission of DPR for Satjelia (Zone-III) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Gosaba Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division |  | ORD/001850/2022-2023 | 11816/AD | 23/02/2023 | 09/04/2023 | TECH VISION | 4.2 | 4.2 | 100 | 0
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF SATJELIA (ZONE-III) PWSS FOR PROVIDING FHTC, BLOCK - GOSABA | SM/15992 | Augmentation | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Satjelia W/S Scheme (Zone-III), Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-I] | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001980/2022-2023 | 12641/AD | 13/03/2023 | 27/04/2023 | R.G. ENTERPRISE (I) | 8.9 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF SATJELIA (ZONE-III) PWSS FOR PROVIDING FHTC, BLOCK - GOSABA | SM/15992 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000053/2023-2024 | 260/AD | 24/04/2023 | 24/04/2023 | Resource Division | 50.2 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF SATJELIA (ZONE-III) PWSS FOR PROVIDING FHTC, BLOCK - GOSABA | SM/15992 | Augmentation | Sinking of 02 (two) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Satjelia W/S Scheme (Zone - III), Block - Gosaba under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000140/2023-2024 | 276/AD | 24/04/2023 | 08/07/2023 | GOLDEN ENTERPRISE | 43.97 | 40.72 | 92.61 | 100
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF SATJELIA (ZONE-III) PWSS FOR PROVIDING FHTC, BLOCK - GOSABA | SM/15992 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000415/2023-2024 | 371/AD | 19/01/2024 | 19/01/2024 | Resource Division | 7.83 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION AND RETROFITTING OF SATJELIA (ZONE-III) PWSS FOR PROVIDING FHTC, BLOCK - GOSABA | SM/15992 | Augmentation | Quotation for new service ( power ) connection at Satjelia Zone-III , PH-2 under Gosaba block (REF ID : 106521065) (APP ID: 1007603702) |  |  | BILL/01384/2024-2025 | BP-2024-25-347 | 09/09/2024 | 09/09/2024 | WBSEDCL | 4.52 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION AND RETROFITTING OF SATJELIA (ZONE-III) PWSS FOR PROVIDING FHTC, BLOCK - GOSABA | SM/15992 | Augmentation | PAYMENT OF ELECTRICITY BILL FOR NEW SERVICE CONNECTION UNDER SMD PHE DTE. |  |  | BILL/05702/2023-2024 | BP-2023-24-604 | 28/03/2024 | 28/03/2024 | WBSEDCL | 6.92 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF SATJELIA (ZONE-III) PWSS FOR PROVIDING FHTC, BLOCK - GOSABA | SM/15992 | Augmentation | Construction of 200 m³ capacity 20 M. staging height R.C.C. Over Head Water Reservoir, Laying distribution system & Providing FHTC etc of Ground Water Based Augmentation Piped W/S Scheme for Satjelia (Zone-III) Block - Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. [No. of FHTC = 1271] | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000261/2023-2024 | 1449/AD | 13/07/2023 | 01/06/2025 | SUBHO CONSTRUCTION | 389.99 | 201.39 | 51.64 | 71
9 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF SATJELIA (ZONE-III) PWSS FOR PROVIDING FHTC, BLOCK - GOSABA | SM/15992 | Augmentation | Inter connection and rising main with supply of specials of Augmentation of Satjelia (Zone-III) W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000101/2023-2024 | 504/AD | 11/05/2023 | 01/07/2025 | M/S. BISWAS CONSTRUCTION(I) | 23.87 | 0 | 0 | 80
10 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION AND RETROFITTING OF SATJELIA (ZONE-III) PWSS FOR PROVIDING FHTC, BLOCK - GOSABA | SM/15992 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 Zone-III for Augmentation of Satjelia water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Gpsaba] | Assistant Engineer ,Assistant Engineer -I | Junior Engineer | ORD/000277/2023-2024 | 1138/SMD | 24/04/2023 | 14/10/2027 | JAL PRAVAHIKA PVT. LTD. | 21.7 | 0 | 0 | 45
11 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF SATJELIA (ZONE-III) PWSS FOR PROVIDING FHTC, BLOCK - GOSABA | SM/15992 | Augmentation | Laying additional pipeline and other allied works at Augmentation of Satjelia (Zone - III) W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000310/2024-2025 | 2691/AD | 24/06/2024 | 01/09/2025 | R.S.CONSTRUCTION CO. | 65.49 | 0 | 0 | 40
12 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF SATJELIA (ZONE-III) PWSS FOR PROVIDING FHTC, BLOCK - GOSABA | SM/15992 | Augmentation | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Satjelia W/S Scheme (Zone-III), Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-II] | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/002010/2022-2023 | 12916/AD | 21/03/2023 | 01/08/2024 | MISTRY CONSTRUCTION | 8.61 | 0 | 0 | 100
Total | [13 empty] | 636.2 | 246.31 | 38.72