## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF SATJELIA (ZONE-I) PWSS FOR PROVIDING FHTC, BLOCK - GOSABA | SM/16002 | Augmentation | Conducting route survey, design distribution network and preparation & submission of DPR for Satjelia (Zone-I) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Gosaba Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division |  | ORD/001847/2022-2023 | 11814/AD | 23/02/2023 | 09/04/2023 | TECH VISION | 3.82 | 3.82 | 100 | 0
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF SATJELIA (ZONE-I) PWSS FOR PROVIDING FHTC, BLOCK - GOSABA | SM/16002 | Augmentation | Inter connection and rising main with supply of specials of Augmentation of Satjelia (Zone-I) W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000100/2023-2024 | 503/AD | 11/05/2023 | 26/05/2023 | S.P. CONSTRUCTION (I) | 18.49 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION AND RETROFITTING OF SATJELIA (ZONE-I) PWSS FOR PROVIDING FHTC, BLOCK - GOSABA | SM/16002 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2 & 3, Zone-I for Augmentation of Satjelia Water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Gosaba] | Assistant Engineer | Junior Engineer | ORD/000273/2023-2024 | 1134/SMD | 24/04/2023 | 20/10/2025 | UNIVERSAL ENTERPRISES | 29.32 | 0 | 0 | 90
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF SATJELIA (ZONE-I) PWSS FOR PROVIDING FHTC, BLOCK - GOSABA | SM/16002 | Augmentation | Construction of 200 M3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir, Laying distribution system & Providing FHTC etc of Ground Water Based Augmentation Piped W/S Scheme for Satjelia (Zone-I) Block - Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. [No. of FHTC = 1893] | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001071/2023-2024 | 3508/AD | 16/10/2023 | 11/08/2024 | PATHIK PABAN NANDI | 512.98 | 275.4 | 53.69 | 60
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF SATJELIA (ZONE-I) PWSS FOR PROVIDING FHTC, BLOCK - GOSABA | SM/16002 | Augmentation | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Satjelia W/S Scheme (Zone-I), Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-III] | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/002008/2022-2023 | 12914/AD | 21/03/2023 | 01/08/2024 | MONDAL CONSTRUCTION (SANDESHKHALI) | 8.61 | 0 | 0 | 100
6 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF SATJELIA (ZONE-I) PWSS FOR PROVIDING FHTC, BLOCK - GOSABA | SM/16002 | Augmentation | Sinking of 03 (three) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Satjelia W/S Scheme (Zone - I), Block - Gosaba under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/002035/2022-2023 | 13031/AD | 24/03/2023 | 22/07/2023 | SADIKUL ISLAM | 65.92 | 60.91 | 92.39 | 90
7 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF SATJELIA (ZONE-I) PWSS FOR PROVIDING FHTC, BLOCK - GOSABA | SM/16002 | Augmentation | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Satjelia W/S Scheme (Zone-I), Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-II] | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001978/2022-2023 | 12639/AD | 13/03/2023 | 01/08/2024 | M/S. BISWAS CONSTRUCTION(I) | 8.6 | 0 | 0 | 100
8 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION AND RETROFITTING OF SATJELIA (ZONE-I) PWSS FOR PROVIDING FHTC, BLOCK - GOSABA | SM/16002 | Augmentation | Supply and Installation of Phase Reversal arrangement including all electrical connection complete at PH No 1 & 2, of Satjelia W/S Scheme under South 24-Pgs Mechanical Division, PHE Dte. (Block-Gosaba) |  |  | ORD/002294/2022-2023 | ..321/SMSD | 31/03/2023 | 21/04/2023 | JECLAT ENGINEERING CO-OPERATIVE SOCIETY LTD. | 0.87 | 0.87 | 100 | 100
9 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF SATJELIA (ZONE-I) PWSS FOR PROVIDING FHTC, BLOCK - GOSABA | SM/16002 | Augmentation | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Satjelia W/S Scheme (Zone-I), Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-I] | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001975/2022-2023 | 12638/AD | 13/03/2023 | 27/04/2023 | M/S. BISWAS CONSTRUCTION(I) | 8.91 | 8.63 | 96.86 | 100
10 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF SATJELIA (ZONE-I) PWSS FOR PROVIDING FHTC, BLOCK - GOSABA | SM/16002 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000051/2023-2024 | 258/AD | 24/04/2023 | 24/04/2023 | Resource Division | 44.96 | 0 | 0 | 0
11 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF SATJELIA (ZONE-I) PWSS FOR PROVIDING FHTC, BLOCK - GOSABA | SM/16002 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000413/2023-2024 | 369/AD | 19/01/2024 | 19/01/2024 | Resource Division | 11.66 | 0 | 0 | 0
12 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION AND RETROFITTING OF SATJELIA (ZONE-I) PWSS FOR PROVIDING FHTC, BLOCK - GOSABA | SM/16002 | Augmentation | QUOTATION FOE NEW POWER CONNECTION AT SATJELIA ZONE-I PH-2 UNDER SMD PHE DTE.(Application ID:-1007627508) ( Reference ID:-106535007) |  |  | BILL/00131/2024-2025 | BP-2024-25-34 | 24/04/2024 | 24/04/2024 | WBSEDCL | 3.62 | 0 | 0 | 0
13 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION AND RETROFITTING OF SATJELIA (ZONE-I) PWSS FOR PROVIDING FHTC, BLOCK - GOSABA | SM/16002 | Augmentation | Quotation for new service( power) connection at Satjelia Zone-I PH-3 Water supply scheme under Gosaba block. Reference ID:-106770521, Application No :-1008125345 |  |  | BILL/01840/2024-2025 | BP-2024-25-465 | 18/11/2024 | 18/11/2024 | WBSEDCL | 4.54 | 0 | 0 | 0
14 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION AND RETROFITTING OF SATJELIA (ZONE-I) PWSS FOR PROVIDING FHTC, BLOCK - GOSABA | SM/16002 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/04814/2023-2024 | BP-2023-24-528 | 22/02/2024 | 22/02/2024 | WBSEDCL | 4.45 | 0 | 0 | 0
15 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION AND RETROFITTING OF SATJELIA (ZONE-I) PWSS FOR PROVIDING FHTC, BLOCK - GOSABA | SM/16002 | Augmentation | Supply & delivery of valve and UPVC column pipe etc at Satjelia Zone-I PH-3 water supply scheme under SMD, P.H.E. Dte. [SM/16002] | Assistant Engineer | Junior Engineer | ORD/000379/2025-2026 | 565/SMSD | 17/04/2025 | 02/05/2025 | SARVATAH PROJECTS PRIVATE LIMITED | 0.7 | 0 | 0 | 100
16 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION AND RETROFITTING OF SATJELIA (ZONE-I) PWSS FOR PROVIDING FHTC, BLOCK - GOSABA | SM/16002 | Augmentation | Supply & fixing main switch & Bus Bar at Zone-I, Pump House-2, 3 Aug of Satjelia water supply sche under SMD,PHE Dte. (Block-Gosaba) (SM/16002) | Assistant Engineer | Junior Engineer | ORD/002492/2024-2025 | 271/SMSD | 24/02/2025 | 11/03/2025 | SARVATAH PROJECTS PRIVATE LIMITED | 0.61 | 0 | 0 | 100
17 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION AND RETROFITTING OF SATJELIA (ZONE-I) PWSS FOR PROVIDING FHTC, BLOCK - GOSABA | SM/16002 | Augmentation | Improvement of outdoor illumination arrangement with allied works at Zone-I, Pump House-2 Aug of Satjelia water supply sche under SMD,PHE Dte. (Block-Gosaba) (SM/16002) | Assistant Engineer | Junior Engineer | ORD/002493/2024-2025 | 272/SMSD | 24/02/2025 | 11/03/2025 | SARVATAH PROJECTS PRIVATE LIMITED | 0.97 | 0 | 0 | 100
18 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION AND RETROFITTING OF SATJELIA (ZONE-I) PWSS FOR PROVIDING FHTC, BLOCK - GOSABA | SM/16002 | Augmentation | Improvement of outdoor illumination arrangement with allied works at Zone-I, Pump House-3 Aug of Satjelia water supply sche under SMD,PHE Dte. (Block-Gosaba) (SM/16002) | Assistant Engineer | Junior Engineer | ORD/002494/2024-2025 | 273/SMSD | 24/02/2025 | 11/03/2025 | SARVATAH PROJECTS PRIVATE LIMITED | 0.97 | 0 | 0 | 100
19 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION AND RETROFITTING OF SATJELIA (ZONE-I) PWSS FOR PROVIDING FHTC, BLOCK - GOSABA | SM/16002 | Augmentation | Supply & delivery of valve and UPVC column pipe etc at Satjelia Zone-I PH-2 water supply scheme under SMD, P.H.E. Dte. [SM/16002] | Assistant Engineer | Junior Engineer | ORD/000376/2025-2026 | 567/SMSD | 17/04/2025 | 02/05/2025 | SARVATAH PROJECTS PRIVATE LIMITED | 0.7 | 0 | 0 | 100
20 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION AND RETROFITTING OF SATJELIA (ZONE-I) PWSS FOR PROVIDING FHTC, BLOCK - GOSABA | SM/16002 | Augmentation | Supply & delivery of Cast Iron wafer type butterfly valve with 3 phase actuator at Satjelia Zone-I PH-2 water supply scheme under Gosaba Block under SMD, PHE Dte. (SM/16002) | Assistant Engineer | Junior Engineer | ORD/000378/2025-2026 | 564/SMSD | 17/04/2025 | 02/05/2025 | SARVATAH PROJECTS PRIVATE LIMITED | 0.99 | 0 | 0 | 100
21 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION AND RETROFITTING OF SATJELIA (ZONE-I) PWSS FOR PROVIDING FHTC, BLOCK - GOSABA | SM/16002 | Augmentation | Supply & delivery of Cast Iron wafer type butterfly valve with 3 phase actuator at Satjelia Zone-I PH-3 water supply scheme under Gosaba Block under SMD, PHE Dte. (SM/16002) | Assistant Engineer | Junior Engineer | ORD/000377/2025-2026 | 569/SMSD | 17/04/2025 | 02/05/2025 | SARVATAH PROJECTS PRIVATE LIMITED | 0.99 | 0 | 0 | 100
Total | [13 empty] | 732.68 | 349.62 | 47.72