## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF HARISHPUR PIPED WATER SUPPLY SCHEME, BLOCK-GOSABA,DISTRICT-SOUTH 24 PARGANAS | SM/16008 | Augmentation | Conducting route survey, design distribution network and preparation & submission of DPR for Harishpur (Zone-I) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Gosaba Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division |  | ORD/001853/2022-2023 | 11819/AD | 23/02/2023 | 09/04/2023 | TECH VISION | 3.68 | 3.68 | 100 | 0
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF HARISHPUR PIPED WATER SUPPLY SCHEME, BLOCK-GOSABA,DISTRICT-SOUTH 24 PARGANAS | SM/16008 | Augmentation | Construction of 100 m³ capacity 20 M. staging height R.C.C. Over Head Water Reservoir, Laying distribution system & Providing FHTC etc of Ground Water Based Augmentation of Harishpur (Zone-I) piped water supply scheme of Gosaba Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. [No. of FHTC = 921] | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000038/2023-2024 | 173/AD | 19/04/2023 | 01/07/2025 | SARDAR ENTERPRISE | 354.02 | 187.44 | 52.94 | 56
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF HARISHPUR PIPED WATER SUPPLY SCHEME, BLOCK-GOSABA,DISTRICT-SOUTH 24 PARGANAS | SM/16008 | Augmentation | Inter connection and rising main with supply of specials of Augmentation of Harishpur (Zone-I) W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/002017/2022-2023 | 12923/AD | 21/03/2023 | 01/10/2024 | M/S. TRIPATHI & CO. | 31.2 | 0 | 0 | 95
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF HARISHPUR PIPED WATER SUPPLY SCHEME, BLOCK-GOSABA,DISTRICT-SOUTH 24 PARGANAS | SM/16008 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000057/2023-2024 | 264/AD | 24/04/2023 | 24/04/2023 | Resource Division | 45.85 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF HARISHPUR PIPED WATER SUPPLY SCHEME, BLOCK-GOSABA,DISTRICT-SOUTH 24 PARGANAS | SM/16008 | Augmentation | Construction of boundary wall at Head Work for Augmentation of Harishpur (Zone-I) Piped Water Supply Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000732/2024-2025 | 4390/AD | 05/11/2024 | 20/12/2024 | SARDAR ENTERPRISE | 33.94 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF HARISHPUR PIPED WATER SUPPLY SCHEME, BLOCK-GOSABA,DISTRICT-SOUTH 24 PARGANAS | SM/16008 | Augmentation | Renovation and retrofitting of Pump House No. 3 of Augmentation of Harishpur W/S Scheme, under Gosaba Block of Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/002508/2023-2024 | 1603/CSD | 28/02/2024 | 29/03/2024 | KIRON CONSTRUCTION | 2.63 | 0 | 0 | 100
7 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF HARISHPUR PIPED WATER SUPPLY SCHEME, BLOCK-GOSABA,DISTRICT-SOUTH 24 PARGANAS | SM/16008 | Augmentation | Renovation and retrofitting of Pump House No. 1 of Augmentation of Harishpur W/S Scheme, under Gosaba Block of Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/002507/2023-2024 | 1602/CSD | 28/02/2024 | 29/03/2024 | NASKAR ENTERPRISE | 3.59 | 3.39 | 94.31 | 100
8 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF HARISHPUR PIPED WATER SUPPLY SCHEME, BLOCK-GOSABA,DISTRICT-SOUTH 24 PARGANAS | SM/16008 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000419/2023-2024 | 374/AD | 19/01/2024 | 19/01/2024 | Resource Division | 5.67 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF HARISHPUR PIPED WATER SUPPLY SCHEME, BLOCK-GOSABA,DISTRICT-SOUTH 24 PARGANAS | SM/16008 | Augmentation | Renovation and retrofitting of Pump House No. 2 of Augmentation of Harishpur W/S Scheme (Zone-I), under Gosaba Block of Canning Sub-Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000187/2025-2026 | 555/CSD | 02/05/2025 | 01/06/2025 | SANGJOG | 3.1 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF HARISHPUR PIPED WATER SUPPLY SCHEME, BLOCK-GOSABA,DISTRICT-SOUTH 24 PARGANAS | SM/16008 | Augmentation | Renovation and retrofitting of Pump House No. 1 of Augmentation of Harishpur W/S Scheme (Zone-I), under Gosaba Block of Canning Sub-Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000190/2025-2026 | 637/CSD | 22/05/2025 | 21/06/2025 | SAMIR GIRI | 3.15 | 0 | 0 | 100
Total | [13 empty] | 486.83 | 194.51 | 39.95