## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED KALARIA (ZONE-IIB) PIPED WATER SUPPLY SCHEME, BLOCK-CANNING-I, DISTRICT-SOUTH 24 PARGANAS | SM/16013 | Augmentation | Sinking of 02 (two) Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Kalaria (Zone-IIB) W/S Scheme, Block - Canning-I under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/001867/2022-2023 | 12456/AD | 10/03/2023 | 24/04/2023 | B.K. ENTERPRISE. | 40.76 | 37.35 | 91.63 | 95
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED KALARIA (ZONE-IIB) PIPED WATER SUPPLY SCHEME, BLOCK-CANNING-I, DISTRICT-SOUTH 24 PARGANAS | SM/16013 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000067/2023-2024 | 270/AD | 24/04/2023 | 24/04/2023 | Resource Division | 34.64 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED KALARIA (ZONE-IIB) PIPED WATER SUPPLY SCHEME, BLOCK-CANNING-I, DISTRICT-SOUTH 24 PARGANAS | SM/16013 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/03868/2023-2024 | BP-2023-24-397 | 02/12/2023 | 02/12/2023 | WBSEDCL | 5.07 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED KALARIA (ZONE-IIB) PIPED WATER SUPPLY SCHEME, BLOCK-CANNING-I, DISTRICT-SOUTH 24 PARGANAS | SM/16013 | Augmentation | Inter connection and rising main with supply of specials of Augmentation of Kalaria Zone- IIB W/S Scheme, Block-Canning- I under Canning Sub-Division of Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000129/2023-2024 | 489/AD | 10/05/2023 | 09/06/2023 | ASHIS ENTERPRISE | 17.98 | 0 | 0 | 25
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED KALARIA (ZONE-IIB) PIPED WATER SUPPLY SCHEME, BLOCK-CANNING-I, DISTRICT-SOUTH 24 PARGANAS | SM/16013 | Augmentation | Providing Functional Household Tap Connection (FHTC) of Ground Water Based Augmentation Piped Water Supply Scheme for Kalaria (Zone-IIB), Block-Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. [No. of FHTC = 2098] (TSM/017459) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000353/2023-2024 | 1662/AD | 20/07/2023 | 09/07/2025 | SAHANA ENTERPRISE | 105.65 | 81.17 | 76.83 | 90
6 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED KALARIA (ZONE-IIB) PIPED WATER SUPPLY SCHEME, BLOCK-CANNING-I, DISTRICT-SOUTH 24 PARGANAS | SM/16013 | Augmentation | Laying additional pipe line to connect the uncovered habitation for Augmentation of Kalaria (Zone-IIB) W/S Scheme, Block-Canning-I under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000484/2024-2025 | 3543/AD | 02/09/2024 | 17/10/2024 | SUPRITI ENTERPRISE | 19.63 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED KALARIA (ZONE-IIB) PIPED WATER SUPPLY SCHEME, BLOCK-CANNING-I, DISTRICT-SOUTH 24 PARGANAS | SM/16013 | Augmentation | Conducting route survey, design distribution network and preparation & submission of DPR for Kalaria (Zone-IIB) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Canning-I Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division |  | ORD/001950/2022-2023 | 11811/AD | 22/02/2023 | 08/04/2023 | SIRCON ENGINEERING SERVICES | 5.79 | 5.79 | 100 | 95
8 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED KALARIA (ZONE-IIB) PIPED WATER SUPPLY SCHEME, BLOCK-CANNING-I, DISTRICT-SOUTH 24 PARGANAS | SM/16013 | Augmentation | Laying of Distribution System of Ground Water Based Augmentation Piped Water Supply Scheme for Kalaria (Zone-IIB), Block-Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. (TSM/017459) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000018/2023-2024 | 90/AD | 11/04/2023 | 10/07/2023 | SHEKHAR CHAKRABORTY | 131.1 | 97.01 | 74 | 100
9 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED KALARIA (ZONE-IIB) PIPED WATER SUPPLY SCHEME, BLOCK-CANNING-I, DISTRICT-SOUTH 24 PARGANAS | SM/16013 | Augmentation | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Kalaria W/S Scheme (Zone-IIB), Block - Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. (Pump House-II) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000465/2023-2024 | 1927/AD | 01/08/2023 | 15/09/2023 | A.R.CONSTRUCTION | 7.09 | 6.5 | 91.69 | 90
10 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED KALARIA (ZONE-IIB) PIPED WATER SUPPLY SCHEME, BLOCK-CANNING-I, DISTRICT-SOUTH 24 PARGANAS | SM/16013 | Augmentation | Improvement of outdoor illumination arrangement with allied works at Kalaria Zone-IIB PH-2 under Canning-I Block water supply scheme under SMD,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002533/2023-2024 | 164/SMSD | 05/02/2024 | 20/02/2024 | JYOTY SOLAR POWER | 0.89 | 0.89 | 100 | 100
11 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED KALARIA (ZONE-IIB) PIPED WATER SUPPLY SCHEME, BLOCK-CANNING-I, DISTRICT-SOUTH 24 PARGANAS | SM/16013 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/04001/2023-2024 | BP-2023-24-405 | 13/12/2023 | 13/12/2023 | WBSEDCL | 4.66 | 0 | 0 | 0
12 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED KALARIA (ZONE-IIB) PIPED WATER SUPPLY SCHEME, BLOCK-CANNING-I, DISTRICT-SOUTH 24 PARGANAS | SM/16013 | Augmentation | Construction of 23 Nos. different capacity R.C.C OHR (based on Departmental Design & Drawing ) with 20 mtr. staging height including Geo-Technical investigation, foundation, pipeline connection and cost of pipes , specials etc. for augmentation of different piped water supply scheme of Canning-I, Canning-II & Basanti Block under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD,Junior Engineer,1 CSD | ORD/002461/2023-2024 | 1512/AD | 13/03/2024 | 03/11/2025 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LTD | 2624.49 | 0 | 0 | 30
13 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED KALARIA (ZONE-IIB) PIPED WATER SUPPLY SCHEME, BLOCK-CANNING-I, DISTRICT-SOUTH 24 PARGANAS | SM/16013 | Augmentation | Construction of boundary wall at Pump House No. - 1 at Ground Water Based Piped Water Supply Scheme of Kalaria (Zone - IIB) W/S Scheme Block - Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000027/2025-2026 | 2013/AD | 28/04/2025 | 10/09/2025 | SAHANA ENTERPRISE | 26.16 | 0 | 0 | 0
14 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED KALARIA (ZONE-IIB) PIPED WATER SUPPLY SCHEME, BLOCK-CANNING-I, DISTRICT-SOUTH 24 PARGANAS | SM/16013 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 Zone-II-B for Augmentation of Kalaria water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Canning-I] | Assistant Engineer | Junior Engineer | ORD/000267/2023-2024 | 1127/SMD | 24/04/2023 | 31/05/2025 | JYOTY SOLAR POWER | 20.92 | 20.23 | 96.71 | 100
15 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED KALARIA (ZONE-IIB) PIPED WATER SUPPLY SCHEME, BLOCK-CANNING-I, DISTRICT-SOUTH 24 PARGANAS | SM/16013 | Augmentation | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Kalaria W/S Scheme (Zone-IIB), Block - Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. (Pump House-I) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/001084/2023-2024 | 3543/AD | 17/10/2023 | 25/11/2024 | M/S. ASIRUDDIN SEKH ENTERPRISE | 7.28 | 0 | 0 | 100
16 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED KALARIA (ZONE-IIB) PIPED WATER SUPPLY SCHEME, BLOCK-CANNING-I, DISTRICT-SOUTH 24 PARGANAS | SM/16013 | Augmentation | Supply & Installation of LED board at Zone-IB PH-1 & 2 of Kalaria water supply scheme under South 24-Pgs Mechanical Division, PHE Dte [Block-Canning-I] | Assistant Engineer | Junior Engineer | ORD/002553/2023-2024 | 163/SMSD | 05/02/2024 | 20/02/2024 | MUKHERJEE ART CENTRE | 0.78 | 0 | 0 | 100
Total | [13 empty] | 3052.89 | 248.94 | 8.15