## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | GROUND WATER BASED DEBNAGAR PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE, BLOCK-NAMKHANA, DISTRICT-SOUTH 24 PARAGANAS | SM/16027 | New | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme (Debnagar) water supply scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/002161/2022-2023 | 8334/AD | 12/12/2022 | 26/01/2023 | M/S R.DUTTA & CO. | 5.66 | 5.66 | 100 | 100
2 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | GROUND WATER BASED DEBNAGAR PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE, BLOCK-NAMKHANA, DISTRICT-SOUTH 24 PARAGANAS | SM/16027 | New | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Debnagar Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-C) [No. of FHTC = 1140] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000036/2023-2024 | 171/AD | 19/04/2023 | 29/04/2025 | K.B. ENTERPRISE | 113.44 | 80.03 | 70.55 | 90
3 | SOUTH 24 PARGANAS | Namkhana | S24 Pgns Mechanical | GROUND WATER BASED DEBNAGAR PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE, BLOCK-NAMKHANA, DISTRICT-SOUTH 24 PARAGANAS | SM/16027 | New | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 of Debnagar water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Namkhana] | Assistant Engineer -I,Assistant Engineer -II | Junior Engineer | ORD/000114/2023-2024 | 1021/SMD | 12/04/2023 | 30/08/2025 | ANJAN ENTERPRISE | 21.62 | 0 | 0 | 85
4 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | GROUND WATER BASED DEBNAGAR PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE, BLOCK-NAMKHANA, DISTRICT-SOUTH 24 PARAGANAS | SM/16027 | New | Construction of 250 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of foundation after soil investagation including O & M of Laying distribution, Rising Main & FHTC for 1 year after completion of FHTC works for Debnagar Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A). [No. of FHTC = 700] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000365/2023-2024 | 1566/AD | 17/07/2023 | 01/01/2026 | M/S DEBABRATA DAS | 298.39 | 215.52 | 72.23 | 80
5 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | GROUND WATER BASED DEBNAGAR PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE, BLOCK-NAMKHANA, DISTRICT-SOUTH 24 PARAGANAS | SM/16027 | New | Continuation work order for Construction of 250 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of foundation after soil investigation including O & M of Laying distribution, Rising Main & FHTC for 1 year after completion of FHTC works for Debnagar Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A). [No. of FHTC = 700] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/001349/2023-2024 | 4127/AD | 24/11/2023 | 01/10/2024 | M/S DEBABRATA DAS | 10.02 | 8.67 | 86.61 | 100
6 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | GROUND WATER BASED DEBNAGAR PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE, BLOCK-NAMKHANA, DISTRICT-SOUTH 24 PARAGANAS | SM/16027 | New | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Debnagar W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/001833/2022-2023 | 12183/AD | 01/03/2023 | 15/04/2023 | GOLDEN GROUPS | 38.57 | 36.24 | 93.95 | 80
7 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | GROUND WATER BASED DEBNAGAR PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE, BLOCK-NAMKHANA, DISTRICT-SOUTH 24 PARAGANAS | SM/16027 | New | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Debnagar Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) [No. of FHTC = 700] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000035/2023-2024 | 170/AD | 19/04/2023 | 18/07/2023 | S.R. ENTERPRISE | 104.91 | 104.43 | 99.54 | 98
8 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | GROUND WATER BASED DEBNAGAR PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE, BLOCK-NAMKHANA, DISTRICT-SOUTH 24 PARAGANAS | SM/16027 | New | Making and fixing of permanent display board at headwork site of Sibnagar Abad, Debnagar, Narayanganj, Dwariknagar, Namkhana, Uttar Chandanpiri PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/002130/2023-2024 | 936/KSD | 19/12/2023 | 24/12/2023 | ANANTA KUMAR GIRI | 0.94 | 0.16 | 16.62 | 100
9 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | GROUND WATER BASED DEBNAGAR PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE, BLOCK-NAMKHANA, DISTRICT-SOUTH 24 PARAGANAS | SM/16027 | New | Preparation of design (Pile and Pile Cap) drawing for foundation of 250 cum. capacity OHR of Debnagar PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/002218/2023-2024 | 875/KSD | 14/12/2023 | 19/12/2023 | CONSTEEL CONSULTANCY & SERVICES | 0.48 | 0.48 | 100 | 100
10 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | GROUND WATER BASED DEBNAGAR PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE, BLOCK-NAMKHANA, DISTRICT-SOUTH 24 PARAGANAS | SM/16027 | New | Material Requisition To Resource Division |  |  | RTOR000482/2023-2024 | 4784/AD | 19/12/2023 | 19/12/2023 | Resource Division | 27.67 | 0 | 0 | 0
11 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | GROUND WATER BASED DEBNAGAR PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE, BLOCK-NAMKHANA, DISTRICT-SOUTH 24 PARAGANAS | SM/16027 | New | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connection etc. for Debnagar W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/16027) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000155/2024-2025 | 2506/AD | 15/06/2024 | 15/11/2025 | M/S DEBABRATA DAS | 91.21 | 0 | 0 | 25
12 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | GROUND WATER BASED DEBNAGAR PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE, BLOCK-NAMKHANA, DISTRICT-SOUTH 24 PARAGANAS | SM/16027 | New | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Debnagar W/S scheme, Block - Namkhana under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/002278/2023-2024 | 915/AD | 08/02/2024 | 31/01/2025 | P & S ASSOCIATES | 9.6 | 0 | 0 | 100
13 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | GROUND WATER BASED DEBNAGAR PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE, BLOCK-NAMKHANA, DISTRICT-SOUTH 24 PARAGANAS | SM/16027 | New | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Debnagar W/S scheme, Block - Namkhana under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000125/2024-2025 | 2403/AD | 07/06/2024 | 11/01/2025 | M/S OJHA ENTERPRISE | 27.46 | 0 | 0 | 90
14 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | GROUND WATER BASED DEBNAGAR PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE, BLOCK-NAMKHANA, DISTRICT-SOUTH 24 PARAGANAS | SM/16027 | New | Material Requisition To Resource Division |  |  | RTOR000982/2023-2024 | 1775/AD | 27/03/2024 | 27/03/2024 | Resource Division | 3.32 | 0 | 0 | 0
15 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | GROUND WATER BASED DEBNAGAR PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE, BLOCK-NAMKHANA, DISTRICT-SOUTH 24 PARAGANAS | SM/16027 | New | Material Requisition To Resource Division |  |  | RTOR000555/2023-2024 | 43/AD | 03/01/2024 | 03/01/2024 | Resource Division | 15.09 | 0 | 0 | 0
16 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | GROUND WATER BASED DEBNAGAR PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE, BLOCK-NAMKHANA, DISTRICT-SOUTH 24 PARAGANAS | SM/16027 | New | Material Requisition To Resource Division |  |  | RTOR000906/2023-2024 | 894/AD | 07/02/2024 | 07/02/2024 | Resource Division | 12.81 | 0 | 0 | 0
17 | SOUTH 24 PARGANAS | Namkhana | S24 Pgns Mechanical | GROUND WATER BASED DEBNAGAR PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE, BLOCK-NAMKHANA, DISTRICT-SOUTH 24 PARAGANAS | SM/16027 | New | Payment for New Service connection of Debnagar W/S Scheme PH-1 Application No:- 1007183483 Reference ID:- 106222545 |  |  | BILL/00967/2024-2025 | BP-2024-25-186 | 19/07/2024 | 19/07/2024 | WBSEDCL | 3.5 | 0 | 0 | 0
18 | SOUTH 24 PARGANAS | Namkhana | S24 Pgns Mechanical | GROUND WATER BASED DEBNAGAR PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE, BLOCK-NAMKHANA, DISTRICT-SOUTH 24 PARAGANAS | SM/16027 | New | PAYMENT OF ELECTRICITY BILL FOR NEW SERVICE CONNECTION UNDER SMD PHE DTE. |  |  | BILL/05391/2023-2024 | BP-2023-24-597 | 28/03/2024 | 28/03/2024 | WBSEDCL | 4.87 | 0 | 0 | 0
19 | SOUTH 24 PARGANAS | Namkhana | S24 Pgns Mechanical | GROUND WATER BASED DEBNAGAR PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE, BLOCK-NAMKHANA, DISTRICT-SOUTH 24 PARAGANAS | SM/16027 | New | Improvement of outdoor illumination arrangement with allied works at PH-1 of Debnagar W/S Scheme under JJM under South 24-Pgs Mechanical Division,PHE Dte. [Block-Namkhana] (SM/16027) | Assistant Engineer -I,Assistant Engineer -II | Junior Engineer | ORD/002431/2024-2025 | 1670/AE-II/SMD | 06/01/2025 | 21/01/2025 | ANJAN ENTERPRISE | 0.9 | 0 | 0 | 100
20 | SOUTH 24 PARGANAS | Namkhana | S24 Pgns Mechanical | GROUND WATER BASED DEBNAGAR PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE, BLOCK-NAMKHANA, DISTRICT-SOUTH 24 PARAGANAS | SM/16027 | New | Improvement of outdoor illumination arrangement with allied works at PH-2 of Debnagar W/S Scheme under JJM under South 24-Pgs Mechanical Division,PHE Dte. [Block-Namkhana] (SM/16027) | Assistant Engineer -I,Assistant Engineer -II | Junior Engineer | ORD/002432/2024-2025 | 1671/AE-II/SMD | 06/01/2025 | 21/01/2025 | ANJAN ENTERPRISE | 0.9 | 0 | 0 | 100
Total | [13 empty] | 791.36 | 451.19 | 57.01