## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF PHULMALANCHA PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC)(PART-B) | SM/16195 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000160/2023-2024 | 1052/AD | 15/06/2023 | 15/06/2023 | Resource Division | 13.54 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF PHULMALANCHA PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC)(PART-B) | SM/16195 | Augmentation | Construction of OHR (550 cum.), Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water Based Augmentation Piped Water Supply Scheme for the Phul Malancha,Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/001088/2023-2024 | 3605/AD | 30/10/2023 | 25/08/2024 | JIT CONSTRUCTION | 629.62 | 0 | 0 | 60
Total | [13 empty] | 643.16 | 0 | 0