## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED MANMATHANAGAR PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-KAKDWIP,DISTRICT - SOUTH 24 PARGANAS | SM/16291 | New | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Site of Manmathanagar W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000163/2023-2024 | 279/AD | 24/04/2023 | 08/06/2023 | GOLDEN GROUPS | 38.55 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS | Kakdwip | S24 Pgns Mechanical | GROUND WATER BASED MANMATHANAGAR PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-KAKDWIP,DISTRICT - SOUTH 24 PARGANAS | SM/16291 | New | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 of Manmathanagar water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Kakdwip] | Assistant Engineer -I | Junior Engineer | ORD/000111/2023-2024 | 1005/SMD | 11/04/2023 | 10/07/2023 | JAL PRAVAHIKA PVT. LTD. | 21.61 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED MANMATHANAGAR PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-KAKDWIP,DISTRICT - SOUTH 24 PARGANAS | SM/16291 | New | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Manmathanagar W/S scheme, Block - Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000954/2023-2024 | 2986/AD | 26/09/2023 | 10/11/2023 | M/S.SREEJIT ENTERPRISE | 27.52 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED MANMATHANAGAR PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-KAKDWIP,DISTRICT - SOUTH 24 PARGANAS | SM/16291 | New | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Manmathanagar W/S scheme, Block - Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000955/2023-2024 | 2987/AD | 26/09/2023 | 26/10/2023 | M/S. S.B. MANDAL & SONS | 9.58 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED MANMATHANAGAR PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-KAKDWIP,DISTRICT - SOUTH 24 PARGANAS | SM/16291 | New | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme Manmathanagar PWSS including Functional Household Tap Connection (FHTC) for implementation of JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/002163/2022-2023 | 8336/AD | 12/12/2022 | 26/01/2023 | LEMNISCATE | 6.91 | 6.91 | 100 | 100
6 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED MANMATHANAGAR PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-KAKDWIP,DISTRICT - SOUTH 24 PARGANAS | SM/16291 | New | Material Requisition To Resource Division |  |  | RTOR000123/2023-2024 | 659/AD | 17/05/2023 | 17/05/2023 | Resource Division | 15.46 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED MANMATHANAGAR PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-KAKDWIP,DISTRICT - SOUTH 24 PARGANAS | SM/16291 | New | Material Requisition To Resource Division |  |  | RTOR000451/2023-2024 | 4716/AD | 18/12/2023 | 18/12/2023 | Resource Division | 32.08 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED MANMATHANAGAR PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-KAKDWIP,DISTRICT - SOUTH 24 PARGANAS | SM/16291 | New | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections pile and pile cap for OHR etc at Kasinagar, Mrinalnagar, Manmathapur PWSS, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/18873,16292,16291) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000364/2024-2025 | 2913/AD | 10/07/2024 | 07/11/2024 | GARGO TRADERS | 471.61 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED MANMATHANAGAR PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-KAKDWIP,DISTRICT - SOUTH 24 PARGANAS | SM/16291 | New | Preparation of design (Pile and Pile Cap) drawing for foundation of 300 cum. capacity OHR of Manmathapur (Manmathanagar) PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/002073/2023-2024 | 769(A)/KSD | 08/12/2023 | 13/12/2023 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0.49 | 100 | 100
10 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED MANMATHANAGAR PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-KAKDWIP,DISTRICT - SOUTH 24 PARGANAS | SM/16291 | New | Material Requisition To Resource Division |  |  | RTOR000818/2023-2024 | 663/AD | 30/01/2024 | 30/01/2024 | Resource Division | 2.77 | 0 | 0 | 0
11 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED MANMATHANAGAR PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-KAKDWIP,DISTRICT - SOUTH 24 PARGANAS | SM/16291 | New | Construction of 300 cum. (2 nos.), 250 cum. (1 no.), 200 cum. (02 nos.) and 150 cum. (1 no.) Over Head Reservoir (OHR), (20 mtr. Staging Height) along with 12 nos. Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investagation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Uttar Kashiabad, Dakshin Kashiabad, Manmathapur, Ramgopalpur, Mrinalnagar and Bhubannagar Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. [No of FHTC= 12945] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division,Juniour Engineer_4, Kakdwip Sub Division | ORD/000052/2023-2024 | 122/AD | 13/04/2023 | 01/04/2025 | GARGO TRADERS | 2798.35 | 245.7 | 8.78 | 64
12 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED MANMATHANAGAR PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-KAKDWIP,DISTRICT - SOUTH 24 PARGANAS | SM/16291 | New | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Site of Manmathanagar W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/001834/2022-2023 | 12184/AD | 01/03/2023 | 04/02/2025 | GOLDEN GROUPS | 38.55 | 0 | 0 | 100
Total | [13 empty] | 3463.48 | 253.1 | 7.31