## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | Ramnagar Abad Piped Water Supply Scheme. | SM/16759 | New | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Ramnagar Abad Water Supply Scheme, Block - Pathar Pratima under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000134/2023-2024 | 606/AD | 15/05/2023 | 14/07/2023 | SIMPLEX DRILLING CO. | 36.27 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | Ramnagar Abad Piped Water Supply Scheme. | SM/16759 | New | Construction of 200 cum. (1 no.) and 300 cum. (1 no.) Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Dakshin Durgapur and Ramnagar Abad Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. [No. of FHTC = 450] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000765/2023-2024 | 2911/AD | 20/09/2023 | 03/11/2026 | M/S B. ENTERPRISE | 547.29 | 239.2 | 43.71 | 25
3 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | Ramnagar Abad Piped Water Supply Scheme. | SM/16759 | New | Construction of 1 (one) no. Pump House (5.40m x 3.60m) including sanitary arrangement as per departmental drawing at 2nd Tubewell Site of Ramnagar Abad Water Supply Scheme, Block- Pathar Pratima under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer, Kakdwip Sub Division |  | ORD/001164/2023-2024 | 3726/AD | 03/11/2023 | 02/01/2024 | SUDIP PRADHAN | 5.14 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | Ramnagar Abad Piped Water Supply Scheme. | SM/16759 | New | Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Dakshin Durgapur and Ramnagar Abad Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) [No. of FHTC = 1192] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/001214/2023-2024 | 3818/AD | 07/11/2023 | 01/11/2026 | M/S B. ENTERPRISE | 377.97 | 63.51 | 16.8 | 30
5 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | Ramnagar Abad Piped Water Supply Scheme. | SM/16759 | New | Making and fixing of permanent display board at headwork site of Digambarpur, Indranarayanpur, Dakshin Durgapur, Ramnagar Abad, Gurudaspur PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/002102/2023-2024 | 926/KSD | 19/12/2023 | 24/12/2023 | BIMALENDU GIRI | 0.79 | 0.08 | 10.74 | 100
6 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | Ramnagar Abad Piped Water Supply Scheme. | SM/16759 | New | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Ramnagar Abad PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/002624/2023-2024 | 881/KSD | 15/12/2023 | 25/12/2023 | CONSTEEL CONSULTANCY & SERVICES | 0.48 | 0.48 | 100 | 100
7 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | Ramnagar Abad Piped Water Supply Scheme. | SM/16759 | New | Material Requisition To Resource Division |  |  | RTOR000112/2023-2024 | 648/AD | 17/05/2023 | 17/05/2023 | Resource Division | 10.14 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | Ramnagar Abad Piped Water Supply Scheme. | SM/16759 | New | Material Requisition To Resource Division |  |  | RTOR000480/2023-2024 | 4757/AD | 19/12/2023 | 19/12/2023 | Resource Division | 42.86 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS | Patharpratima | S24 Pgns Mechanical | Ramnagar Abad Piped Water Supply Scheme. | SM/16759 | New | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/03415/2023-2024 | BP-2023-24-370 | 13/11/2023 | 13/11/2023 | WBSEDCL | 4.06 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | Ramnagar Abad Piped Water Supply Scheme. | SM/16759 | New | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Ramnagar Abad W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/002163/2023-2024 | 807/AD | 05/02/2024 | 06/03/2024 | M/S. BABA KAPIL MUNI ENTERPRISE | 9.36 | 0 | 0 | 0
11 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | Ramnagar Abad Piped Water Supply Scheme. | SM/16759 | New | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections, pile & pile cap for OHR etc at Ramnagarabad and Dakshin Durgapur PWSS, Block - Patharpratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/16759 and 16758) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000329/2024-2025 | 2732/AD | 25/06/2024 | 01/11/2025 | M/S B. ENTERPRISE | 318.12 | 0 | 0 | 25
12 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | Ramnagar Abad Piped Water Supply Scheme. | SM/16759 | New | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Ramnagar Abad W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/002162/2023-2024 | 806/AD | 05/02/2024 | 05/04/2024 | M/S B. ENTERPRISE | 27.51 | 27.43 | 99.7 | 100
13 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | Ramnagar Abad Piped Water Supply Scheme. | SM/16759 | New | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Ramnagar Abad W/S Scheme, Block - Pathar Pratima under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000120/2024-2025 | 2398/AD | 07/06/2024 | 01/01/2025 | S. CHAKRABORTY AND CO. | 39.9 | 0 | 0 | 100
14 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | Ramnagar Abad Piped Water Supply Scheme. | SM/16759 | New | Material Requisition To Resource Division |  |  | RTOR000765/2023-2024 | 599/AD | 29/01/2024 | 29/01/2024 | Resource Division | 1.82 | 0 | 0 | 0
15 | SOUTH 24 PARGANAS | Patharpratima | S24 Pgns Mechanical | Ramnagar Abad Piped Water Supply Scheme. | SM/16759 | New | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Ramnagar Abad water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Patharpratima] | Assistant Engineer -I | Junior Engineer | ORD/001274/2024-2025 | 277/SMD | 30/01/2025 | 30/04/2025 | A.K.SIKDAR | 0 | 0 | NAN | 0
16 | SOUTH 24 PARGANAS | Patharpratima | S24 Pgns Mechanical | Ramnagar Abad Piped Water Supply Scheme. | SM/16759 | New | New Service connection and security deposit for Ramnagar Abad PH-1 under JJM Application No-1008419392 Ref ID- 106965538 |  |  | BILL/00255/2025-2026 | 42152 | 01/08/2025 | 01/08/2025 | WBSEDCL | 3.38 | 0 | 0 | 0
17 | SOUTH 24 PARGANAS | Patharpratima | S24 Pgns Mechanical | Ramnagar Abad Piped Water Supply Scheme. | SM/16759 | New | New Service connection and security deposit for Ramnagar Abad PH-2 under JJM Application No-1008419321 Ref ID- 106965544 |  |  | BILL/00254/2025-2026 | 42152 | 01/08/2025 | 01/08/2025 | WBSEDCL | 4.02 | 0 | 0 | 0
Total | [13 empty] | 1429.1 | 330.7 | 23.14