## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF HARISHPUR (ZONE-II) PIPED WATER SUPPLY SCHEME, BLOCK : GOSABA, DISTRICT : SOUTH 24 PARGANAS | SM/17200 | Augmentation | Supply, installation and of 15 KVA servo motor operated copper wound line voltage stabilizer at PH No.-1 (Newly energized converted from DG power to WBSEDCL supply) of Harishpur water supply scheme under SMD, PHE Dte. (Block:-Gosaba). | Assistant Engineer | Junior Engineer | ORD/000398/2022-2023 | 543/SMD | 10/06/2022 | 10/07/2022 | SHIVAM ENTERPRISE | 4.12 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF HARISHPUR (ZONE-II) PIPED WATER SUPPLY SCHEME, BLOCK : GOSABA, DISTRICT : SOUTH 24 PARGANAS | SM/17200 | Augmentation | Inter connection and rising main with supply of specials of Augmentation of Harishpur (Zone-II) W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/002018/2022-2023 | 12924/AD | 21/03/2023 | 01/12/2025 | MOUMITA ENTERPRISE | 42.77 | 0 | 0 | 40
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF HARISHPUR (ZONE-II) PIPED WATER SUPPLY SCHEME, BLOCK : GOSABA, DISTRICT : SOUTH 24 PARGANAS | SM/17200 | Augmentation | Construction of 200 m³ capacity 20 M. staging height R.C.C. Over Head Water Reservoir, Laying distribution system & Providing FHTC etc of Ground Water Based Augmentation of Harishpur (Zone-II) piped water supply scheme of Gosaba Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. [No. of FHTC = 1474] | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000259/2023-2024 | 1447/AD | 13/07/2023 | 08/05/2024 | SAMSUL ENTERPRISE | 489.25 | 282.52 | 57.74 | 60
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF HARISHPUR (ZONE-II) PIPED WATER SUPPLY SCHEME, BLOCK : GOSABA, DISTRICT : SOUTH 24 PARGANAS | SM/17200 | Augmentation | Conducting route survey, design distribution network and preparation & submission of DPR for Harishpur (Zone-II) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Gosaba Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer 1,Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/002112/2022-2023 | 12878/AD | 17/03/2023 | 01/05/2023 | TECH VISION | 5.24 | 5.24 | 100 | 95
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF HARISHPUR (ZONE-II) PIPED WATER SUPPLY SCHEME, BLOCK : GOSABA, DISTRICT : SOUTH 24 PARGANAS | SM/17200 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000058/2023-2024 | 265/AD | 24/04/2023 | 24/04/2023 | Resource Division | 46.64 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF HARISHPUR (ZONE-II) PIPED WATER SUPPLY SCHEME, BLOCK : GOSABA, DISTRICT : SOUTH 24 PARGANAS | SM/17200 | Augmentation | Construction of boundary wall at Head Work Site for Augmentation of Harishpur (Zone-II) Piped Water Supply Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000733/2024-2025 | 4391/AD | 05/11/2024 | 20/12/2024 | SAMSUL ENTERPRISE | 45.41 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF HARISHPUR (ZONE-II) PIPED WATER SUPPLY SCHEME, BLOCK : GOSABA, DISTRICT : SOUTH 24 PARGANAS | SM/17200 | Augmentation | Laying of additional pipe line and other allied works at Harishpur (Zone-II) W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001227/2024-2025 | 5230/AD | 16/12/2024 | 13/09/2025 | P.S. CONSTRUCTION | 84.35 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF HARISHPUR (ZONE-II) PIPED WATER SUPPLY SCHEME, BLOCK : GOSABA, DISTRICT : SOUTH 24 PARGANAS | SM/17200 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000420/2023-2024 | 375/AD | 19/01/2024 | 19/01/2024 | Resource Division | 9.08 | 0 | 0 | 0
Total | [13 empty] | 726.86 | 287.75 | 39.59