## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | DURGANAGAR PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18127 | New | Construction of 60 cum. Over Head Reservoir (OHR), (15 mtr. Staging Height) along with Laying distribution system, Rising Main, construction of 1 no. 5.40m x 3.60m. Pump House, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Durganagar Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000022/2023-2024 | 97/AD | 11/04/2023 | 23/07/2026 | ADITYA HAZRA | 108.12 | 21.63 | 20.01 | 75
2 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | DURGANAGAR PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18127 | New | Laying distribution system providing FHTC for Durganagar W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-D) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/002073/2022-2023 | 13223/AD | 31/03/2023 | 30/04/2023 | BHUNIA BUILDERS | 7.25 | 5.79 | 79.89 | 82
3 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | DURGANAGAR PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18127 | New | Laying distribution system providing FHTC for Durganagar W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-E) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/002074/2022-2023 | 13224/AD | 31/03/2023 | 30/04/2023 | BHOLANATH CONSTRUCTION | 8.23 | 3.17 | 38.52 | 50
4 | SOUTH 24 PARGANAS | Namkhana | S24 Pgns Mechanical | DURGANAGAR PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18127 | New | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 of Durganagar Water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Namkhana] | Assistant Engineer -I | Junior Engineer | ORD/001782/2023-2024 | 4766/SMD | 06/12/2023 | 06/06/2024 | COMBINE ENTERPRISES | 9.42 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | DURGANAGAR PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18127 | New | Laying distribution system providing FHTC for Durganagar W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/002071/2022-2023 | 13221/AD | 31/03/2023 | 30/04/2023 | G.M. ENTERPRISE | 15.94 | 11.94 | 74.91 | 100
6 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | DURGANAGAR PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18127 | New | Laying distribution system providing FHTC for Durganagar W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-C) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/002072/2022-2023 | 13222/AD | 31/03/2023 | 30/04/2023 | KHOKAN MONDAL | 15.16 | 14.87 | 98.12 | 100
7 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | DURGANAGAR PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18127 | New | Making and fixing of permanent display board at headwork site of Durganagar, Iswaripur, Ganeshnagar Zone-I, Ganeshnagar Zone-II, Narayanpur Zone- I & II PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/002118/2023-2024 | 934/KSD | 19/12/2023 | 24/12/2023 | BIMALENDU GIRI | 0.94 | 0.31 | 32.99 | 90
8 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | DURGANAGAR PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18127 | New | Material Requisition To Resource Division |  |  | RTOR000128/2023-2024 | 664/AD | 17/05/2023 | 17/05/2023 | Resource Division | 1.65 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | DURGANAGAR PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18127 | New | Material Requisition To Resource Division |  |  | RTOR000468/2023-2024 | 4775/AD | 19/12/2023 | 19/12/2023 | Resource Division | 0.71 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | DURGANAGAR PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18127 | New | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Durganagar W/S scheme, Block - Namkhana under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/002048/2023-2024 | 509/AD | 25/01/2024 | 30/05/2026 | SUGANDHIT SUNDARBAN ENTERPRISE PVT. LTD. | 27.8 | 0 | 0 | 80
11 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | DURGANAGAR PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18127 | New | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st Tubewell Site of Durganagar W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000109/2024-2025 | 4847/AD | 29/11/2024 | 27/02/2025 | DEV AND COMPANY | 19.96 | 0 | 0 | 100
12 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | DURGANAGAR PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18127 | New | Material Requisition To Resource Division |  |  | RTOR000786/2023-2024 | 630/AD | 30/01/2024 | 30/01/2024 | Resource Division | 1.16 | 0 | 0 | 0
Total | [13 empty] | 216.35 | 57.72 | 26.68