## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS | Namkhana | Alipore Division | DURGANAGAR PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18127 | New | Material Requisition To Resource Division |  |  | RTOR000128/2023-2024 | 664/AD | 17/05/2023 |  | Resource Division | 1.65 | 0 | 0 | 0
2 | SOUTH 24 PARAGANAS | Namkhana | Alipore Division | DURGANAGAR PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18127 | New | Construction of 60 cum. Over Head Reservoir (OHR), (15 mtr. Staging Height) along with Laying distribution system, Rising Main, construction of 1 no. 5.40m x 3.60m. Pump House, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Durganagar Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000022/2023-2024 | 97/AD | 11/04/2023 | 05/02/2024 | ADITYA HAZRA | 108.12 | 21.63 | 20.01 | 30
3 | SOUTH 24 PARAGANAS | Namkhana | Alipore Division | DURGANAGAR PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18127 | New | Laying distribution system providing FHTC for Durganagar W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-D) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/002073/2022-2023 | 13223/AD | 31/03/2023 | 30/04/2023 | BHUNIA BUILDERS | 7.25 | 5.79 | 79.89 | 82
4 | SOUTH 24 PARAGANAS | Namkhana | Alipore Division | DURGANAGAR PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18127 | New | Laying distribution system providing FHTC for Durganagar W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-E) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/002074/2022-2023 | 13224/AD | 31/03/2023 | 30/04/2023 | BHOLANATH CONSTRUCTION | 8.23 | 1.59 | 19.26 | 50
5 | SOUTH 24 PARAGANAS | Namkhana | Alipore Division | DURGANAGAR PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18127 | New | Material Requisition To Resource Division |  |  | RTOR000468/2023-2024 | 4775/AD | 19/12/2023 |  | Resource Division | 0.71 | 0 | 0 | 0
6 | SOUTH 24 PARAGANAS | Namkhana | Alipore Division | DURGANAGAR PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18127 | New | Material Requisition To Resource Division |  |  | RTOR000786/2023-2024 | 630/AD | 30/01/2024 |  | Resource Division | 1.16 | 0 | 0 | 0
7 | SOUTH 24 PARAGANAS | Namkhana | Alipore Division | DURGANAGAR PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18127 | New | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Durganagar W/S scheme, Block - Namkhana under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/002048/2023-2024 | 509/AD | 25/01/2024 | 10/03/2024 | SUGANDHIT SUNDARBAN ENTERPRISE PVT. LTD. | 27.8 | 0 | 0 | 0
8 | SOUTH 24 PARAGANAS | Namkhana | S24 Pgns Mechanical | DURGANAGAR PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18127 | New | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 of Durganagar Water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Namkhana] | Assistant Engineer -I | Junior Engineer | ORD/001782/2023-2024 | 4766/SMD | 06/12/2023 | 03/06/2024 | COMBINE ENTERPRISES | 9.42 | 0 | 0 | 0
9 | SOUTH 24 PARAGANAS | Namkhana | Alipore Division | DURGANAGAR PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18127 | New | Making and fixing of permanent display board at headwork site of Durganagar, Iswaripur, Ganeshnagar Zone-I, Ganeshnagar Zone-II, Narayanpur Zone- I & II PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/002118/2023-2024 | 934/KSD | 19/12/2023 | 24/12/2023 | BIMALENDU GIRI | 0.94 | 0 | 0 | 90
10 | SOUTH 24 PARAGANAS | Namkhana | Alipore Division | DURGANAGAR PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18127 | New | Laying distribution system providing FHTC for Durganagar W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/002071/2022-2023 | 13221/AD | 31/03/2023 | 30/04/2023 | G.M. ENTERPRISE | 15.94 | 11.05 | 69.29 | 100
11 | SOUTH 24 PARAGANAS | Namkhana | Alipore Division | DURGANAGAR PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18127 | New | Laying distribution system providing FHTC for Durganagar W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-C) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/002072/2022-2023 | 13222/AD | 31/03/2023 | 30/04/2023 | KHOKAN MONDAL | 15.16 | 12.19 | 80.44 | 100
Total | [13 empty] | 196.39 | 52.25 | 26.6