## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | ISWARIPUR PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION,PHE DTE. | SM/18128 | New | Construction of 50 cum. Over Head Reservoir (OHR), (15 mtr. Staging Height) along with Laying distribution system, Rising Main, construction of 1 no. 5.40m x 3.60m. Pump House, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Iswaripur Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000019/2023-2024 | 96/AD | 11/04/2023 | 23/07/2026 | RELIABLE CONSTRUCTIONS | 103.1 | 33.91 | 32.89 | 50
2 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | ISWARIPUR PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION,PHE DTE. | SM/18128 | New | Laying distribution system providing FHTC for Iswaripur W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/002069/2022-2023 | 13219/AD | 31/03/2023 | 30/04/2023 | JOY ENGINEERING & CONSTRUCTION | 14.48 | 10.71 | 73.99 | 70
3 | SOUTH 24 PARGANAS | Namkhana | S24 Pgns Mechanical | ISWARIPUR PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION,PHE DTE. | SM/18128 | New | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 of Iswaripur Water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Namkhana] | Assistant Engineer -I | Junior Engineer | ORD/001784/2023-2024 | 4767/SMD | 06/12/2023 | 06/03/2024 | COMBINE ENTERPRISES | 9.42 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | ISWARIPUR PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION,PHE DTE. | SM/18128 | New | Laying distribution system providing FHTC for Iswaripur W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-C) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/002070/2022-2023 | 13220/AD | 31/03/2023 | 30/04/2023 | M/S BOSE & CO. | 12.98 | 12.97 | 99.91 | 100
5 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | ISWARIPUR PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION,PHE DTE. | SM/18128 | New | Material Requisition To Resource Division |  |  | RTOR000129/2023-2024 | 665/AD | 17/05/2023 | 17/05/2023 | Resource Division | 1.37 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | ISWARIPUR PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION,PHE DTE. | SM/18128 | New | Material Requisition To Resource Division |  |  | RTOR000469/2023-2024 | 4776/AD | 19/12/2023 | 19/12/2023 | Resource Division | 1.15 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS | Namkhana | S24 Pgns Mechanical | ISWARIPUR PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION,PHE DTE. | SM/18128 | New | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/00627/2023-2024 | BP-2023-24-84 | 14/06/2023 | 14/06/2023 | WBSEDCL | 3.87 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | ISWARIPUR PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION,PHE DTE. | SM/18128 | New | Material Requisition To Resource Division |  |  | RTOR000787/2023-2024 | 631/AD | 30/01/2024 | 30/01/2024 | Resource Division | 0.91 | 0 | 0 | 0
Total | [13 empty] | 147.27 | 57.59 | 39.11