## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | SHIBNAGAR ABAD PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18129 | New | Material Requisition To Resource Division |  |  | RTOR000472/2023-2024 | 4778/AD | 19/12/2023 | 19/12/2023 | Resource Division | 36.29 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | SHIBNAGAR ABAD PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18129 | New | Laying distribution system, Functional Household Tap Connection (FHTC) to all households and Construction 02 nos. Pump House (5.40m. x 3.60m) for Shibnagar Abad Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000166/2023-2024 | 2264/AD | 14/08/2023 | 28/09/2023 | SARADA CONSTRUCTION | 61.08 | 31.39 | 51.39 | 60
3 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | SHIBNAGAR ABAD PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18129 | New | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Shibnagar Abad W/S scheme, Block - Namkhana under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/002050/2023-2024 | 511/AD | 25/01/2024 | 24/02/2024 | SRI DURGA ENTERPRISE | 9.58 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | SHIBNAGAR ABAD PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18129 | New | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Shibnagar Abad W/S scheme, Block - Namkhana under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/002277/2023-2024 | 914/AD | 08/02/2024 | 24/03/2024 | CAMELIA CONSTRUCTION | 26.92 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | SHIBNAGAR ABAD PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18129 | New | Laying distribution system for providing FHTC to all households for Shibnagar Abad Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-D) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/002573/2023-2024 | 516/KSD | 15/03/2024 | 04/04/2024 | M/S SANKARI ENTERPRISE (II) | 3.82 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | SHIBNAGAR ABAD PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18129 | New | Construction of Platform and Road Restoration for Shibnagar Abad W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-II) (SM/18129) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000459/2024-2025 | 3418/AD | 21/08/2024 | 20/09/2024 | SARADA CONSTRUCTION | 18.15 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | SHIBNAGAR ABAD PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18129 | New | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 3rd Tubewell Site of Shibnagar Abad W/S scheme, Block : Namkhana under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/18129) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000230/2024-2025 | 2560/AD | 18/06/2024 | 18/07/2024 | SUKUMAR HALDAR | 9.6 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | SHIBNAGAR ABAD PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18129 | New | Construction of 1 nos. Pump House of size 5.40 mtr. x 3.60 mtr. at 3rd tubewell Site for Shibnagar Abad Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/18129) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000231/2024-2025 | 2542/AD | 18/06/2024 | 02/08/2024 | M/S SAKTI GIRI ENTERPRISE | 5.62 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | SHIBNAGAR ABAD PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18129 | New | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Shibnagar Abad Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/002080/2022-2023 | 13255/AD | 31/03/2023 | 15/05/2023 | AQUATECH ENGINEERS | 36.97 | 36.61 | 99.04 | 40
10 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | SHIBNAGAR ABAD PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18129 | New | Making and fixing of permanent display board at headwork site of Sibnagar Abad, Debnagar, Narayanganj, Dwariknagar, Namkhana, Uttar Chandanpiri PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/002130/2023-2024 | 936/KSD | 19/12/2023 | 24/12/2023 | ANANTA KUMAR GIRI | 0.94 | 0.16 | 16.56 | 100
11 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | SHIBNAGAR ABAD PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18129 | New | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Shibnagar Abad PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/002619/2023-2024 | 956/KSD | 19/12/2023 | 24/12/2023 | CONSTEEL CONSULTANCY & SERVICES | 0.48 | 0.48 | 100 | 100
12 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | SHIBNAGAR ABAD PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18129 | New | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded GravelFilter for Shibnagar Abad W/S Scheme, Block - Namkhana under JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/18129)(2nd Call) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000450/2024-2025 | 3359/AD | 14/08/2024 | 05/12/2024 | SARADA CONSTRUCTION | 20.39 | 0 | 0 | 100
13 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | SHIBNAGAR ABAD PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18129 | New | Material Requisition To Resource Division |  |  | RTOR000562/2023-2024 | 50/AD | 03/01/2024 | 03/01/2024 | Resource Division | 8.93 | 0 | 0 | 0
14 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | SHIBNAGAR ABAD PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18129 | New | Material Requisition To Resource Division |  |  | RTOR000977/2023-2024 | 1770/AD | 27/03/2024 | 27/03/2024 | Resource Division | 3.32 | 0 | 0 | 0
15 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | SHIBNAGAR ABAD PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18129 | New | Material Requisition To Resource Division |  |  | RTOR000788/2023-2024 | 632/AD | 30/01/2024 | 30/01/2024 | Resource Division | 0.43 | 0 | 0 | 0
16 | SOUTH 24 PARGANAS | Namkhana | S24 Pgns Mechanical | SHIBNAGAR ABAD PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18129 | New | Payment for New Service connection of Shibnagarbad PH-1 W/S Scheme JL No-:- 004, Khatian No;- 1714, Plot:- 3348, Mouza:- Shibnagarabad Application No:- 1007514909 Reference ID:- 106460088 |  |  | BILL/00215/2024-2025 | BP-2024-25-66 | 16/05/2024 | 16/05/2024 | WBSEDCL | 3.86 | 0 | 0 | 0
17 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | SHIBNAGAR ABAD PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18129 | New | Construction of 200 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design & drawing of pile foundation & pile cap after soil investigation along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M for Shibnagar Abad Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/001143/2023-2024 | 3671/AD | 01/11/2023 | 01/10/2025 | PRINCE INDUSTRIES (INDIA) | 381.91 | 65.69 | 17.2 | 75
18 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | SHIBNAGAR ABAD PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18129 | New | Laying distribution system for providing FHTC to all households for Shibnagar Abad Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-C) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/002129/2023-2024 | 819/AD | 05/02/2024 | 28/10/2025 | S.M. ENTERPRISE | 30.06 | 0 | 0 | 80
19 | SOUTH 24 PARGANAS | Namkhana | S24 Pgns Mechanical | SHIBNAGAR ABAD PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18129 | New | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 &2 of Shibnagar Abad water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Namkhana] | Assistant Engineer -II | Junior Engineer | ORD/001464/2023-2024 | 684/SMD | 01/02/2024 | 01/04/2026 | PS & ASSOCIATES | 22.42 | 0 | 0 | 45
20 | SOUTH 24 PARGANAS | Namkhana | S24 Pgns Mechanical | SHIBNAGAR ABAD PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18129 | New | Payment for New Service connection of Shibnagarabad PH-2 W/S Scheme Application No- 1008252336 Reference ID:- 106851336 |  |  | BILL/02492/2024-2025 | BP-2024-25-533 | 24/01/2025 | 24/01/2025 | WBSEDCL | 3.39 | 0 | 0 | 0
21 | SOUTH 24 PARGANAS | Namkhana | S24 Pgns Mechanical | SHIBNAGAR ABAD PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18129 | New | Supply & fixing of main switch & Bus bar with allied works at PH-1 & 2 of Shibnagar Abad W/S Scheme under JJM under South 24-Pgs Mechanical Division,PHE Dte. [Block-Pathar Pratima] (SM/18129) | Assistant Engineer -II | Junior Engineer | ORD/001247/2025-2026 | 1571-AE-II-SMD | 16/09/2025 | 07/10/2025 | PS & ASSOCIATES | 0.72 | 0 | 0 | 0
22 | SOUTH 24 PARGANAS | Namkhana | S24 Pgns Mechanical | SHIBNAGAR ABAD PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18129 | New | Improvement of outdoor illumination arrangement with allied works at PH-1 of Shibnagar Abad W/S Scheme under JJM under South 24-Pgs Mechanical Division,PHE Dte. [Block-Pathar Pratima] (SM/18129) | Assistant Engineer -II | Junior Engineer | ORD/001261/2025-2026 | 1643-AE-II-SMD | 10/10/2025 | 31/10/2025 | PS & ASSOCIATES | 0.93 | 0 | 0 | 0
23 | SOUTH 24 PARGANAS | Namkhana | S24 Pgns Mechanical | SHIBNAGAR ABAD PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18129 | New | Improvement of outdoor illumination arrangement with allied works at PH-2 of Shibnagar Abad W/S Scheme under JJM under South 24-Pgs Mechanical Division,PHE Dte. [Block-Pathar Pratima] (SM/18129) |  | Junior Engineer | ORD/001262/2025-2026 | 1546/AE-II/SMD | 11/09/2025 | 02/10/2025 | PS & ASSOCIATES | 0.93 | 0 | 0 | 0
Total | [13 empty] | 686.72 | 134.33 | 19.56