## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF PATHANKHALI (ZONE-I) PIPED WATER SUPPLY SCHEME, BLOCK-GOSABA,DISTRICT-SOUTH 24 PARGANAS | SM/18244 | Augmentation | Inter connection and rising main with supply of specials of Augmentation of Pathankhali (Zone-I) W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division |  | ORD/000491/2023-2024 | 1931/AD | 01/08/2023 | 15/09/2023 | NATURAL RESOURCES CONSORTIUM | 51.2 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF PATHANKHALI (ZONE-I) PIPED WATER SUPPLY SCHEME, BLOCK-GOSABA,DISTRICT-SOUTH 24 PARGANAS | SM/18244 | Augmentation | Conducting route survey, design distribution network and preparation & submission of DPR for Pathankhali (Zone-I) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Gosaba Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000607/2023-2024 | 1829/AD | 27/07/2023 | 10/09/2023 | TECH VISION | 7.45 | 7.45 | 100 | 99
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF PATHANKHALI (ZONE-I) PIPED WATER SUPPLY SCHEME, BLOCK-GOSABA,DISTRICT-SOUTH 24 PARGANAS | SM/18244 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000049/2023-2024 | 256/AD | 24/04/2023 | 24/04/2023 | Resource Division | 124.68 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF PATHANKHALI (ZONE-I) PIPED WATER SUPPLY SCHEME, BLOCK-GOSABA,DISTRICT-SOUTH 24 PARGANAS | SM/18244 | Augmentation | Construction of OHR (350 Cum), Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water based Augmentation Piped Water Supply Scheme for the PATHANKHALI (ZONE-I), Block-Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000485/2023-2024 | 1998/AD | 04/08/2023 | 30/05/2024 | M/S SHIBAM ENTERPRISE | 711.48 | 164.37 | 23.1 | 25
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF PATHANKHALI (ZONE-I) PIPED WATER SUPPLY SCHEME, BLOCK-GOSABA,DISTRICT-SOUTH 24 PARGANAS | SM/18244 | Augmentation | Construction of boundary wall at Pump House no.1 for Augmentation of Pathakhali (Zone-I) Piped Water Supply Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000730/2024-2025 | 4388/AD | 05/11/2024 | 05/12/2024 | KANAN CONSTRUCTION | 28.81 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF PATHANKHALI (ZONE-I) PIPED WATER SUPPLY SCHEME, BLOCK-GOSABA,DISTRICT-SOUTH 24 PARGANAS | SM/18244 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000410/2023-2024 | 364/AD | 19/01/2024 | 19/01/2024 | Resource Division | 14.32 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF PATHANKHALI (ZONE-I) PIPED WATER SUPPLY SCHEME, BLOCK-GOSABA,DISTRICT-SOUTH 24 PARGANAS | SM/18244 | Augmentation | Sinking of 250mm x 150mm dia. 360 mtr. deep (Replacement) Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Augmentation of Pathankhali (Zone - I) W/S Scheme, Block - Gosaba under Canning Sub Division of Alipore Division, PHE Dte. (Tubewell No. - 4) (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000743/2024-2025 | 4417/AD | 05/11/2024 | 05/12/2024 | MOSTAFIZUR HAQUE GAINE | 22.43 | 0 | 0 | 25
8 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF PATHANKHALI (ZONE-I) PIPED WATER SUPPLY SCHEME, BLOCK-GOSABA,DISTRICT-SOUTH 24 PARGANAS | SM/18244 | Augmentation | Construction of boundary wall at Pump House No. - 2 for Ground Water Based at Bipradaspur Piped Water Supply Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/002495/2024-2025 | 788/AD | 25/02/2025 | 27/03/2025 | REZU CONSTRUCTION | 12.42 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF PATHANKHALI (ZONE-I) PIPED WATER SUPPLY SCHEME, BLOCK-GOSABA,DISTRICT-SOUTH 24 PARGANAS | SM/18244 | Augmentation | Inter connection and rising main with supply of specials of Augmentation of Pathankhali (Zone - l) W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000094/2025-2026 | 2523/AD | 30/05/2025 | 14/07/2025 | SURYA ENTERPRISE | 19.5 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF PATHANKHALI (ZONE-I) PIPED WATER SUPPLY SCHEME, BLOCK-GOSABA,DISTRICT-SOUTH 24 PARGANAS | SM/18244 | Augmentation | Renovation and retrofitting of Pump House No. 2 of Augmentation of Pathankhali W/S Scheme (Zone-I), under Gosaba Block of Canning Sub-Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000185/2025-2026 | 549/CSD | 30/04/2025 | 30/05/2025 | LASKAR CONSTRUCTION | 2.49 | 0 | 0 | 100
11 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF PATHANKHALI (ZONE-I) PIPED WATER SUPPLY SCHEME, BLOCK-GOSABA,DISTRICT-SOUTH 24 PARGANAS | SM/18244 | Augmentation | Renovation and retrofitting of Pump House No. 1 of Augmentation of Pathankhali W/S Scheme (Zone-I), under Gosaba Block of Canning Sub-Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000301/2025-2026 | 623/CSD | 20/05/2025 | 01/08/2025 | A.K. ENTERPRISE | 2.47 | 0 | 0 | 80
12 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF PATHANKHALI (ZONE-I) PIPED WATER SUPPLY SCHEME, BLOCK-GOSABA,DISTRICT-SOUTH 24 PARGANAS | SM/18244 | Augmentation | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Gosaba) Name of PWSS :- Amlamethi, Sambhunagar, Choto Mollakhali (Zone-I), Bijoynagar, Luxbagan, Puinjali, Lahiripur, Pathankhali (Zone - I), Pathankhali (Zone - II), Pathankhali (Zone - III), Gosaba (Zone - I), Gosaba (Zone - II), Gosaba (Zone - III), Kumirmari (Zone- I) & Kumirmari (Zone-II) (For 15 (Fifteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000969/2024-2025 | 1182/CSD | 24/10/2024 | 13/11/2024 | A.P. CONSTRUCTION | 4.38 | 0 | 0 | 100
Total | [13 empty] | 1001.66 | 171.82 | 17.15