## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF KACHU KHALI PIPED WATER SUPPLY SCHEME, BLOCK-GOSABA,DISTRICT-SOUTH 24 PARGANAS | SM/18267 | Augmentation | Sinking of 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Kachukhali W/S Scheme, Block - Gosaba under Canning Sub Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000385/2023-2024 | 1574/AD | 17/07/2023 | 16/08/2023 | MAA SANTOSHI ENTERPRISE | 21.96 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF KACHU KHALI PIPED WATER SUPPLY SCHEME, BLOCK-GOSABA,DISTRICT-SOUTH 24 PARGANAS | SM/18267 | Augmentation | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Kachukhali W/S Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000394/2023-2024 | 1779/AD | 26/07/2023 | 01/01/2025 | BHATTACHARYA ENTERPRISE | 8.57 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF KACHU KHALI PIPED WATER SUPPLY SCHEME, BLOCK-GOSABA,DISTRICT-SOUTH 24 PARGANAS | SM/18267 | Augmentation | Construction of OHR (200 Cum), Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water based Augmentation Piped Water Supply Scheme for the KACHUKHALI, Block-Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000630/2023-2024 | 2434/AD | 22/08/2023 | 17/06/2024 | UNITED BUILDERS | 588.5 | 330.26 | 56.12 | 70
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF KACHU KHALI PIPED WATER SUPPLY SCHEME, BLOCK-GOSABA,DISTRICT-SOUTH 24 PARGANAS | SM/18267 | Augmentation | Sinking of 200mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Augmentation of Kachukhali W/S Scheme, Block - Gosaba under Canning Sub Division of Alipore Division, PHE Dte. (Tubewell No. - II) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001190/2023-2024 | 3995/AD | 21/11/2023 | 21/12/2023 | MEHAI TECHNOLOGY LIMITED | 20.46 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF KACHU KHALI PIPED WATER SUPPLY SCHEME, BLOCK-GOSABA,DISTRICT-SOUTH 24 PARGANAS | SM/18267 | Augmentation | Laying additional pipeline and other allied works at Augmentation of Kachukhali W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000282/2024-2025 | 2639/AD | 20/06/2024 | 01/05/2025 | MS SINHA ROY & CO | 39.38 | 0 | 0 | 80
6 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF KACHU KHALI PIPED WATER SUPPLY SCHEME, BLOCK-GOSABA,DISTRICT-SOUTH 24 PARGANAS | SM/18267 | Augmentation | Construction of boundary wall at Head Work Site for Ground Water Based at Kachukhali Piped Water Supply Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001238/2024-2025 | 5219/AD | 16/12/2024 | 25/01/2025 | NITYANANDA MONDAL | 32.8 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF KACHU KHALI PIPED WATER SUPPLY SCHEME, BLOCK-GOSABA,DISTRICT-SOUTH 24 PARGANAS | SM/18267 | Augmentation | Construction of boundary wall at Pump House No. - 1 for Ground Water Based at Kachukhali Piped Water Supply Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001237/2024-2025 | 5218/AD | 16/12/2024 | 15/01/2025 | UNITED BUILDERS | 6.91 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF KACHU KHALI PIPED WATER SUPPLY SCHEME, BLOCK-GOSABA,DISTRICT-SOUTH 24 PARGANAS | SM/18267 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000063/2023-2024 | 541/AD | 25/01/2024 | 25/01/2024 | Resource Division | 26.47 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF KACHU KHALI PIPED WATER SUPPLY SCHEME, BLOCK-GOSABA,DISTRICT-SOUTH 24 PARGANAS | SM/18267 | Augmentation | Quotation for new service( power) connection at Kachukhali PH- 1 Water supply scheme under Gosaba block. Reference ID:-106770520, Application No :-1008125133 |  |  | BILL/01845/2024-2025 | BP-2024-25-464 | 18/11/2024 | 18/11/2024 | WBSEDCL | 4.34 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF KACHU KHALI PIPED WATER SUPPLY SCHEME, BLOCK-GOSABA,DISTRICT-SOUTH 24 PARGANAS | SM/18267 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 for Augmentation of Kachukhali water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block:Gosaba] (SM/18267) | Assistant Engineer | Junior Engineer | ORD/000048/2025-2026 | 1429/SMD | 21/05/2025 | 03/10/2025 | DIPALI CONSTRUCTION | 10.34 | 0 | 0 | 0
11 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF KACHU KHALI PIPED WATER SUPPLY SCHEME, BLOCK-GOSABA,DISTRICT-SOUTH 24 PARGANAS | SM/18267 | Augmentation | Renovation and retrofitting of Pump House No. 2 of Augmentation of Kachukhali W/S Scheme, under Gosaba Block of Canning Sub-Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000186/2025-2026 | 550/CSD | 30/04/2025 | 16/02/2026 | BAPAN HALDAR | 2.9 | 0 | 0 | 0
12 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF KACHU KHALI PIPED WATER SUPPLY SCHEME, BLOCK-GOSABA,DISTRICT-SOUTH 24 PARGANAS | SM/18267 | Augmentation | Renovation and retrofitting of Pump House No. 1 of Augmentation of Kachukhali W/S Scheme, under Gosaba Block of Canning Sub-Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000189/2025-2026 | 629/CSD | 21/05/2025 | 20/06/2025 | HALDER & CO. | 2.93 | 0 | 0 | 100
Total | [13 empty] | 765.57 | 330.26 | 43.14