## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION SCHEME FOR HAREKRISHNAPUR PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE, BLOCK - BASANTI | SM/18279 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2,3, & 4 for Augmentation of Harekrishnapur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Basanti] | Assistant Engineer | Junior Engineer | ORD/001514/2022-2023 | 894/SMD | 27/03/2023 | 25/06/2023 | S.P. CONSTRUCTION | 41.63 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION SCHEME FOR HAREKRISHNAPUR PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE, BLOCK - BASANTI | SM/18279 | Augmentation | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Harekrishnapur W/S Scheme, Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-III] | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000288/2023-2024 | 1540/AD | 17/07/2023 | 31/08/2023 | MAA SOLAR ENTERPRISE | 7.11 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION SCHEME FOR HAREKRISHNAPUR PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE, BLOCK - BASANTI | SM/18279 | Augmentation | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Harekrishnapur W/S Scheme, Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-II] | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000286/2023-2024 | 1539/AD | 17/07/2023 | 31/08/2023 | RINAS INFRASTRUCTURE | 7.08 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION SCHEME FOR HAREKRISHNAPUR PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE, BLOCK - BASANTI | SM/18279 | Augmentation | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Harekrishnapur W/S Scheme, Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-IV] | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000290/2023-2024 | 1541/AD | 17/07/2023 | 31/08/2023 | MAA SOLAR ENTERPRISE | 7.11 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION SCHEME FOR HAREKRISHNAPUR PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE, BLOCK - BASANTI | SM/18279 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000003/2023-2024 | 120/AD | 13/04/2023 | 13/04/2023 | Resource Division | 0.34 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION SCHEME FOR HAREKRISHNAPUR PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE, BLOCK - BASANTI | SM/18279 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000031/2023-2024 | 235/AD | 24/04/2023 | 24/04/2023 | Resource Division | 109.7 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION SCHEME FOR HAREKRISHNAPUR PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE, BLOCK - BASANTI | SM/18279 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000140/2023-2024 | 852/AD | 27/05/2023 | 27/05/2023 | Resource Division | 1.72 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION SCHEME FOR HAREKRISHNAPUR PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE, BLOCK - BASANTI | SM/18279 | Augmentation | Laying Distribution System, Providing Functional Household Tap Connection for Ground Water Based Augmentation Piped Water Supply Scheme for the Harekrishnapur, Block-Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [No. of FHTC = 2343] | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000315/2023-2024 | 1516/AD | 15/07/2023 | 13/10/2023 | M/S SHIBAM ENTERPRISE | 405.58 | 0 | 0 | 40
9 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION SCHEME FOR HAREKRISHNAPUR PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE, BLOCK - BASANTI | SM/18279 | Augmentation | Inter connection and rising main with supply of specials of Augmentation of Harekrishnapur W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000238/2023-2024 | 1390/AD | 12/07/2023 | 27/07/2023 | SUPER CONSTRUCTION | 23.7 | 0 | 0 | 80
10 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION SCHEME FOR HAREKRISHNAPUR PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE, BLOCK - BASANTI | SM/18279 | Augmentation | Conducting route survey, design distribution network and preparation & submission of DPR for Harekrishnapur Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Basanti Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/002447/2023-2024 | 1513/AD | 13/03/2024 | 27/04/2024 | M/S APEX ENGINEERING | 7.15 | 0 | 0 | 100
11 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION SCHEME FOR HAREKRISHNAPUR PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE, BLOCK - BASANTI | SM/18279 | Augmentation | Construction of 23 Nos. different capacity R.C.C OHR (based on Departmental Design & Drawing ) with 20 mtr. staging height including Geo-Technical investigation, foundation, pipeline connection and cost of pipes , specials etc. for augmentation of different piped water supply scheme of Canning-I, Canning-II & Basanti Block under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD,Junior Engineer,1 CSD | ORD/002461/2023-2024 | 1512/AD | 13/03/2024 | 03/11/2025 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LTD | 2624.49 | 0 | 0 | 30
Total | [13 empty] | 3235.6 | 0 | 0