## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED MATHER DIGHI (ZONE-I,II & III) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE,BLOCK-CANNING-II,DISTRICT-SOUTH 24 PARGANAS | SM/18280 | Augmentation | Inter connection and rising main with supply of specials of Augmentation of Matherdighi (Zone-I) W/S Scheme, Block-Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000106/2023-2024 | 1545/AD | 17/07/2023 | 01/08/2023 | GANGA TUBEWELL AND HARDWARE | 10.68 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED MATHER DIGHI (ZONE-I,II & III) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE,BLOCK-CANNING-II,DISTRICT-SOUTH 24 PARGANAS | SM/18280 | Augmentation | Inter connection and rising main with supply of specials of Augmentation of Matherdighi (Zone-II) W/S Scheme, Block-Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000107/2023-2024 | 1546/AD | 17/07/2023 | 01/08/2023 | M/S. MIHIR KUMAR NASKAR | 15.23 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED MATHER DIGHI (ZONE-I,II & III) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE,BLOCK-CANNING-II,DISTRICT-SOUTH 24 PARGANAS | SM/18280 | Augmentation | Providing Functional Household Tap Connection (FHTC) of Ground Water Based Augmentation Piped Water Supply Scheme for Matherdighi (Zone-I), Block-Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. [No. of FHTC = 2147] (TSM/016448) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000313/2023-2024 | 1515/AD | 15/07/2023 | 13/10/2023 | M/S ROY TRADING CO. | 139.14 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED MATHER DIGHI (ZONE-I,II & III) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE,BLOCK-CANNING-II,DISTRICT-SOUTH 24 PARGANAS | SM/18280 | Augmentation | Providing Functional Household Tap Connection (FHTC) of Ground Water Based Augmentation Piped Water Supply Scheme for Matherdighi (Zone-II), Block-Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. [No. of FHTC = 1909] (TSM/016448) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000362/2023-2024 | 1563/AD | 17/07/2023 | 15/10/2023 | M/S GIRIDHARI ENTERPRISE | 125.9 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED MATHER DIGHI (ZONE-I,II & III) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE,BLOCK-CANNING-II,DISTRICT-SOUTH 24 PARGANAS | SM/18280 | Augmentation | Conducting route survey, design distribution network and preparation & submission of DPR for Matherdighi (Zone-I, II & III) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Canning-II Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000612/2023-2024 | 1831/AD | 27/07/2023 | 10/09/2023 | INDRANIL DUTTA & ASSOCIATES | 12.1 | 12.1 | 100 | 98
6 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED MATHER DIGHI (ZONE-I,II & III) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE,BLOCK-CANNING-II,DISTRICT-SOUTH 24 PARGANAS | SM/18280 | Augmentation | Laying of Distribution Systemof Ground Water Based Augmentation Piped Water Supply Scheme for Matherdighi (Zone-I), Block-Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (TSM/016448) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000312/2023-2024 | 1514/AD | 15/07/2023 | 13/10/2023 | M/S ROY TRADING CO. | 183.15 | 130.64 | 71.33 | 60
7 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED MATHER DIGHI (ZONE-I,II & III) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE,BLOCK-CANNING-II,DISTRICT-SOUTH 24 PARGANAS | SM/18280 | Augmentation | Sinking of 03 (three) Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Matherdighi W/S Scheme (Zone-I), Block - Canning-II under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000550/2023-2024 | 2082/AD | 07/08/2023 | 06/10/2023 | BHATTACHARJEE & CO. | 60.27 | 32.25 | 53.5 | 66
8 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED MATHER DIGHI (ZONE-I,II & III) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE,BLOCK-CANNING-II,DISTRICT-SOUTH 24 PARGANAS | SM/18280 | Augmentation | Laying of Distribution Systemof Ground Water Based Augmentation Piped Water Supply Scheme for Matherdighi (Zone-II), Block-Canning-II under Canning Sub-Division of Alipore Division, PHE Dte.(TSM/016448) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000361/2023-2024 | 1562/AD | 17/07/2023 | 28/01/2024 | M N J ENTERPRISES | 174.43 | 146.66 | 84.08 | 90
9 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED MATHER DIGHI (ZONE-I,II & III) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE,BLOCK-CANNING-II,DISTRICT-SOUTH 24 PARGANAS | SM/18280 | Augmentation | Sinking of 03 (three) Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Matherdighi W/S Scheme (Zone-II), Block - Canning-II under Canning Sub Division of Alipore Division, P | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000551/2023-2024 | 2083/AD | 07/08/2023 | 19/01/2024 | G.B. CONSTRUCTION (TW) | 60.27 | 8.63 | 14.31 | 65
10 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED MATHER DIGHI (ZONE-I,II & III) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE,BLOCK-CANNING-II,DISTRICT-SOUTH 24 PARGANAS | SM/18280 | Augmentation | Construction of 1 (one) no. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Matherdighi W/S Scheme (Zone-I, II & III), Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (Zone-II, Pump House No. - III) (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/002510/2023-2024 | 1562/AD | 16/03/2024 | 30/04/2024 | MOSTAFIZUR HAQUE GAINE | 7.25 | 0 | 0 | 0
11 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED MATHER DIGHI (ZONE-I,II & III) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE,BLOCK-CANNING-II,DISTRICT-SOUTH 24 PARGANAS | SM/18280 | Augmentation | Construction of 1 (one) no. switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Matherdighi W/S Scheme (Zone-I, II & III), Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (Zone-III, Pump House No. - I) (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/002515/2023-2024 | 1563/AD | 16/03/2024 | 30/04/2024 | M/S GIRIDHARI ENTERPRISE | 7.5 | 0 | 0 | 0
12 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED MATHER DIGHI (ZONE-I,II & III) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE,BLOCK-CANNING-II,DISTRICT-SOUTH 24 PARGANAS | SM/18280 | Augmentation | Construction of 1 (one) no. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Matherdighi W/S Scheme (Zone-I, II & III), Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (Zone-II, Pump House No. - II) (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/002506/2023-2024 | 1561/AD | 16/03/2024 | 30/04/2024 | MOSTAFIZUR HAQUE GAINE | 7.25 | 0 | 0 | 0
13 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED MATHER DIGHI (ZONE-I,II & III) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE,BLOCK-CANNING-II,DISTRICT-SOUTH 24 PARGANAS | SM/18280 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, of Moukhali Kumarkhali (Part-III) Mini piped water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Canning-II] | Assistant Engineer | Junior Engineer | ORD/000588/2022-2023 | 649/SMD | 03/03/2023 | 01/06/2023 | B. P. CONSTRUCTION | 8.85 | 0 | 0 | 100
14 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED MATHER DIGHI (ZONE-I,II & III) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE,BLOCK-CANNING-II,DISTRICT-SOUTH 24 PARGANAS | SM/18280 | Augmentation | Sinking of 03 (three) Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Matherdighi W/S Scheme (Zone-III), Block - Canning-II under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000392/2023-2024 | 1778/AD | 26/07/2023 | 24/09/2023 | CIVIL CRAFT | 59.88 | 52.7 | 88 | 100
15 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED MATHER DIGHI (ZONE-I,II & III) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE,BLOCK-CANNING-II,DISTRICT-SOUTH 24 PARGANAS | SM/18280 | Augmentation | Laying of Pipeline and other allied works of AUGMENTATION OF GROUND WATER BASED MATHER DIGHI (ZONE-I,II and III) PIPED WATER SUPPLY SCHEME , Block ¿ Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (at Matherdighi, Zone-III) SM/18280 | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001018/2023-2024 | 3303/AD | 07/10/2023 | 06/11/2023 | M/S. LOKNATH CONSTRUCTION | 6.24 | 4.71 | 75.52 | 100
16 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED MATHER DIGHI (ZONE-I,II & III) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE,BLOCK-CANNING-II,DISTRICT-SOUTH 24 PARGANAS | SM/18280 | Augmentation | Construction of 1 (one) no. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Matherdighi W/S Scheme (Zone-I, II & III), Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (Zone-III, Pump House No. - II)(2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/002517/2023-2024 | 1564/AD | 16/03/2024 | 01/12/2024 | M/S GIRIDHARI ENTERPRISE | 7.26 | 0 | 0 | 100
17 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED MATHER DIGHI (ZONE-I,II & III) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE,BLOCK-CANNING-II,DISTRICT-SOUTH 24 PARGANAS | SM/18280 | Augmentation | Quotation for new service ( power ) connection at Matherdighi Zone-III, PH-1 under Canning -II block (REF ID : 106665562) (APP ID: 1007924028) |  |  | BILL/00997/2024-2025 | BP-2024-25-197 | 30/07/2024 | 30/07/2024 | WBSEDCL | 2.02 | 0 | 0 | 0
18 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED MATHER DIGHI (ZONE-I,II & III) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE,BLOCK-CANNING-II,DISTRICT-SOUTH 24 PARGANAS | SM/18280 | Augmentation | Quotation for new service ( power ) connection at Matherdighi Zone-III PH-3 under Canning -II block |  |  | BILL/00998/2024-2025 | BP-2024-25-198 | 30/07/2024 | 30/07/2024 | WBSEDCL | 13.33 | 0 | 0 | 0
19 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED MATHER DIGHI (ZONE-I,II & III) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE,BLOCK-CANNING-II,DISTRICT-SOUTH 24 PARGANAS | SM/18280 | Augmentation | Quotation for new service ( power ) connection at Matherdighi Zone-III PH-2 under Canning -II block (REF ID : 106665555) (APP ID: 1007924044) |  |  | BILL/01001/2024-2025 | BP-2024-25-201 | 30/07/2024 | 30/07/2024 | WBSEDCL | 11.04 | 0 | 0 | 0
20 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED MATHER DIGHI (ZONE-I,II & III) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE,BLOCK-CANNING-II,DISTRICT-SOUTH 24 PARGANAS | SM/18280 | Augmentation | Quotation for new service ( power ) connection at Matherdighi Zone-I, PH-2 under Canning -II block (REF ID : 106665560) (APP ID: 1007924076) |  |  | BILL/01003/2024-2025 | BP-2024-25-203 | 30/07/2024 | 30/07/2024 | WBSEDCL | 5.35 | 0 | 0 | 0
21 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED MATHER DIGHI (ZONE-I,II & III) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE,BLOCK-CANNING-II,DISTRICT-SOUTH 24 PARGANAS | SM/18280 | Augmentation | Quotation for new service ( power ) connection at Matherdighi Zone- I PH-3 under Canning -II block (REF ID : 106665563) (APP ID: 1007924056) |  |  | BILL/00999/2024-2025 | BP-2024-25-199 | 30/07/2024 | 30/07/2024 | WBSEDCL | 3.78 | 0 | 0 | 0
22 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED MATHER DIGHI (ZONE-I,II & III) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE,BLOCK-CANNING-II,DISTRICT-SOUTH 24 PARGANAS | SM/18280 | Augmentation | Quotation for new service ( power ) connection at Matherdighi Zone-II, PH-2 under Canning -II block (REF ID : 106665559) (APP ID: 1007924629) |  |  | BILL/01002/2024-2025 | BP-2024-25-202 | 30/07/2024 | 30/07/2024 | WBSEDCL | 3.75 | 0 | 0 | 0
23 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED MATHER DIGHI (ZONE-I,II & III) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE,BLOCK-CANNING-II,DISTRICT-SOUTH 24 PARGANAS | SM/18280 | Augmentation | Quotation for new service( power) connection at Matherdighi and adjoining mouza (inconnction with Kulerkhoj ) PH-1 Water supply scheme under Canning-II block. Reference ID:-106599046, Application No :-1007775984 |  |  | BILL/02038/2024-2025 | BP-2024-25-486 | 09/12/2024 | 09/12/2024 | WBSEDCL | 10.53 | 0 | 0 | 0
24 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED MATHER DIGHI (ZONE-I,II & III) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE,BLOCK-CANNING-II,DISTRICT-SOUTH 24 PARGANAS | SM/18280 | Augmentation | Quotation for new service ( power ) connection at Matherdighi Zone-II, PH-1 under Canning -II block (REF ID : 106665564) (APP ID: 1007924727) |  |  | BILL/01000/2024-2025 | BP-2024-25-200 | 30/07/2024 | 30/07/2024 | WBSEDCL | 13 | 0 | 0 | 0
25 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED MATHER DIGHI (ZONE-I,II & III) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE,BLOCK-CANNING-II,DISTRICT-SOUTH 24 PARGANAS | SM/18280 | Augmentation | Laying of Distribution System, Providing Functional Household Tap Connection (FHTC) etc. of Ground Water Based Augmentation Piped Water Supply Scheme for Matherdighi (Zone-III), Block-Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. [No. of FHTC = 715] (TSM/016448) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000368/2023-2024 | 1569/AD | 17/07/2023 | 18/08/2025 | S.R.ENTERPRISE | 146.5 | 34.21 | 23.35 | 50
26 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED MATHER DIGHI (ZONE-I,II & III) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE,BLOCK-CANNING-II,DISTRICT-SOUTH 24 PARGANAS | SM/18280 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2 & 3, (Zone-I) , P.H. 1,2 & 3, (Zone-II), P.H. 1,2 & 3, (Zone-III) for Augmentation of Mather Dighi Water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Canning-II] | Assistant Engineer | Junior Engineer | ORD/000269/2023-2024 | 1129/SMD | 24/04/2023 | 02/01/2026 | M/S. S.S. ENTERPRISE | 82.02 | 0 | 0 | 30
27 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED MATHER DIGHI (ZONE-I,II & III) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE,BLOCK-CANNING-II,DISTRICT-SOUTH 24 PARGANAS | SM/18280 | Augmentation | Inter connection and rising main with supply of specials of Augmentation of Matherdighi (Zone-III) W/S Scheme, Block-Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. (3rd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001354/2023-2024 | 4426/AD | 06/12/2023 | 15/01/2025 | AHANA ENTERPRISE | 8.02 | 0 | 0 | 90
28 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED MATHER DIGHI (ZONE-I,II & III) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE,BLOCK-CANNING-II,DISTRICT-SOUTH 24 PARGANAS | SM/18280 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, of Kuler Khoj water supply scheme adjacent to Augmentation of Ground water based Mather Dighi ( Zone-I,II & III) piped water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Canning-II] | Assistant Engineer | Junior Engineer | ORD/002930/2023-2024 | 2302/SMD | 27/06/2023 | 06/08/2025 | KARUNAMOY ENGINEERING | 9.25 | 0 | 0 | 95
29 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED MATHER DIGHI (ZONE-I,II & III) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE,BLOCK-CANNING-II,DISTRICT-SOUTH 24 PARGANAS | SM/18280 | Augmentation | Construction of 1 (one) no. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Matherdighi W/S Scheme (Zone-I, II & III), Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (Zone-III, Pump House No. - III) (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/002519/2023-2024 | 1565/AD | 16/03/2024 | 01/02/2025 | RIDIP ENTERPRISE | 7.26 | 0 | 0 | 100
30 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED MATHER DIGHI (ZONE-I,II & III) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE,BLOCK-CANNING-II,DISTRICT-SOUTH 24 PARGANAS | SM/18280 | Augmentation | Construction of 23 Nos. different capacity R.C.C OHR (based on Departmental Design & Drawing ) with 20 mtr. staging height including Geo-Technical investigation, foundation, pipeline connection and cost of pipes , specials etc. for augmentation of different piped water supply scheme of Canning-I, Canning-II & Basanti Block under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD,Junior Engineer,1 CSD | ORD/002461/2023-2024 | 1512/AD | 13/03/2024 | 03/11/2025 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LTD | 2624.49 | 0 | 0 | 30
31 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED MATHER DIGHI (ZONE-I,II & III) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE,BLOCK-CANNING-II,DISTRICT-SOUTH 24 PARGANAS | SM/18280 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, of Baintala water supply scheme adjacent to Augmentation of Ground water based Mather Dighi ( Zone-I,II & III) piped water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Canning-II] | Assistant Engineer | Junior Engineer | ORD/002929/2023-2024 | 2301/SMD | 27/06/2023 | 30/05/2025 | DITHI ENTERPRISE | 9.39 | 2.11 | 22.45 | 90
32 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED MATHER DIGHI (ZONE-I,II & III) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE,BLOCK-CANNING-II,DISTRICT-SOUTH 24 PARGANAS | SM/18280 | Augmentation | Laying of washout pipe line with other allied works at Matherdighi RO Plant (Zone -A) W/S Scheme, Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001051/2024-2025 | 1269/CSD | 18/11/2024 | 18/12/2024 | SUKANTA HALDER | 4.17 | 0 | 0 | 100
33 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED MATHER DIGHI (ZONE-I,II & III) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE,BLOCK-CANNING-II,DISTRICT-SOUTH 24 PARGANAS | SM/18280 | Augmentation | Improvement of outdoor illumination arrangement with allied works at Pump House-1 Kuler Khoj water supply sche under SMD,PHE Dte. (Block-Canning-II) (SM/18280) | Assistant Engineer | Junior Engineer | ORD/002195/2024-2025 | 1754/SMSD | 31/12/2024 | 15/01/2025 | KARUNAMOY ENGINEERING | 0.8 | 0 | 0 | 0
34 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED MATHER DIGHI (ZONE-I,II & III) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE,BLOCK-CANNING-II,DISTRICT-SOUTH 24 PARGANAS | SM/18280 | Augmentation | Construction of 1 (one) no. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Matherdighi W/S Scheme (Zone-I, II, III), Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (Zone-I, Pump House No. - III) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/002569/2024-2025 | 894/AD | 04/03/2025 | 18/04/2025 | KIRON CONSTRUCTION | 7.05 | 0 | 0 | 0
35 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED MATHER DIGHI (ZONE-I,II & III) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE,BLOCK-CANNING-II,DISTRICT-SOUTH 24 PARGANAS | SM/18280 | Augmentation | Construction of 1 (one) no. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Matherdighi W/S Scheme (Zone-I, II, III), Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (Zone-I, Pump House No. - II) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/002566/2024-2025 | 893/AD | 04/03/2025 | 18/04/2025 | GANGA TUBEWELL AND HARDWARE | 7.05 | 0 | 0 | 0
36 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED MATHER DIGHI (ZONE-I,II & III) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE,BLOCK-CANNING-II,DISTRICT-SOUTH 24 PARGANAS | SM/18280 | Augmentation | Supply & Fixing main switch & Bus bar at Zone-III Pump House no- 1 & 2,3 of Aug of Matherdighi W/S Scheme under SMD, P.H.E. Dte.(Block-Canning-II) (SM/18280) | Assistant Engineer | Junior Engineer | ORD/002384/2024-2025 | 465/SMSD | 21/03/2025 | 05/04/2025 | M/S. S.S. ENTERPRISE | 0.88 | 0 | 0 | 0
37 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED MATHER DIGHI (ZONE-I,II & III) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE,BLOCK-CANNING-II,DISTRICT-SOUTH 24 PARGANAS | SM/18280 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Zone-III Pump House no-2 of Aug of Matherdighi W/S Scheme under SMD, P.H.E. Dte.(Block-Canning-II) (SM/18280) | Assistant Engineer | Junior Engineer | ORD/002385/2024-2025 | 456/SMSD | 21/03/2025 | 05/04/2025 | M/S. S.S. ENTERPRISE | 0.71 | 0 | 0 | 0
38 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED MATHER DIGHI (ZONE-I,II & III) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE,BLOCK-CANNING-II,DISTRICT-SOUTH 24 PARGANAS | SM/18280 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Zone-III Pump House no-3 of Aug of Matherdighi W/S Scheme under SMD, P.H.E. Dte.(Block-Canning-II) (SM/18280) | Assistant Engineer | Junior Engineer | ORD/002387/2024-2025 | 458/SMSD | 21/03/2025 | 05/04/2025 | M/S. S.S. ENTERPRISE | 0.71 | 0 | 0 | 0
39 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED MATHER DIGHI (ZONE-I,II & III) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE,BLOCK-CANNING-II,DISTRICT-SOUTH 24 PARGANAS | SM/18280 | Augmentation | Supply delivery of UPVC column pipe, sluice valve non return valve etc. at Zone-III PH-1 Aug of Matherdighi water supply scheme under Canning-II Block under SMD, P.H.E. Dte. (SM/18280) | Assistant Engineer | Junior Engineer | ORD/002388/2024-2025 | 464/SMSD | 21/03/2025 | 05/04/2025 | M/S. S.S. ENTERPRISE | 0.74 | 0 | 0 | 0
40 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED MATHER DIGHI (ZONE-I,II & III) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE,BLOCK-CANNING-II,DISTRICT-SOUTH 24 PARGANAS | SM/18280 | Augmentation | Supply delivery of Cast Iron wafer type 3 phase actuator operated wafer type butterfly valve at Zone-III PH-1 Aug of Matherdighi water supply scheme under Canning -II block Under SMD PHE Dte. (SM/18280) | Assistant Engineer | Junior Engineer | ORD/002389/2024-2025 | 463/SMSD | 21/03/2025 | 05/04/2025 | M/S. S.S. ENTERPRISE | 0.99 | 0 | 0 | 0
41 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED MATHER DIGHI (ZONE-I,II & III) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE,BLOCK-CANNING-II,DISTRICT-SOUTH 24 PARGANAS | SM/18280 | Augmentation | Supply delivery of UPVC column pipe, sluice valve non return valve etc. at Zone-III PH-2 Aug of Matherdighi water supply scheme under Canning-II Block under SMD, P.H.E. Dte. (SM/18280) | Assistant Engineer | Junior Engineer | ORD/002390/2024-2025 | 462/SMSD | 21/03/2025 | 05/04/2025 | M/S. S.S. ENTERPRISE | 0.74 | 0 | 0 | 0
42 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED MATHER DIGHI (ZONE-I,II & III) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE,BLOCK-CANNING-II,DISTRICT-SOUTH 24 PARGANAS | SM/18280 | Augmentation | Supply delivery of Cast Iron wafer type 3 phase actuator operated wafer type butterfly valve at Zone-III PH-2 Aug of Matherdighi water supply scheme under Canning -II block Under SMD PHE Dte. (SM/18280) | Assistant Engineer | Junior Engineer | ORD/002391/2024-2025 | 461/SMSD | 21/03/2025 | 05/04/2025 | M/S. S.S. ENTERPRISE | 0.99 | 0 | 0 | 0
43 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED MATHER DIGHI (ZONE-I,II & III) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE,BLOCK-CANNING-II,DISTRICT-SOUTH 24 PARGANAS | SM/18280 | Augmentation | Supply delivery of UPVC column pipe, sluice valve non return valve etc. at Zone-III PH-3 Aug of Matherdighi water supply scheme under Canning-II Block under SMD, P.H.E. Dte. (SM/18280) | Assistant Engineer | Junior Engineer | ORD/002392/2024-2025 | 460/SMSD | 21/03/2025 | 05/04/2025 | M/S. S.S. ENTERPRISE | 0.74 | 0 | 0 | 0
44 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED MATHER DIGHI (ZONE-I,II & III) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE,BLOCK-CANNING-II,DISTRICT-SOUTH 24 PARGANAS | SM/18280 | Augmentation | Supply delivery of Cast Iron wafer type 3 phase actuator operated wafer type butterfly valve at Zone-III PH-3 Aug of Matherdighi water supply scheme under Canning -II block Under SMD PHE Dte. (SM/18280) | Assistant Engineer | Junior Engineer | ORD/002393/2024-2025 | 459/SMSD | 21/03/2025 | 05/04/2025 | M/S. S.S. ENTERPRISE | 0.99 | 0 | 0 | 0
45 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED MATHER DIGHI (ZONE-I,II & III) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE,BLOCK-CANNING-II,DISTRICT-SOUTH 24 PARGANAS | SM/18280 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Zone-III Pump House no-1 of Aug of Matherdighi W/S Scheme under SMD, P.H.E. Dte.(Block-Canning-II) (SM/18280) | Assistant Engineer | Junior Engineer | ORD/002386/2024-2025 | 457/SMSD | 21/03/2025 | 05/04/2025 | M/S. S.S. ENTERPRISE | 0.73 | 0 | 0 | 0
46 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED MATHER DIGHI (ZONE-I,II & III) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE,BLOCK-CANNING-II,DISTRICT-SOUTH 24 PARGANAS | SM/18280 | Augmentation | Supply delivery of submersible pump motor at Aug of Matherdighi Zone-III PH-1 water supply scheme under Canning-II block Under SMD PHE Dte. (SM/18280) | Assistant Engineer | Junior Engineer | ORD/002438/2024-2025 | 409/SMSD | 20/03/2025 | 10/04/2025 | M/S. S.S. ENTERPRISE | 0.57 | 0 | 0 | 0
47 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED MATHER DIGHI (ZONE-I,II & III) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE,BLOCK-CANNING-II,DISTRICT-SOUTH 24 PARGANAS | SM/18280 | Augmentation | Supply delivery of submersible pump motor at Aug of Matherdighi Zone-III PH-3 water supply scheme under Canning-II block Under SMD PHE Dte. (SM/18280) | Assistant Engineer | Junior Engineer | ORD/002439/2024-2025 | 410/SMSD | 20/03/2025 | 10/04/2025 | M/S. S.S. ENTERPRISE | 0.57 | 0 | 0 | 0
48 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED MATHER DIGHI (ZONE-I,II & III) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE,BLOCK-CANNING-II,DISTRICT-SOUTH 24 PARGANAS | SM/18280 | Augmentation | Supply delivery of submersible pump motor at Aug of Matherdighi Zone-III PH-2 water supply scheme under Canning-II block Under SMD PHE Dte. (SM/18280) | Assistant Engineer | Junior Engineer | ORD/002440/2024-2025 | 466/SMSD | 21/03/2025 | 11/04/2025 | M/S. S.S. ENTERPRISE | 0.57 | 0 | 0 | 0
Total | [13 empty] | 3864.16 | 424.01 | 10.97