## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF TILKUMAR PIPED WATER SUPPLY SCHEME, BLOCK-BASANTI UNDER ALIPORE DIVISION, PHE DTE | SM/18281 | Augmentation | Inter connection and rising main with supply of specials of Augmentation of Tilkumar (Zone-II) W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000104/2023-2024 | 1543/AD | 17/07/2023 | 01/08/2023 | DIPTI ENTERPRISE | 8.77 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF TILKUMAR PIPED WATER SUPPLY SCHEME, BLOCK-BASANTI UNDER ALIPORE DIVISION, PHE DTE | SM/18281 | Augmentation | Inter connection and rising main with supply of specials of Augmentation of Tilkumar (Zone-I) W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000103/2023-2024 | 1542/AD | 17/07/2023 | 01/08/2023 | DIPTI ENTERPRISE | 8.34 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF TILKUMAR PIPED WATER SUPPLY SCHEME, BLOCK-BASANTI UNDER ALIPORE DIVISION, PHE DTE | SM/18281 | Augmentation | Construction of boundary wall and Land development for head work Site for Augmentation of Tilkumar (Zone-I, II & III) W/S Scheme Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [for Zone-II] | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 3 CSD | ORD/000773/2024-2025 | 4475/AD | 11/11/2024 | 26/12/2024 | SUDIP PRADHAN | 42.27 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF TILKUMAR PIPED WATER SUPPLY SCHEME, BLOCK-BASANTI UNDER ALIPORE DIVISION, PHE DTE | SM/18281 | Augmentation | Construction of boundary wall and Land development for T/W No - 2 Site for Augmentation of Tilkumar (Zone-I, II & III) W/S Scheme Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [for Zone-III] | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/001306/2024-2025 | 5380/AD | 23/12/2024 | 22/01/2025 | AAHAN CONSTRUCTION | 11.98 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF TILKUMAR PIPED WATER SUPPLY SCHEME, BLOCK-BASANTI UNDER ALIPORE DIVISION, PHE DTE | SM/18281 | Augmentation | Construction of boundary wall and Land development for T/W No - 3 Site for Augmentation of Tilkumar (Zone-I, II & III) W/S Scheme Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [for Zone-II] | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 3 CSD | ORD/000772/2024-2025 | 4474/AD | 11/11/2024 | 11/12/2024 | B.S.ENTERPRISE | 16.16 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF TILKUMAR PIPED WATER SUPPLY SCHEME, BLOCK-BASANTI UNDER ALIPORE DIVISION, PHE DTE | SM/18281 | Augmentation | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing on Augmentation and Retrofitting of Tilkumar PWSS, Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. (Zone-II, Pump House No. - III) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/001907/2023-2024 | 221/AD | 11/01/2024 | 25/02/2024 | M/S ASHA ENGINEERING | 6.65 | 6.64 | 99.81 | 98
7 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF TILKUMAR PIPED WATER SUPPLY SCHEME, BLOCK-BASANTI UNDER ALIPORE DIVISION, PHE DTE | SM/18281 | Augmentation | Conducting route survey, design distribution network and preparation & submission of DPR for Tilkumar (Zone-I, II & III) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Basanti Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer,1 CSD | ORD/002448/2023-2024 | 1514/AD | 15/03/2024 | 29/04/2024 | M/S APEX ENGINEERING | 22.4 | 22.4 | 100 | 100
8 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF TILKUMAR PIPED WATER SUPPLY SCHEME, BLOCK-BASANTI UNDER ALIPORE DIVISION, PHE DTE | SM/18281 | Augmentation | RESTORATION OF KOLKATA BASANTI ROAD FROM 68.00 TO 96.255 KM BLOCK CANNING I UNDER SOUTH 24 PARGANAS HIGHWAY DIVISION, DAMAGED CAUSED DUE TO LAYING OF WATER PIPE LINE BY PHED UNDER CSD |  |  | BILL/01320/2024-2025 | BP-2024-25-684 | 04/10/2024 | 04/10/2024 | EXECUTIVE ENGNEER, 24 PGS. HIGHWAY DIVN, P.W.(ROADS) DEPTT. | 416.07 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF TILKUMAR PIPED WATER SUPPLY SCHEME, BLOCK-BASANTI UNDER ALIPORE DIVISION, PHE DTE | SM/18281 | Augmentation | Restoration of Basanti Herobhanga Road from 0.00 kmp to 19.95km. block Basanti under South 24 Pags. Highway Division damaged caused due to laying of water pipe lines by PHED under Canning Sub Division of Alipore Division |  |  | BILL/01321/2024-2025 | BP-2024-25-683 | 04/10/2024 | 04/10/2024 | EXECUTIVE ENGNEER, 24 PGS. HIGHWAY DIVN, P.W.(ROADS) DEPTT. | 107.4 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF TILKUMAR PIPED WATER SUPPLY SCHEME, BLOCK-BASANTI UNDER ALIPORE DIVISION, PHE DTE | SM/18281 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2,3,4,5 & 6 Zone-I for Augmentation of Tilkumar water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Basanti] | Assistant Engineer | Junior Engineer | ORD/001513/2022-2023 | 889/SMD | 24/03/2023 | 02/05/2025 | S.P. CONSTRUCTION | 65.3 | 30.65 | 46.94 | 80
11 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF TILKUMAR PIPED WATER SUPPLY SCHEME, BLOCK-BASANTI UNDER ALIPORE DIVISION, PHE DTE | SM/18281 | Augmentation | Laying Distribution System for Augmentation of Tilkumar W/S Scheme (Zone-I, Zone-II and Zone-III), Block-Basanti under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer,1 CSD | ORD/000483/2023-2024 | 1996/AD | 04/08/2023 | 03/04/2025 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 556.14 | 148.59 | 26.72 | 70
12 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF TILKUMAR PIPED WATER SUPPLY SCHEME, BLOCK-BASANTI UNDER ALIPORE DIVISION, PHE DTE | SM/18281 | Augmentation | Construction of 23 Nos. different capacity R.C.C OHR (based on Departmental Design & Drawing ) with 20 mtr. staging height including Geo-Technical investigation, foundation, pipeline connection and cost of pipes , specials etc. for augmentation of different piped water supply scheme of Canning-I, Canning-II & Basanti Block under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD,Junior Engineer,1 CSD | ORD/002461/2023-2024 | 1512/AD | 13/03/2024 | 03/11/2025 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LTD | 2624.49 | 0 | 0 | 30
13 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF TILKUMAR PIPED WATER SUPPLY SCHEME, BLOCK-BASANTI UNDER ALIPORE DIVISION, PHE DTE | SM/18281 | Augmentation | Construction of boundary wall and Land development for T/W No - 2 Site for Augmentation of Tilkumar (Zone-I, II & III) W/S Scheme Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. (for Zone-II) (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000034/2025-2026 | 2020/AD | 28/04/2025 | 28/05/2025 | SAHANA ENTERPRISE | 14.69 | 0 | 0 | 0
Total | [13 empty] | 3900.67 | 208.29 | 5.34