## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF TILKUMAR PIPED WATER SUPPLY SCHEME, BLOCK-BASANTI UNDER ALIPORE DIVISION, PHE DTE | SM/18281 | Augmentation | Inter connection and rising main with supply of specials of Augmentation of Tilkumar (Zone-II) W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000104/2023-2024 | 1543/AD | 17/07/2023 | 01/08/2023 | DIPTI ENTERPRISE | 8.77 | 0 | 0 | 0
2 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF TILKUMAR PIPED WATER SUPPLY SCHEME, BLOCK-BASANTI UNDER ALIPORE DIVISION, PHE DTE | SM/18281 | Augmentation | Inter connection and rising main with supply of specials of Augmentation of Tilkumar (Zone-I) W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000103/2023-2024 | 1542/AD | 17/07/2023 | 01/08/2023 | DIPTI ENTERPRISE | 8.34 | 0 | 0 | 0
3 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF TILKUMAR PIPED WATER SUPPLY SCHEME, BLOCK-BASANTI UNDER ALIPORE DIVISION, PHE DTE | SM/18281 | Augmentation | Construction of 23 Nos. different capacity R.C.C OHR (based on Departmental Design & Drawing ) with 20 mtr. staging height including Geo-Technical investigation, foundation, pipeline connection and cost of pipes , specials etc. for augmentation of different piped water supply scheme of Canning-I, Canning-II & Basanti Block under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/002461/2023-2024 | 1512/AD | 13/03/2024 | 07/01/2025 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LTD | 2624.49 | 0 | 0 | 30
4 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF TILKUMAR PIPED WATER SUPPLY SCHEME, BLOCK-BASANTI UNDER ALIPORE DIVISION, PHE DTE | SM/18281 | Augmentation | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing on Augmentation and Retrofitting of Tilkumar PWSS, Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. (Zone-II, Pump House No. - III) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/001907/2023-2024 | 221/AD | 11/01/2024 | 25/02/2024 | M/S ASHA ENGINEERING | 6.65 | 3.32 | 49.91 | 98
5 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF TILKUMAR PIPED WATER SUPPLY SCHEME, BLOCK-BASANTI UNDER ALIPORE DIVISION, PHE DTE | SM/18281 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2,3,4,5 & 6 Zone-I for Augmentation of Tilkumar water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Basanti] | Assistant Engineer | Junior Engineer | ORD/001513/2022-2023 | 889/SMD | 24/03/2023 | 22/06/2023 | S.P. CONSTRUCTION | 65.3 | 15.33 | 23.47 | 50
6 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF TILKUMAR PIPED WATER SUPPLY SCHEME, BLOCK-BASANTI UNDER ALIPORE DIVISION, PHE DTE | SM/18281 | Augmentation | Conducting route survey, design distribution network and preparation & submission of DPR for Tilkumar (Zone-I, II & III) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Basanti Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer,1 CSD | ORD/002448/2023-2024 | 1514/AD | 15/03/2024 | 29/04/2024 | M/S APEX ENGINEERING | 22.4 | 0 | 0 | 100
7 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF TILKUMAR PIPED WATER SUPPLY SCHEME, BLOCK-BASANTI UNDER ALIPORE DIVISION, PHE DTE | SM/18281 | Augmentation | Laying Distribution System for Augmentation of Tilkumar W/S Scheme (Zone-I, Zone-II and Zone-III), Block-Basanti under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer,1 CSD | ORD/000483/2023-2024 | 1996/AD | 04/08/2023 | 02/11/2023 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 556.14 | 0 | 0 | 28
Total | [13 empty] | 3292.1 | 18.65 | 0.57