## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF BHANGAN KHALI PIPED WATER SUPPLY SCHEME BLOCK-BASANTI UNDER CANNING SUB-DIVISION OF ALIPORE DIVISION,PHE DTE | SM/18286 | Augmentation | Construction of OHR (500 cum.), Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water Based Augmentation Piped Water Supply Scheme for the Bhangankhali,Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer,1 CSD | ORD/000352/2023-2024 | 1661/AD | 20/07/2023 | 15/05/2024 | SPA ENTERPRISE | 636.93 | 10.7 | 1.68 | 5
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF BHANGAN KHALI PIPED WATER SUPPLY SCHEME BLOCK-BASANTI UNDER CANNING SUB-DIVISION OF ALIPORE DIVISION,PHE DTE | SM/18286 | Augmentation | Inter connection and rising main with supply of specials of Augmentation of Bhangankhali W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000493/2023-2024 | 1793/AD | 26/07/2023 | 24/09/2023 | M/S KRISHNA MONDAL | 88.05 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF BHANGAN KHALI PIPED WATER SUPPLY SCHEME BLOCK-BASANTI UNDER CANNING SUB-DIVISION OF ALIPORE DIVISION,PHE DTE | SM/18286 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000034/2023-2024 | 239/AD | 24/04/2023 | 24/04/2023 | Resource Division | 142.93 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF BHANGAN KHALI PIPED WATER SUPPLY SCHEME BLOCK-BASANTI UNDER CANNING SUB-DIVISION OF ALIPORE DIVISION,PHE DTE | SM/18286 | Augmentation | Renovation of Pump House No. 3 and its boundary wall of Bhangankhali W/S Scheme, under Basanti Block of Canning Sub-Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/002514/2023-2024 | 1605/CSD | 28/02/2024 | 29/03/2024 | DIPA CHHETRI | 2.03 | 1.98 | 97.34 | 95
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF BHANGAN KHALI PIPED WATER SUPPLY SCHEME BLOCK-BASANTI UNDER CANNING SUB-DIVISION OF ALIPORE DIVISION,PHE DTE | SM/18286 | Augmentation | RESTORATION OF KOLKATA BASANTI ROAD FROM 68.00 TO 96.255 KM BLOCK CANNING I UNDER SOUTH 24 PARGANAS HIGHWAY DIVISION, DAMAGED CAUSED DUE TO LAYING OF WATER PIPE LINE BY PHED UNDER CSD |  |  | BILL/01320/2024-2025 | BP-2024-25-684 | 04/10/2024 | 04/10/2024 | EXECUTIVE ENGNEER, 24 PGS. HIGHWAY DIVN, P.W.(ROADS) DEPTT. | 416.07 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF BHANGAN KHALI PIPED WATER SUPPLY SCHEME BLOCK-BASANTI UNDER CANNING SUB-DIVISION OF ALIPORE DIVISION,PHE DTE | SM/18286 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 for Augmentation of Bhangankhali water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Basanti] (SM/18286) | Assistant Engineer | Junior Engineer | ORD/000081/2025-2026 | 1442/SMD | 22/05/2025 | 04/10/2025 | M/S. A.K. BANERJEE | 11.13 | 0 | 0 | 0
Total | [13 empty] | 1297.13 | 12.68 | 0.98