## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF KALARIA PIPED WATER SUPPLY SCHEME IN CANNING-I BLOCK IN SOUTH 24 PARGANAS OF CANNING SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18332 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2,3,4,5,6 & 7 for Augmentation of Kalaria water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Canning-I] | Assistant Engineer | Junior Engineer | ORD/000108/2023-2024 | 938/SMD | 04/04/2023 | 03/07/2023 | M/S. S.S. ENTERPRISE | 78.3 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF KALARIA PIPED WATER SUPPLY SCHEME IN CANNING-I BLOCK IN SOUTH 24 PARGANAS OF CANNING SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18332 | Augmentation | Land development work at Over Head Reservoir site of Kalaria W/S Scheme (Zone-I), under Canning-I Block, south 24 parganas Distric of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/001643/2021-2022 | 1511/CSD | 15/02/2022 | 02/03/2022 | ASHIS ENTERPRISE | 1.98 | 1.97 | 99.52 | 100
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF KALARIA PIPED WATER SUPPLY SCHEME IN CANNING-I BLOCK IN SOUTH 24 PARGANAS OF CANNING SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18332 | Augmentation | Land development work at Over Head Reservoir site (balance portion) of Kalaria W/S Scheme (Zone-I), under Canning-I Block, south 24 parganas District of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000867/2022-2023 | 844/CSD | 16/08/2022 | 10/09/2022 | ASHIS ENTERPRISE | 3.54 | 3.54 | 99.86 | 100
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF KALARIA PIPED WATER SUPPLY SCHEME IN CANNING-I BLOCK IN SOUTH 24 PARGANAS OF CANNING SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18332 | Augmentation | Construction of boundary wall at Pump House No. - 2 at Ground Water Based Piped Water Supply Scheme of Kalaria (Zone - IIB) W/S Scheme Block - Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000686/2024-2025 | 4291/AD | 29/10/2024 | 28/11/2024 | HARIDAS DUTTA | 8.59 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF KALARIA PIPED WATER SUPPLY SCHEME IN CANNING-I BLOCK IN SOUTH 24 PARGANAS OF CANNING SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18332 | Augmentation | Construction of boundary wall at Pump House No. - 2 at Ground Water Based Piped Water Supply Scheme of Kalaria (Zone - IB) W/S Scheme Block - Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000684/2024-2025 | 4289/AD | 29/10/2024 | 28/11/2024 | ASHIS ENTERPRISE | 10.8 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF KALARIA PIPED WATER SUPPLY SCHEME IN CANNING-I BLOCK IN SOUTH 24 PARGANAS OF CANNING SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18332 | Augmentation | Laying damaged pipe line due to widening of road by South 24 Parganas Zilla Parishad from Piali Railway Station to Nawbhasan More at Kalaria W/S Scheme (Zone-I), Block-Canning-I under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000280/2022-2023 | 273/CSD | 19/05/2022 | 18/06/2022 | ASHIS ENTERPRISE | 4.18 | 0 | 0 | 100
7 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF KALARIA PIPED WATER SUPPLY SCHEME IN CANNING-I BLOCK IN SOUTH 24 PARGANAS OF CANNING SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18332 | Augmentation | Supply and delivery of DI fittings and construction of Sluice Valve Chamber for the proposed DI line from Piali Railway Station to Nawbhasan More at Kalaria W/S Scheme (Zone-I), Block-Canning-I under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000999/2022-2023 | 849/CSD | 18/08/2022 | 17/09/2022 | ASHIS ENTERPRISE | 4.76 | 0 | 0 | 100
8 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF KALARIA PIPED WATER SUPPLY SCHEME IN CANNING-I BLOCK IN SOUTH 24 PARGANAS OF CANNING SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18332 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000002/2024-2025 | 4550/AD | 13/11/2024 | 13/11/2024 | Resource Division | 61.6 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF KALARIA PIPED WATER SUPPLY SCHEME IN CANNING-I BLOCK IN SOUTH 24 PARGANAS OF CANNING SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18332 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000003/2024-2025 | 5158/AD | 12/12/2024 | 12/12/2024 | Resource Division | 123.2 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF KALARIA PIPED WATER SUPPLY SCHEME IN CANNING-I BLOCK IN SOUTH 24 PARGANAS OF CANNING SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18332 | Augmentation | Construction of boundary wall at Pump House No. - 3 at Ground Water Based Piped Water Supply Scheme of Kalaria (Zone - IB) W/S Scheme Block - Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000685/2024-2025 | 4290/AD | 29/10/2024 | 28/11/2024 | SAHANA ENTERPRISE | 8.33 | 0 | 0 | 68
11 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF KALARIA PIPED WATER SUPPLY SCHEME IN CANNING-I BLOCK IN SOUTH 24 PARGANAS OF CANNING SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18332 | Augmentation | Construction of boundary wall at Pump House No. - 1 at Ground Water Based Piped Water Supply Scheme of Kalaria (Zone - IB) W/S Scheme Block - Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000683/2024-2025 | 4288/AD | 29/10/2024 | 27/05/2025 | SAHANA ENTERPRISE | 4.83 | 0 | 0 | 0
12 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF KALARIA PIPED WATER SUPPLY SCHEME IN CANNING-I BLOCK IN SOUTH 24 PARGANAS OF CANNING SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18332 | Augmentation | Supply and delivery of wafer type 3 phase actuator operated wafer type butterfly valve at Kalaria Augmentation water supply scheme of Zone -IA, PH-1 under South 24 pgs. Mechanical Division, PHE Dte. [Canning -I] | Assistant Engineer | Junior Engineer | ORD/000163/2024-2025 | 586/SMSD | 13/05/2024 | 28/05/2024 | PADMA ENGINEERING CO. | 0.99 | 0 | 0 | 100
13 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF KALARIA PIPED WATER SUPPLY SCHEME IN CANNING-I BLOCK IN SOUTH 24 PARGANAS OF CANNING SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18332 | Augmentation | Renovation of Electro-Mechanical works at Zone ¿IB, PH-1 of Kalaria Augmentation water supply scheme under South 24 pgs. Mechanical Division, PHE Dte. [Canning-I] | Assistant Engineer | Junior Engineer | ORD/000137/2024-2025 | 587/SMSD | 13/05/2024 | 28/05/2024 | PADMA ENGINEERING CO. | 0.58 | 0 | 0 | 100
14 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF KALARIA PIPED WATER SUPPLY SCHEME IN CANNING-I BLOCK IN SOUTH 24 PARGANAS OF CANNING SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18332 | Augmentation | Renovation of Electro-Mechanical works at Zone ¿IA, PH-1 of Kalaria Augmentation water supply scheme under South 24 pgs. Mechanical Division, PHE Dte. [Canning-I] | Assistant Engineer | Junior Engineer | ORD/000159/2024-2025 | 589/SMSD | 13/05/2024 | 28/05/2024 | PADMA ENGINEERING CO. | 0.58 | 0 | 0 | 100
15 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF KALARIA PIPED WATER SUPPLY SCHEME IN CANNING-I BLOCK IN SOUTH 24 PARGANAS OF CANNING SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18332 | Augmentation | Supply and delivery of wafer type 3 phase actuator operated wafer type butterfly valve at Kalaria Augmentation water supply scheme of Zone -IA, PH-2 under South 24 pgs. Mechanical Division, PHE Dte. [Canning -I] | Assistant Engineer | Junior Engineer | ORD/000160/2024-2025 | 585/SMSD | 13/05/2024 | 28/05/2024 | PADMA ENGINEERING CO. | 0.99 | 0 | 0 | 100
16 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF KALARIA PIPED WATER SUPPLY SCHEME IN CANNING-I BLOCK IN SOUTH 24 PARGANAS OF CANNING SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18332 | Augmentation | Installation of submersible pumping machinery along with allied works at Zone -1A, PH No-2 of Kalaria Augmentation water supply scheme under south 24 pgs. Mechanical Division ,PHE Dte.[Canning -I] | Assistant Engineer | Junior Engineer | ORD/000162/2024-2025 | 581/SMSD | 13/05/2024 | 28/05/2024 | PADMA ENGINEERING CO. | 0.97 | 0 | 0 | 100
17 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF KALARIA PIPED WATER SUPPLY SCHEME IN CANNING-I BLOCK IN SOUTH 24 PARGANAS OF CANNING SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18332 | Augmentation | Installation of submersible pumping machinery along with allied works at Zone -1A, PH No-1 of Kalaria Augmentation water supply scheme under south 24 pgs. Mechanical Division ,PHE Dte.[Canning -I] | Assistant Engineer | Junior Engineer | ORD/000153/2024-2025 | 591/SMSD | 13/05/2024 | 28/05/2024 | PADMA ENGINEERING CO. | 0.97 | 0 | 0 | 100
18 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF KALARIA PIPED WATER SUPPLY SCHEME IN CANNING-I BLOCK IN SOUTH 24 PARGANAS OF CANNING SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18332 | Augmentation | Renevation of auto panel and allied works at Zone-IB, PH- 1 of Kalaria Augmentation water supply scheme under south 24 pgs. Mechanical Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000156/2024-2025 | 593/SMSD | 13/05/2024 | 28/05/2024 | PADMA ENGINEERING CO. | 0.9 | 0 | 0 | 100
19 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF KALARIA PIPED WATER SUPPLY SCHEME IN CANNING-I BLOCK IN SOUTH 24 PARGANAS OF CANNING SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18332 | Augmentation | Installation of submersible pumping machinery along with allied works at Zone -1B, PH No-1 of Kalaria Augmentation water supply scheme under south 24 pgs. Mechanical Division ,PHE Dte.[Canning -I] | Assistant Engineer | Junior Engineer | ORD/000157/2024-2025 | 590/SMSD | 13/05/2024 | 28/05/2024 | PADMA ENGINEERING CO. | 0.97 | 0 | 0 | 100
20 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF KALARIA PIPED WATER SUPPLY SCHEME IN CANNING-I BLOCK IN SOUTH 24 PARGANAS OF CANNING SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18332 | Augmentation | Renovation of Electro-Mechanical works at Zone ¿IA, PH-2 of Kalaria Augmentation water supply scheme under South 24 pgs. Mechanical Division, PHE Dte. [Canning-I] | Assistant Engineer | Junior Engineer | ORD/000158/2024-2025 | 588/SMSD | 13/05/2024 | 28/05/2024 | PADMA ENGINEERING CO. | 0.58 | 0 | 0 | 100
21 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF KALARIA PIPED WATER SUPPLY SCHEME IN CANNING-I BLOCK IN SOUTH 24 PARGANAS OF CANNING SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18332 | Augmentation | Supply and delivery of wafer type 3 phase actuator operated wafer type butterfly valve at Kalaria Augmentation water supply scheme of Zone -IB, PH-1 under South 24 pgs. Mechanical Division, PHE Dte. [Canning -I] | Assistant Engineer | Junior Engineer | ORD/000161/2024-2025 | 584/SMSD | 13/05/2024 | 28/05/2024 | PADMA ENGINEERING CO. | 0.99 | 0 | 0 | 100
22 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF KALARIA PIPED WATER SUPPLY SCHEME IN CANNING-I BLOCK IN SOUTH 24 PARGANAS OF CANNING SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18332 | Augmentation | Improvement of outdoor illumination arrangement with allied works at Kalaria Zone-1B PH-3 under Canning-I Block water supply scheme under SMD,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002784/2023-2024 | 204/SMSD | 13/02/2024 | 28/02/2024 | PADMA ENGINEERING CO. | 0.89 | 0 | 0 | 100
23 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF KALARIA PIPED WATER SUPPLY SCHEME IN CANNING-I BLOCK IN SOUTH 24 PARGANAS OF CANNING SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18332 | Augmentation | Renevation of auto panel and allied works at Zone-IA, PH- 2 of Kalaria Augmentation water supply scheme under south 24 pgs. Mechanical Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000154/2024-2025 | 595/SMSD | 16/05/2024 | 31/05/2024 | PADMA ENGINEERING CO. | 0.9 | 0 | 0 | 100
24 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF KALARIA PIPED WATER SUPPLY SCHEME IN CANNING-I BLOCK IN SOUTH 24 PARGANAS OF CANNING SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18332 | Augmentation | Renevation of auto panel and allied works at Zone-IA, PH- 1 of Kalaria Augmentation water supply scheme under south 24 pgs. Mechanical Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000155/2024-2025 | 592/SMSD | 13/05/2024 | 28/05/2024 | PADMA ENGINEERING CO. | 0.9 | 0 | 0 | 100
25 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF KALARIA PIPED WATER SUPPLY SCHEME IN CANNING-I BLOCK IN SOUTH 24 PARGANAS OF CANNING SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18332 | Augmentation | Supply, delivery, Installation of 3 Phase 25 KVA (range from 200V-500V oil cooled type) microprocessor based servo motor operated voltage stabilizer at Kalaria Aug. W/S scheme Zone-IA PH- 1and 2 and Zone-IB PH-1 of Canning-I block under SMD PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000437/2024-2025 | 2732/SMD | 02/09/2024 | 01/03/2025 | PADMA ENGINEERING CO. | 7.95 | 0 | 0 | 100
26 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF KALARIA PIPED WATER SUPPLY SCHEME IN CANNING-I BLOCK IN SOUTH 24 PARGANAS OF CANNING SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18332 | Augmentation | Improvement of outdoor illumination arrangement with allied works at Kalaria Zone-IIB, PH-1 under Canning-I Block water supply scheme under SMD, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002348/2024-2025 | 1477/SMSD | 06/11/2024 | 21/11/2024 | JYOTY SOLAR POWER | 0.9 | 0 | 0 | 100
Total | [13 empty] | 330.15 | 5.51 | 1.67