## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-I, MATHURAPUR-I BLOCK FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) IN CONNECTION WITH JAL JEEVAN MISSION (JJM) UNDER MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR UNDER ALIPORE | SM/18378 | Augmentation | Restoration of concrete village road for LDS work at Zone-I (Node point Y-Z) of Mathurapur-I Block under 'Mega surface water based water supply scheme-Falta Mathurapur, Dist. ¿ South 24 Parganas¿ under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division |  | ORD/003184/2020-2021 | 357/RSD | 13/10/2020 | 12/11/2020 | M/S. GANGA ENTERPRISE | 4.8 | 3.96 | 82.42 | 100
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-I, MATHURAPUR-I BLOCK FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) IN CONNECTION WITH JAL JEEVAN MISSION (JJM) UNDER MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR UNDER ALIPORE | SM/18378 | Augmentation | Sinking of 01 (one) No. 250mm x 150mm dia. 360 mtr. deep Replacement Tubewell (Pump House No. 2) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter for Augmentation of Tentulberia W/S Scheme (Zone-I, Mathurapur-I Block) in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer-1, South 24 WS Circle. | ORD/001258/2023-2024 | 4183/AD | 28/11/2023 | 28/12/2023 | MEHAI TECHNOLOGY LIMITED | 19.84 | 15.22 | 76.7 | 95
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-I, MATHURAPUR-I BLOCK FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) IN CONNECTION WITH JAL JEEVAN MISSION (JJM) UNDER MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR UNDER ALIPORE | SM/18378 | Augmentation | Supply of Specials, laying DI pipeline including restoration of road in connection with piped water supply at Zone-I Mathurapur-I Block in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer-1, South 24 WS Circle. | ORD/000281/2024-2025 | 2629/AD | 20/06/2024 | 18/09/2024 | M/S B. ENTERPRISE | 127.22 | 107.42 | 84.44 | 95
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-I, MATHURAPUR-I BLOCK FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) IN CONNECTION WITH JAL JEEVAN MISSION (JJM) UNDER MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR UNDER ALIPORE | SM/18378 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000598/2023-2024 | 233/AD | 11/01/2024 | 11/01/2024 | Resource Division | 13 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-I, MATHURAPUR-I BLOCK FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) IN CONNECTION WITH JAL JEEVAN MISSION (JJM) UNDER MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR UNDER ALIPORE | SM/18378 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000844/2023-2024 | 707/AD | 31/01/2024 | 31/01/2024 | Resource Division | 137.95 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-I, MATHURAPUR-I BLOCK FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) IN CONNECTION WITH JAL JEEVAN MISSION (JJM) UNDER MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR UNDER ALIPORE | SM/18378 | Augmentation | Construction of 1500 cum capacity 20 M. staging height R.C.C. Over Head Water Reservoir, Providing FHTC including distribution system and other allied works at Zone- I of Mathurapur -I Block for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division,Junior Engineer-1, South 24 WS Circle. | ORD/000576/2023-2024 | 2262/AD | 14/08/2023 | 05/04/2025 | M/S. S.S. ENTERPRISE | 1185.63 | 206.21 | 17.39 | 10
7 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-I, MATHURAPUR-I BLOCK FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) IN CONNECTION WITH JAL JEEVAN MISSION (JJM) UNDER MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR UNDER ALIPORE | SM/18378 | Augmentation | Supplying, fabrication & insertion of 600 mm dia. (ID) 10mm thick MS casing pipe line 75 mtr. in length by HORIZONTAL DIRECTION DRILLING (HDD) technique underneath the Railway Track in between Node Point No. 442 to 443 of LDS under Zone ¿ I, Mathurapur ¿ I Block. The said location is in between Mathurapur and Madhabpur railway Station (Between mast no. 56/4, 56/6 and 56/5, 56/7 of Baruipur ¿ Lakshikantapur Section of Eastern Railway and comes with Gunjipur mouza as per permission of Railway Authority, for laying of 355.6 (OD) mm dia., 8 mm thick MS Water Supply Pipe 90 mtr. in length through the casing pipe for Augmentation of Laying Distribution System to extend the benefit of 100% households in Zone-I at Mathurapur ¿ I Block within Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District- South 24 Parganas under Alipore Division, PHE Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division,Junior Engineer-1, South 24 WS Circle. | ORD/002290/2023-2024 | 1026/AD | 19/02/2024 | 15/12/2024 | TELETONE INDIA PVT. LTD. | 60.47 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-I, MATHURAPUR-I BLOCK FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) IN CONNECTION WITH JAL JEEVAN MISSION (JJM) UNDER MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR UNDER ALIPORE | SM/18378 | Augmentation | Restoration of road in connection with piped water supply at Zone-I Mathurapur-I Block in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. (SM/10218 & SM/18378) | Assistant Engineer, Raidighi sub division | Junior Engineer-1, South 24 WS Circle. | ORD/000444/2024-2025 | 3325/AD | 12/08/2024 | 09/05/2025 | M/S B. ENTERPRISE | 119.73 | 0 | 0 | 95
9 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-I, MATHURAPUR-I BLOCK FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) IN CONNECTION WITH JAL JEEVAN MISSION (JJM) UNDER MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR UNDER ALIPORE | SM/18378 | Augmentation | Hiring of Diesel Maxi Cab for inspection and monitoring of JJM works on temporary basis under Raidighi Sub-Division P.H.E. Dte. [For 01/07/2024 to 31/08/2024 (Two) Months] | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/002723/2024-2025 | 613/RSD | 29/06/2024 | 29/08/2024 | SANKAR HALDER | 0.8 | 0.79 | 98.16 | 0
10 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-I, MATHURAPUR-I BLOCK FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) IN CONNECTION WITH JAL JEEVAN MISSION (JJM) UNDER MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR UNDER ALIPORE | SM/18378 | Augmentation | Hiring of Diesel Maxi Cab for inspection and monitoring of JJM works on temporary basis under Raidighi Sub-Division P.H.E. Dte. [For 01/05/2024 to 30/06/2024 (Two) Months] | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/002722/2024-2025 | 141/RSD | 29/04/2024 | 29/06/2024 | SANKAR HALDER | 0.8 | 0.76 | 95.42 | 0
11 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-I, MATHURAPUR-I BLOCK FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) IN CONNECTION WITH JAL JEEVAN MISSION (JJM) UNDER MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR UNDER ALIPORE | SM/18378 | Augmentation | Hiring of Diesel Maxi Cab for inspection and monitoring of JJM works on temporary basis under Raidighi Sub-Division P.H.E. Dte. [For 01/09/2024 to 31/10/2024 (Two) Months] | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/002724/2024-2025 | 689C/RSD | 29/08/2024 | 29/10/2024 | SANKAR HALDER | 0.8 | 0.75 | 93.47 | 0
12 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-I, MATHURAPUR-I BLOCK FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) IN CONNECTION WITH JAL JEEVAN MISSION (JJM) UNDER MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR UNDER ALIPORE | SM/18378 | Augmentation | Soil-Investigation work for the proposed 1500 Cum. Capacity Over Head Reservoir for Zone I, Mathurapur - I Block in connection with Jal Jeevan Mission (JJM) under Maga surface water based W/S Scheme for Falta - Mathurapur Dist. South 24 Parganas under Raidighi Sub-Division of Alipore Division PHE Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer-1, South 24 WS Circle. | ORD/000133/2025-2026 | 179/RSD | 05/06/2025 | 20/06/2025 | BOSE ENGINEERS | 0.96 | 0 | 0 | 100
Total | [13 empty] | 1672.01 | 335.11 | 20.04