## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS UNDER ZONE-II, MATHURAPUR-II BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS I/C/W JJM UNDER MEGA SURFACE WATER BASED W/S/S FOR FALTA-MATHURAPUR UNDER ALIPORE DIVISION, PHE DTE. | SM/18379 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000246/2023-2024 | 3103/AD | 28/09/2023 | 28/09/2023 | Resource Division | 43.57 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS UNDER ZONE-II, MATHURAPUR-II BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS I/C/W JJM UNDER MEGA SURFACE WATER BASED W/S/S FOR FALTA-MATHURAPUR UNDER ALIPORE DIVISION, PHE DTE. | SM/18379 | Augmentation | Construction of 900 M3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir, Providing FHTC including distribution system, boundary wall and other allied works at Zone- II of Mathurapur -II Block for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division,Junior Engineer-1, South 24 WS Circle. | ORD/000480/2023-2024 | 3670/AD | 01/11/2023 | 19/04/2026 | M/S GHOSH & CO. | 1045.49 | 268.64 | 25.7 | 28
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS UNDER ZONE-II, MATHURAPUR-II BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS I/C/W JJM UNDER MEGA SURFACE WATER BASED W/S/S FOR FALTA-MATHURAPUR UNDER ALIPORE DIVISION, PHE DTE. | SM/18379 | Augmentation | Preparation of Design (Pile with Pile Cap), Drawing for foundation of 900 m3 capacity Over Head Reservoir as per latest requisite I.S. Codes at Zone-II, Mathurapur- II Block under JJM as per direction and satisfaction of the Engineer In-Charge under Raidighi Sub-Division of Alipore Division PHE Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/001712/2023-2024 | 421/RSD | 02/01/2024 | 01/02/2024 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0.49 | 100 | 100
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS UNDER ZONE-II, MATHURAPUR-II BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS I/C/W JJM UNDER MEGA SURFACE WATER BASED W/S/S FOR FALTA-MATHURAPUR UNDER ALIPORE DIVISION, PHE DTE. | SM/18379 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000657/2023-2024 | 261/AD | 15/01/2024 | 15/01/2024 | Resource Division | 8.95 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS UNDER ZONE-II, MATHURAPUR-II BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS I/C/W JJM UNDER MEGA SURFACE WATER BASED W/S/S FOR FALTA-MATHURAPUR UNDER ALIPORE DIVISION, PHE DTE. | SM/18379 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000007/2024-2025 | 5162/AD | 12/12/2024 | 12/12/2024 | Resource Division | 30.8 | 0 | 0 | 0
Total | [13 empty] | 1129.29 | 269.13 | 23.83