## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS UNDER ZONE-IV, MATHURAPUR-II BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS IN CONNECTION WITH JAL JEEVAN MISSION UNDER MEGA SURFACE BASED WATER SUPPLY CSHEME FOR FALTA MATHURAPUR UNDER A | SM/18380 | Augmentation | Contruction of 1250 cum capacity 20 M. staging height R.C.C. Over Head Water Reservoir, Providing FHTC including distribution system and other allied works at Zone- IV of Mathurapur -II Block for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000482/2023-2024 | 1995/AD | 04/08/2023 | 30/05/2024 | SPA ENTERPRISE | 818.91 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS UNDER ZONE-IV, MATHURAPUR-II BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS IN CONNECTION WITH JAL JEEVAN MISSION UNDER MEGA SURFACE BASED WATER SUPPLY CSHEME FOR FALTA MATHURAPUR UNDER A | SM/18380 | Augmentation | Construction of boundary wall at Zone - IV, Mathurapur - II Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. (SM/09401 and SM/18380) | Assistant Engineer, Raidighi sub division | Junior Engineer-1, South 24 WS Circle. | ORD/001303/2024-2025 | 5377/AD | 23/12/2024 | 22/01/2025 | BAPAN HALDAR | 6.52 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS UNDER ZONE-IV, MATHURAPUR-II BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS IN CONNECTION WITH JAL JEEVAN MISSION UNDER MEGA SURFACE BASED WATER SUPPLY CSHEME FOR FALTA MATHURAPUR UNDER A | SM/18380 | Augmentation | Laying distribution system of piped water supply at Zone- IV of Mathurapur - II Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer-1, South 24 WS Circle. | ORD/001041/2024-2025 | 4959/AD | 04/12/2024 | 02/02/2025 | S.M. ENTERPRISE | 40.33 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS UNDER ZONE-IV, MATHURAPUR-II BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS IN CONNECTION WITH JAL JEEVAN MISSION UNDER MEGA SURFACE BASED WATER SUPPLY CSHEME FOR FALTA MATHURAPUR UNDER A | SM/18380 | Augmentation | Preparation of Design (Pile with Pile Cap), Drawing for foundation of 1250 m3 capacity Over Head Reservoir as per latest requisite I.S. Codes at Zone - IV, Mathurapur - II Block under JJM as per direction and satisfaction of the Engineer In-Charge under Raidighi Sub-Division of Alipore Division PHE Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer-1, South 24 WS Circle. | ORD/000276/2024-2025 | 593/RSD | 10/06/2024 | 10/07/2024 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 0 | 90
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS UNDER ZONE-IV, MATHURAPUR-II BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS IN CONNECTION WITH JAL JEEVAN MISSION UNDER MEGA SURFACE BASED WATER SUPPLY CSHEME FOR FALTA MATHURAPUR UNDER A | SM/18380 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000663/2023-2024 | 267/AD | 15/01/2024 | 15/01/2024 | Resource Division | 11.41 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS UNDER ZONE-IV, MATHURAPUR-II BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS IN CONNECTION WITH JAL JEEVAN MISSION UNDER MEGA SURFACE BASED WATER SUPPLY CSHEME FOR FALTA MATHURAPUR UNDER A | SM/18380 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000845/2023-2024 | 706/AD | 31/01/2024 | 31/01/2024 | Resource Division | 264.14 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS UNDER ZONE-IV, MATHURAPUR-II BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS IN CONNECTION WITH JAL JEEVAN MISSION UNDER MEGA SURFACE BASED WATER SUPPLY CSHEME FOR FALTA MATHURAPUR UNDER A | SM/18380 | Augmentation | Laying distribution system of piped water supply at Zone-IV of Mathurapur-II Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. (SM/09401 & SM/18380) | Assistant Engineer, Raidighi sub division | Junior Engineer-1, South 24 WS Circle. | ORD/000790/2024-2025 | 4489/AD | 11/11/2024 | 11/03/2025 | NITYANANDA MONDAL | 115.08 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS UNDER ZONE-IV, MATHURAPUR-II BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS IN CONNECTION WITH JAL JEEVAN MISSION UNDER MEGA SURFACE BASED WATER SUPPLY CSHEME FOR FALTA MATHURAPUR UNDER A | SM/18380 | Augmentation | Laying of additional D.I. (K7) pipes in connection with revised design of laying distribution alongwith supply, delivery and fitting & fixing at site of different dia specials at Zone - IV (Gilarchat PWSS) Mathurapur - II Block in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer-1, South 24 WS Circle.,Junior Engineer1, Raidghi Sub Division | ORD/000326/2024-2025 | 2729/AD | 25/06/2024 | 20/06/2025 | NITYANANDA MONDAL | 149.16 | 0 | 0 | 10
9 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS UNDER ZONE-IV, MATHURAPUR-II BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS IN CONNECTION WITH JAL JEEVAN MISSION UNDER MEGA SURFACE BASED WATER SUPPLY CSHEME FOR FALTA MATHURAPUR UNDER A | SM/18380 | Augmentation | Interconnection with OHR, Rising main and distribution system for different Zone ( Zone-I, II, III, IV, V), Mathurapur-II Block in connection with Jal Jeevan Mission (JJM) under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer-1, South 24 WS Circle. | ORD/000043/2025-2026 | 2071/AD | 30/04/2025 | 29/06/2025 | M/S B. ENTERPRISE | 27.24 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS UNDER ZONE-IV, MATHURAPUR-II BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS IN CONNECTION WITH JAL JEEVAN MISSION UNDER MEGA SURFACE BASED WATER SUPPLY CSHEME FOR FALTA MATHURAPUR UNDER A | SM/18380 | Augmentation | Preparation of Design (Pile with Pile Cap), Drawing for foundation of 1250 m3 capacity Over Head Reservoir as per latest requisite I.S. Codes at Zone IV, Mathurapur - II Block in connection with Jal Jeevan Mission (JJM) under Maga surface water based W/S Scheme for Falta - Mathurapur Dist. South 24 Parganas under Raidighi Sub-Division of Alipore Division PHE Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer-1, South 24 WS Circle. | ORD/000491/2024-2025 | 629/RSD | 11/07/2024 | 26/07/2024 | SPA ENTERPRISE | 0.48 | 0 | 0 | 100
Total | [13 empty] | 1433.77 | 0 | 0