## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED CHATRAKHALI (ZONE-I, II & III) PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, PHE DTE., BLOCK : BASANTI, DISTRICT : SOUTH 24 PARGANAS | SM/18381 | Augmentation | Sinking of 04 (four) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Augmentation of Chatrakhali (Zone-I) W/S Scheme, Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000387/2023-2024 | 1576/AD | 17/07/2023 | 15/10/2023 | ANWAR SHAIKH | 77.59 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED CHATRAKHALI (ZONE-I, II & III) PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, PHE DTE., BLOCK : BASANTI, DISTRICT : SOUTH 24 PARGANAS | SM/18381 | Augmentation | onstruction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Chatrakhali W/S Scheme (Zone-III) , Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-II] (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000474/2023-2024 | 1786/AD | 26/07/2023 | 09/09/2023 | SABITA INFRASTRUCTURE | 7.11 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED CHATRAKHALI (ZONE-I, II & III) PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, PHE DTE., BLOCK : BASANTI, DISTRICT : SOUTH 24 PARGANAS | SM/18381 | Augmentation | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Chatrakhali W/S Scheme (Zone-III) , Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-III] (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000475/2023-2024 | 1787/AD | 26/07/2023 | 09/09/2023 | JAGANNATH CONSTRUCTION | 7.11 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED CHATRAKHALI (ZONE-I, II & III) PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, PHE DTE., BLOCK : BASANTI, DISTRICT : SOUTH 24 PARGANAS | SM/18381 | Augmentation | Inter connection and rising main with supply of specials of Augmentation of Chatrakhali (Zone-III) W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000391/2023-2024 | 1777/AD | 26/07/2023 | 10/08/2023 | M/S BABUSONA ENTERPRISE | 13.7 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED CHATRAKHALI (ZONE-I, II & III) PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, PHE DTE., BLOCK : BASANTI, DISTRICT : SOUTH 24 PARGANAS | SM/18381 | Augmentation | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Chatrakhali W/S Scheme (Zone-I), Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-I] (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000469/2023-2024 | 1781/AD | 26/07/2023 | 09/09/2023 | M/S. TAPAS MONDAL | 7.37 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED CHATRAKHALI (ZONE-I, II & III) PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, PHE DTE., BLOCK : BASANTI, DISTRICT : SOUTH 24 PARGANAS | SM/18381 | Augmentation | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Chatrakhali W/S Scheme (Zone-I) , Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-II] (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000470/2023-2024 | 1782/AD | 26/07/2023 | 09/09/2023 | SUJIT KUMAR GHOSH | 7.11 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED CHATRAKHALI (ZONE-I, II & III) PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, PHE DTE., BLOCK : BASANTI, DISTRICT : SOUTH 24 PARGANAS | SM/18381 | Augmentation | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Chatrakhali W/S Scheme (Zone-I) , Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-IV] (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000472/2023-2024 | 1784/AD | 26/07/2023 | 09/09/2023 | SUJIT KUMAR GHOSH | 7.11 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED CHATRAKHALI (ZONE-I, II & III) PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, PHE DTE., BLOCK : BASANTI, DISTRICT : SOUTH 24 PARGANAS | SM/18381 | Augmentation | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Chatrakhali W/S Scheme (Zone-II) , Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000473/2023-2024 | 1785/AD | 26/07/2023 | 09/09/2023 | SUSHANTA MANDAL | 7.11 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED CHATRAKHALI (ZONE-I, II & III) PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, PHE DTE., BLOCK : BASANTI, DISTRICT : SOUTH 24 PARGANAS | SM/18381 | Augmentation | Sinking of 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Augmentation of Chatrakhali (Zone-II) W/S Scheme, Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000388/2023-2024 | 1577/AD | 17/07/2023 | 16/08/2023 | MAA SARADA ENTERPRISE | 19.57 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED CHATRAKHALI (ZONE-I, II & III) PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, PHE DTE., BLOCK : BASANTI, DISTRICT : SOUTH 24 PARGANAS | SM/18381 | Augmentation | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Chatrakhali W/S Scheme (Zone-I) , Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-III] (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000471/2023-2024 | 1783/AD | 26/07/2023 | 09/09/2023 | M/S. TAPAS MONDAL | 7.11 | 0 | 0 | 0
11 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED CHATRAKHALI (ZONE-I, II & III) PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, PHE DTE., BLOCK : BASANTI, DISTRICT : SOUTH 24 PARGANAS | SM/18381 | Augmentation | Inter connection and rising main with supply of specials of Augmentation of Chatrakhali (Zone-I) W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000374/2023-2024 | 1573/AD | 17/07/2023 | 01/08/2023 | BHOLANATH CONSTRUCTION | 13.56 | 0 | 0 | 0
12 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED CHATRAKHALI (ZONE-I, II & III) PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, PHE DTE., BLOCK : BASANTI, DISTRICT : SOUTH 24 PARGANAS | SM/18381 | Augmentation | Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water based Augmentation Piped Water Supply Scheme for the CHATRAKHALI (ZONE-III), Block-Basanti under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000354/2023-2024 | 1663/AD | 20/07/2023 | 18/10/2023 | RIVER BENZ CONSTRUCTION | 249.56 | 0 | 0 | 0
13 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED CHATRAKHALI (ZONE-I, II & III) PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, PHE DTE., BLOCK : BASANTI, DISTRICT : SOUTH 24 PARGANAS | SM/18381 | Augmentation | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Chatrakhali W/S Scheme (Zone-III), Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-I] | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/001147/2023-2024 | 3692/AD | 02/11/2023 | 17/12/2023 | I.B. ENTERPRISE | 7.36 | 0 | 0 | 0
14 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED CHATRAKHALI (ZONE-I, II & III) PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, PHE DTE., BLOCK : BASANTI, DISTRICT : SOUTH 24 PARGANAS | SM/18381 | Augmentation | Sinking of 1 Nos. 200mm x 100mm dia. 420 mtr. deep Tubewell (Replacement) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Chatrakhali Water Supply Scheme Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division |  | ORD/000934/2020-2021 | 4862/AD | 28/01/2021 | 14/03/2021 | AQUATECH ENGINEERS | 16.7 | 15.22 | 91.17 | 99
15 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED CHATRAKHALI (ZONE-I, II & III) PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, PHE DTE., BLOCK : BASANTI, DISTRICT : SOUTH 24 PARGANAS | SM/18381 | Augmentation | Inter connection of Tubewell-1 & Tubewell-2 and laying of pipe line from Chatrakhali PWD Road to Spandan Sishu Academy at Chatrakhali W/S Scheme, Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division |  | ORD/000277/2022-2023 | 270/CSD | 19/05/2022 | 18/06/2022 | M/S. MIHIR KUMAR NASKAR | 1.43 | 0.7 | 48.83 | 98
16 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED CHATRAKHALI (ZONE-I, II & III) PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, PHE DTE., BLOCK : BASANTI, DISTRICT : SOUTH 24 PARGANAS | SM/18381 | Augmentation | Conducting route survey, design distribution network and preparation & submission of DPR for Chatrakhali (Zone-I, II & III) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Basanti Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000614/2023-2024 | 1832/AD | 27/07/2023 | 10/09/2023 | INDRANIL DUTTA & ASSOCIATES | 15.03 | 15.03 | 100 | 98
17 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED CHATRAKHALI (ZONE-I, II & III) PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, PHE DTE., BLOCK : BASANTI, DISTRICT : SOUTH 24 PARGANAS | SM/18381 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000032/2023-2024 | 237/AD | 24/04/2023 | 24/04/2023 | Resource Division | 157.26 | 0 | 0 | 0
18 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED CHATRAKHALI (ZONE-I, II & III) PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, PHE DTE., BLOCK : BASANTI, DISTRICT : SOUTH 24 PARGANAS | SM/18381 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000387/2023-2024 | 328/AD | 19/01/2024 | 19/01/2024 | Resource Division | 41.73 | 0 | 0 | 0
19 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED CHATRAKHALI (ZONE-I, II & III) PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, PHE DTE., BLOCK : BASANTI, DISTRICT : SOUTH 24 PARGANAS | SM/18381 | Augmentation | Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water based Augmentation Piped Water Supply Scheme for the CHATRAKHALI (ZONE-II), Block-Basanti under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000371/2023-2024 | 1572/AD | 17/07/2023 | 19/07/2025 | SUPRITI ENTERPRISE | 308.46 | 41.72 | 13.53 | 22
20 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED CHATRAKHALI (ZONE-I, II & III) PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, PHE DTE., BLOCK : BASANTI, DISTRICT : SOUTH 24 PARGANAS | SM/18381 | Augmentation | Sinking of 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of the Augmentation Ground Water Based at Chatrakhali (Zone-I, II & III) W/S Scheme, Block - Canning-I under Canning Sub Division of Alipore Division, PHE Dte. (Zone-I, TW No. 1 replacement Tubewell) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/002379/2023-2024 | 1203/AD | 29/02/2024 | 03/04/2025 | BHATTACHARJEE & CO. | 19.68 | 0 | 0 | 99
21 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED CHATRAKHALI (ZONE-I, II & III) PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, PHE DTE., BLOCK : BASANTI, DISTRICT : SOUTH 24 PARGANAS | SM/18381 | Augmentation | Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water basedAugmentation Piped Water Supply Scheme for the CHATRAKHALI (ZONE-I), Block-Basanti under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000755/2024-2025 | 4439/AD | 06/11/2024 | 03/08/2025 | SUPRITI ENTERPRISE | 309.22 | 0 | 0 | 30
22 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED CHATRAKHALI (ZONE-I, II & III) PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, PHE DTE., BLOCK : BASANTI, DISTRICT : SOUTH 24 PARGANAS | SM/18381 | Augmentation | Construction of 23 Nos. different capacity R.C.C OHR (based on Departmental Design & Drawing ) with 20 mtr. staging height including Geo-Technical investigation, foundation, pipeline connection and cost of pipes , specials etc. for augmentation of different piped water supply scheme of Canning-I, Canning-II & Basanti Block under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD,Junior Engineer,1 CSD | ORD/002461/2023-2024 | 1512/AD | 13/03/2024 | 03/11/2025 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LTD | 2624.49 | 0 | 0 | 30
23 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED CHATRAKHALI (ZONE-I, II & III) PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, PHE DTE., BLOCK : BASANTI, DISTRICT : SOUTH 24 PARGANAS | SM/18381 | Augmentation | Repairing & renovation of Pump House no. - 2 of Chatrakhali, Zone-II W/S Scheme Block - Basanti under Canning Sub- Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000277/2025-2026 | 682/CSD | 26/05/2025 | 25/06/2025 | SUDIP DEBNATH | 2.4 | 0 | 0 | 0
24 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED CHATRAKHALI (ZONE-I, II & III) PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, PHE DTE., BLOCK : BASANTI, DISTRICT : SOUTH 24 PARGANAS | SM/18381 | Augmentation | Supply and delivery of UPVC pipe (CD) for Sinking of 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Augmentation Ground Water Based at Chatrakhali (Zone - I, II & III) W/S Scheme, Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. (Zone - I,Tubewell No. - 1, Replacement Tubewell) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/003677/2024-2025 | 258/CSD | 04/03/2025 | 06/03/2025 | BHATTACHARJEE & CO. | 1.58 | 0 | 0 | 95
Total | [13 empty] | 3929.34 | 72.68 | 1.85