## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF CHAR BAIDYARABAD PIPED WATER SUPPLY SCHEME, BLOCK - BASANTI UNDER CANNING SUB - DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18391 | Augmentation | Sinking of 250mm x 150mm dia. 360 mtr. deep Tubewell (New) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter for retrofitting of Char Baidyarabad W/S Scheme, Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000855/2022-2023 | 6994/AD | 19/11/2022 | 19/12/2022 | PAPPU ENTERPRISE | 19.48 | 0 | 0 | 95
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF CHAR BAIDYARABAD PIPED WATER SUPPLY SCHEME, BLOCK - BASANTI UNDER CANNING SUB - DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18391 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000033/2023-2024 | 238/AD | 24/04/2023 | 24/04/2023 | Resource Division | 73.69 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF CHAR BAIDYARABAD PIPED WATER SUPPLY SCHEME, BLOCK - BASANTI UNDER CANNING SUB - DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18391 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/01990/2023-2024 | BP-2023-24-240 | 11/09/2023 | 11/09/2023 | WBSEDCL | 2.51 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF CHAR BAIDYARABAD PIPED WATER SUPPLY SCHEME, BLOCK - BASANTI UNDER CANNING SUB - DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18391 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no. 3 of Char Baidyarabad W/S Scheme under SMD, P.H.E. Dte. (Block-Basanti )(SM/18391) | Assistant Engineer | Junior Engineer | ORD/002854/2023-2024 | 346/SMSD | 19/03/2024 | 03/04/2024 | D.K.ELECTRIC | 0.98 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF CHAR BAIDYARABAD PIPED WATER SUPPLY SCHEME, BLOCK - BASANTI UNDER CANNING SUB - DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18391 | Augmentation | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site for Retrofitting of Char Baidyarabad W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000489/2023-2024 | 1789/AD | 26/07/2023 | 25/08/2023 | NATURAL RESOURCES CONSORTIUM | 7.17 | 0 | 0 | 98
6 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF CHAR BAIDYARABAD PIPED WATER SUPPLY SCHEME, BLOCK - BASANTI UNDER CANNING SUB - DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18391 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 of Char Baidyarabad water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Basanti] | Assistant Engineer | Junior Engineer | ORD/001548/2023-2024 | 4765/SMD | 06/12/2023 | 06/03/2024 | D.K.ELECTRIC | 11.43 | 0 | 0 | 100
7 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF CHAR BAIDYARABAD PIPED WATER SUPPLY SCHEME, BLOCK - BASANTI UNDER CANNING SUB - DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18391 | Augmentation | Construction of OHR (500 cum.), Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water Based Augmentation Piped Water Supply Scheme for the Char Baidyarabad, Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000486/2023-2024 | 1999/AD | 04/08/2023 | 20/01/2026 | SAMSUL ENTERPRISE | 651.91 | 0 | 0 | 71
8 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF CHAR BAIDYARABAD PIPED WATER SUPPLY SCHEME, BLOCK - BASANTI UNDER CANNING SUB - DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18391 | Augmentation | Laying of additional pipe line to connect the uncovered habitation at Augmentation of Char Baidyarabad, Block - Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. [SM/18391] | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD | ORD/002489/2024-2025 | 771/AD | 25/02/2025 | 26/04/2025 | M/S. UMA CONSTRUCTION | 128.86 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF CHAR BAIDYARABAD PIPED WATER SUPPLY SCHEME, BLOCK - BASANTI UNDER CANNING SUB - DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18391 | Augmentation | Inter connection and rising main with supply of specials of Augmentation of Char Baidyarabad W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000229/2023-2024 | 1386/AD | 12/07/2023 | 01/12/2024 | R CONSTRUCTION | 35.33 | 0 | 0 | 86
10 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF CHAR BAIDYARABAD PIPED WATER SUPPLY SCHEME, BLOCK - BASANTI UNDER CANNING SUB - DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18391 | Augmentation | Hiring of 1 (One) No. Diesel Car / Luxury Taxi for supervision of different works Under JJM at Canning Sub-Division of Alipore Division, PHE Dte. for 06 (six) months from the issuance of work order. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/002429/2023-2024 | 1553/CSD | 19/02/2024 | 19/08/2024 | SWAPAN KUMAR MANDAL | 2.4 | 0 | 0 | 70
Total | [13 empty] | 933.76 | 0 | 0