## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS | Namkhana | S24 Pgns Mechanical | BALIARA PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18392 | New | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 of Baliara water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Namkhana] | Assistant Engineer -I | Junior Engineer | ORD/000115/2023-2024 | 1022/SMD | 12/04/2023 | 11/07/2023 | ANJAN ENTERPRISE | 25.43 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | BALIARA PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18392 | New | Material Requisition To Resource Division |  |  | RTOR000476/2023-2024 | 4781/AD | 19/12/2023 | 19/12/2023 | Resource Division | 15.04 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | BALIARA PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18392 | New | Laying distribution system, Providing Functional Household Tap Connection (FHTC) to all households for Baliara Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-C) [No. of FHTC = 500] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000344/2023-2024 | 1604/AD | 18/07/2023 | 16/10/2023 | PIJUSH KANTI TRIPATHI | 110.16 | 89.55 | 81.29 | 50
4 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | BALIARA PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18392 | New | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections etc at Baliara PWSS, Block-Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (Part-A) (SM/18392) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000363/2024-2025 | 2912/AD | 10/07/2024 | 08/09/2024 | AVIK ENTERPRISE | 115.68 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | BALIARA PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18392 | New | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 1st and 2nd Tubewell Site of Baliara W/S scheme, Block : Namkhana under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/18392) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000416/2024-2025 | 3067/AD | 25/07/2024 | 08/09/2024 | AVIK ENTERPRISE | 44.14 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | BALIARA PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18392 | New | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Baliara W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000117/2024-2025 | 2394/AD | 07/06/2024 | 22/07/2024 | DEV AND COMPANY | 45.39 | 0 | 0 | 30
7 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | BALIARA PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18392 | New | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections etc at Baliara PWSS, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/18392) (Part-B) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000156/2024-2025 | 2507/AD | 15/06/2024 | 14/08/2024 | PIJUSH KANTI TRIPATHI | 53.71 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | BALIARA PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18392 | New | Making and fixing of permanent display board at headwork site of Kusumtala, Bagdanga, Baliara PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/002138/2023-2024 | 939/KSD | 19/12/2023 | 24/12/2023 | ANANTA KUMAR GIRI | 0.54 | 0 | 0 | 100
9 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | BALIARA PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18392 | New | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Baliara PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/002602/2023-2024 | 227/KSD | 24/01/2024 | 29/01/2024 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0.49 | 100 | 100
10 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | BALIARA PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18392 | New | Material Requisition To Resource Division |  |  | RTOR000558/2023-2024 | 46/AD | 03/01/2024 | 03/01/2024 | Resource Division | 16.9 | 0 | 0 | 0
11 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | BALIARA PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18392 | New | Material Requisition To Resource Division |  |  | RTOR000980/2023-2024 | 1773/AD | 27/03/2024 | 27/03/2024 | Resource Division | 1.17 | 0 | 0 | 0
12 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | BALIARA PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18392 | New | Construction of 300 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design & drawing of foundation after soil investigation along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M of Laying distribution, Rising Main & FHTC for 1 year after completion of FHTC works for Baliara Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000366/2023-2024 | 1567/AD | 17/07/2023 | 01/11/2025 | AVIK ENTERPRISE | 409.79 | 141.4 | 34.51 | 60
13 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | BALIARA PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18392 | New | Laying distribution system, Functional Household Tap Connection (FHTC) to all households and Construction 02 nos. Pump House (5.40m. x 3.60m.) for Baliara Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000580/2023-2024 | 2267/AD | 14/08/2023 | 01/06/2025 | TANMAY ROY CHOWDHURY | 64.8 | 42.41 | 65.45 | 50
Total | [13 empty] | 903.25 | 273.85 | 30.32