## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | PATIBANIA PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS UNDER ALIPORE DIVISION, PHE DTE. | SM/18395 | New | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Patibania Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-D) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000566/2023-2024 | 1806/AD | 26/07/2023 | 25/08/2023 | ABONTICA ENTERPRISE | 17.93 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | PATIBANIA PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS UNDER ALIPORE DIVISION, PHE DTE. | SM/18395 | New | Laying distribution system, Functional Household Tap Connection (FHTC) to all households and Construction 02 nos. Pump House (5.40m. x 3.60m) for Patibania Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000578/2023-2024 | 2265/AD | 14/08/2023 | 28/09/2023 | SUPRITI ENTERPRISE | 63.53 | 35.54 | 55.95 | 20
3 | SOUTH 24 PARGANAS | Namkhana | S24 Pgns Mechanical | PATIBANIA PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS UNDER ALIPORE DIVISION, PHE DTE. | SM/18395 | New | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, Zone-II of Patibania water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Namkhana] | Assistant Engineer -I | Junior Engineer | ORD/000744/2023-2024 | 2633/SMD | 09/08/2023 | 07/11/2023 | S.K. ENTERPRISE | 27.18 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | PATIBANIA PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS UNDER ALIPORE DIVISION, PHE DTE. | SM/18395 | New | Material Requisition To Resource Division |  |  | RTOR000130/2023-2024 | 666/AD | 17/05/2023 | 17/05/2023 | Resource Division | 15.23 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | PATIBANIA PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS UNDER ALIPORE DIVISION, PHE DTE. | SM/18395 | New | Material Requisition To Resource Division |  |  | RTOR000470/2023-2024 | 4777/AD | 19/12/2023 | 19/12/2023 | Resource Division | 29.79 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | PATIBANIA PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS UNDER ALIPORE DIVISION, PHE DTE. | SM/18395 | New | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 3rd Tubewell Site of Patibania W/S scheme, Block - Namkhana under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/18395) (2nd Call) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000510/2024-2025 | 4570/AD | 14/11/2024 | 14/12/2024 | AZAD RAHAMAN LASKAR | 8.9 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | PATIBANIA PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS UNDER ALIPORE DIVISION, PHE DTE. | SM/18395 | New | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Patibania W/S scheme, Block : Namkhana under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/18395) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000220/2024-2025 | 2603/AD | 19/06/2024 | 19/07/2024 | KRISHNA CONSTRUCTION | 9.56 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | PATIBANIA PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS UNDER ALIPORE DIVISION, PHE DTE. | SM/18395 | New | Construction of 1 nos. Pump House of size 5.40 mtr. x 3.60 mtr. at 4th tubewell Site for Patibania Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/18395) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000227/2024-2025 | 2557/AD | 18/06/2024 | 02/08/2024 | M/S MALI ENTERPRISE | 5.62 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | PATIBANIA PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS UNDER ALIPORE DIVISION, PHE DTE. | SM/18395 | New | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connection etc. for Patibania W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. [Part-I] (SM/18395) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000340/2024-2025 | 2772/AD | 28/06/2024 | 27/08/2024 | PROJECT INDIA | 99.02 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | PATIBANIA PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS UNDER ALIPORE DIVISION, PHE DTE. | SM/18395 | New | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Patibania W/S scheme, Block : Namkhana under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/18395) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000219/2024-2025 | 2602/AD | 19/06/2024 | 03/08/2024 | M/S MALI ENTERPRISE | 28.95 | 0 | 0 | 0
11 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | PATIBANIA PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS UNDER ALIPORE DIVISION, PHE DTE. | SM/18395 | New | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 4th Tubewell Site of Patibania W/S scheme, Block - Namkhana under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/18395) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000226/2024-2025 | 2525/AD | 18/06/2024 | 18/07/2024 | RIYANA ENTERPRISE | 9.66 | 0 | 0 | 0
12 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | PATIBANIA PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS UNDER ALIPORE DIVISION, PHE DTE. | SM/18395 | New | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Patibania Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000572/2023-2024 | 1809/AD | 26/07/2023 | 09/09/2023 | AQUATECH ENGINEER | 36.71 | 33.21 | 90.46 | 80
13 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | PATIBANIA PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS UNDER ALIPORE DIVISION, PHE DTE. | SM/18395 | New | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Patabania Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-C) [No. of FHTC =950] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000716/2023-2024 | 2661/AD | 04/09/2023 | 02/01/2024 | PROJECT INDIA | 161.87 | 161.52 | 99.78 | 40
14 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | PATIBANIA PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS UNDER ALIPORE DIVISION, PHE DTE. | SM/18395 | New | Making and fixing of permanent display board at headwork site of Nadabhanga, Patibania, Dakshin Durgapur, Rajnagar, Budhakhali Zone - I (Part - I & II) PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/002128/2023-2024 | 935/KSD | 19/12/2023 | 24/12/2023 | M/S B. ENTERPRISE | 0.95 | 0.16 | 16.55 | 90
15 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | PATIBANIA PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS UNDER ALIPORE DIVISION, PHE DTE. | SM/18395 | New | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Patibania PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/002625/2023-2024 | 882/KSD | 15/12/2023 | 25/12/2023 | CONSTEEL CONSULTANCY & SERVICES | 0.48 | 0.48 | 100 | 100
16 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | PATIBANIA PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS UNDER ALIPORE DIVISION, PHE DTE. | SM/18395 | New | Material Requisition To Resource Division |  |  | RTOR000841/2023-2024 | 634/AD | 30/01/2024 | 30/01/2024 | Resource Division | 7.87 | 0 | 0 | 0
17 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | PATIBANIA PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS UNDER ALIPORE DIVISION, PHE DTE. | SM/18395 | New | Material Requisition To Resource Division |  |  | RTOR000976/2023-2024 | 1769/AD | 27/03/2024 | 27/03/2024 | Resource Division | 28.97 | 0 | 0 | 0
18 | SOUTH 24 PARGANAS | Namkhana | S24 Pgns Mechanical | PATIBANIA PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS UNDER ALIPORE DIVISION, PHE DTE. | SM/18395 | New | Payment for New Service connection Patibunia Zone-2 PH-2 W/S Scheme Application No:- 1007183453 Reference ID: 106222544 |  |  | BILL/02230/2024-2025 | BP-2024-25-497 | 19/12/2024 | 19/12/2024 | WBSEDCL | 6.1 | 0 | 0 | 0
19 | SOUTH 24 PARGANAS | Namkhana | S24 Pgns Mechanical | PATIBANIA PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS UNDER ALIPORE DIVISION, PHE DTE. | SM/18395 | New | Payment for New Service connection Patibunia Zone-2, PH-1W/S Scheme Application No:- 1007183440 Reference ID: 106222543 |  |  | BILL/02233/2024-2025 | BP-2024-25-498 | 19/12/2024 | 19/12/2024 | WBSEDCL | 8.05 | 0 | 0 | 0
20 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | PATIBANIA PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS UNDER ALIPORE DIVISION, PHE DTE. | SM/18395 | New | Construction of 350 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design & drawing of pile foundation & pile cap after soil investigation along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M for 1 year after completion of FHTC works for Patibania Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000359/2023-2024 | 1558/AD | 17/07/2023 | 01/11/2025 | SYN DEVELOPERS PVT. LTD. | 437.8 | 136.75 | 31.24 | 15
21 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | PATIBANIA PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS UNDER ALIPORE DIVISION, PHE DTE. | SM/18395 | New | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Patibania W/S Scheme, Block - Namkhana under JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/18395) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000161/2024-2025 | 2512/AD | 15/06/2024 | 12/03/2025 | DEV AND COMPANY | 40.82 | 0 | 0 | 50
22 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | PATIBANIA PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS UNDER ALIPORE DIVISION, PHE DTE. | SM/18395 | New | Construction of 1 nos. Pump House of size 5.40 mtr. x 3.60 mtr. at 3rd tubewell Site for Patibania Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/18395) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000225/2024-2025 | 2556/AD | 18/06/2024 | 28/03/2025 | SUMAN ENTERPRISE | 5.63 | 0 | 0 | 90
Total | [13 empty] | 1050.61 | 367.66 | 34.99