## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM WITH ALLIED WORKS FOR PROVIDING FHTC TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS AT ZONE-II OF DIAMOND HARBOUR-I BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOUTH 24 PAR | SM/18399 | Augmentation | Construction of boundary wall at proposed OHR site at Mouza - Netra under Zone- II of Diamond Harbour-I Block for Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. (2nd call) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer | ORD/000130/2023-2024 | 1790/AD | 26/07/2023 | 25/08/2023 | MAYA CONSTRUCTION | 25.02 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM WITH ALLIED WORKS FOR PROVIDING FHTC TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS AT ZONE-II OF DIAMOND HARBOUR-I BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOUTH 24 PAR | SM/18399 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000231/2023-2024 | 2192/AD | 10/08/2023 | 10/08/2023 | Resource Division | 37.76 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM WITH ALLIED WORKS FOR PROVIDING FHTC TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS AT ZONE-II OF DIAMOND HARBOUR-I BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOUTH 24 PAR | SM/18399 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000666/2023-2024 | 419/AD | 22/01/2024 | 22/01/2024 | Resource Division | 315.41 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM WITH ALLIED WORKS FOR PROVIDING FHTC TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS AT ZONE-II OF DIAMOND HARBOUR-I BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOUTH 24 PAR | SM/18399 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000891/2023-2024 | 745/AD | 03/02/2024 | 03/02/2024 | Resource Division | 38.95 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM WITH ALLIED WORKS FOR PROVIDING FHTC TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS AT ZONE-II OF DIAMOND HARBOUR-I BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOUTH 24 PAR | SM/18399 | Augmentation | Payment against "Restoration of Hatuganj Basuldanga Road (MDR) 0Km-12.2Km), under Diamond Harbour Highway Division, PWD damaged caused due to laying of water pipe lines by PHED under Raidighi Sub Division, PHE Dte. in the district of South 24 Pgs" vide Memo no. 264(W)/618G, Dt. 19.02.2024 of SE, Southern highway Circle P.W.(Roads) Dte. & 9nos |  |  | BILL/01577/2024-2025 | BP-2024-25-891 | 19/11/2024 | 19/11/2024 | EXECUTIVE ENGNEER, DIAMOND HARBOUR DIVN, P.W.(ROADS) DTE. | 54.41 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM WITH ALLIED WORKS FOR PROVIDING FHTC TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS AT ZONE-II OF DIAMOND HARBOUR-I BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOUTH 24 PAR | SM/18399 | Augmentation | Augmentation of laying distribution system including construction of 900 cum capacity of OHR to extend the benefit of 100% household by Providing Functional Household Tap Connection (FHTC) from distribution system in Zone- II at Netra of Diamond Harbour- I block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. [No of FHTC=6323] . | Assistant Engineer, Diamond Harbour sub division,Assistant Engineer, Raidighi sub division | Junior Engineer,Junior Engineer 2 DHSD | ORD/000740/2023-2024 | 2908/AD | 20/09/2023 | 03/06/2025 | TARUN ENTERPRISE | 1223.41 | 179.67 | 14.69 | 55
7 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM WITH ALLIED WORKS FOR PROVIDING FHTC TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS AT ZONE-II OF DIAMOND HARBOUR-I BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOUTH 24 PAR | SM/18399 | Augmentation | Erection of 20 nos scheme information display board at different headwork site of falta,Diamond Harbour I ,Diamond Harbour II and Kulpi Block under Diamond Harbour Sub Division of Alipore Division PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/000065/2025-2026 | 35/DHSD | 08/04/2025 | 15/04/2025 | SADHURHAT CO OP. LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 3.75 | 0 | 0 | 100
8 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM WITH ALLIED WORKS FOR PROVIDING FHTC TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS AT ZONE-II OF DIAMOND HARBOUR-I BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOUTH 24 PAR | SM/18399 | Augmentation | Construction of pipe carrying structure with laying of different dia. M.S. distribution line for crossing of 10 nos. culvert with allied works at Lakshmipur village road, at Netra stations to Panchagram road and Netra stations to Usthi road under Augmentation scheme of Diamond Harbour-I Zone-II and Zone-VIII within Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur District - South-24 Parganas under Diamond Harbour Sub- Division of Alipore Division, PHE Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2 DHSD | ORD/000097/2025-2026 | 2526/AD | 30/05/2025 | 29/07/2025 | SRIJON ENTERPRISE | 93.95 | 0 | 0 | 100
Total | [13 empty] | 1792.67 | 179.67 | 10.02