## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-IX OF KULPI BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOUTH 24 | SM/18551 | Augmentation | Support service for detail surveying, cross checking of available LOP with making permission drawings for other department by using Survey Instruments like Remotly Piloted Aircraft System/ DGPS / Total Station etc. and detailed design of pipeline by using Watergems Software on the basis of the population density within the Zone-IX of Kulpi Block under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division |  | ORD/001022/2022-2023 | 295/DHSD | 15/09/2022 | 15/10/2022 | CHAYANIKA ENGINEERING CONSULTANCY | 3.59 | 3.18 | 88.57 | 98
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-IX OF KULPI BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOUTH 24 | SM/18551 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000364/2023-2024 | 3228/AD | 04/10/2023 | 04/10/2023 | Resource Division | 0.21 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-IX OF KULPI BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOUTH 24 | SM/18551 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000212/2023-2024 | 2021/AD | 05/08/2023 | 05/08/2023 | Resource Division | 25.17 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-IX OF KULPI BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOUTH 24 | SM/18551 | Augmentation | Preparation of design, drawing for fundation of different capacities for the proposed R.C.C. Over Head Reservoir at (Zone IX, OHR Size-450 Cum. Mouza - Karanjali ) of Kulpi Block and at Moukhali W/S Scheme (OHR Size-350 Cum., Mouza - Moukhali) of Budge Budge-I Block under "Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas" under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division |  | ORD/000365/2022-2023 | 198/DHSD | 27/07/2022 | 03/08/2022 | ASTER CONSULTANCY | 1 | 1 | 100 | 30
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-IX OF KULPI BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOUTH 24 | SM/18551 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000629/2023-2024 | 291/AD | 15/01/2024 | 15/01/2024 | Resource Division | 9.24 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-IX OF KULPI BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOUTH 24 | SM/18551 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000671/2023-2024 | 424/AD | 22/01/2024 | 22/01/2024 | Resource Division | 24.29 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-IX OF KULPI BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOUTH 24 | SM/18551 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000897/2023-2024 | 791/AD | 03/02/2024 | 03/02/2024 | Resource Division | 11.21 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-IX OF KULPI BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOUTH 24 | SM/18551 | Augmentation | Augmentation of laying distribution system including construction of 600 m3 capacity OHR to extend the benefit of 100% household by Providing Functional Household Tap Connection (FHTC) from distribution system in Zone-IX at Kulpi block within "Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer | ORD/000561/2023-2024 | 3736/AD | 03/11/2023 | 31/03/2026 | M/S GHOSH & CO. | 905.65 | 369.23 | 40.77 | 100
9 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-IX OF KULPI BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOUTH 24 | SM/18551 | Augmentation | Additional bored cast in situ R.C.C pile due to revised drawing for the construction of 600 m3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir within Zone-IX at Krishnachandrapur of Kulpi Block for the Mega Surface Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/000331/2024-2025 | 2748/AD | 26/06/2024 | 24/09/2024 | M/S GHOSH & CO. | 60.27 | 18.09 | 30.01 | 60
10 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-IX OF KULPI BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOUTH 24 | SM/18551 | Augmentation | Repairing of boundary wall at Pump House No-2 under Karanjali PWSS under Zone- IX of Kulpi Block for Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/001369/2024-2025 | 5498/AD | 27/12/2024 | 26/01/2025 | SANKAR HALDER | 5.36 | 0 | 0 | 100
11 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-IX OF KULPI BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOUTH 24 | SM/18551 | Augmentation | Construction of pipe carrying structure with laying of 219.10 mm dia. (OD) M.S. distribution line for crossing of Karanjali Canal at Karanjali bridge (Node point 249 to 253) for Providing distribution network under the Augmentation scheme of Kulpi Zone-IX within Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur District-South-24 Parganas under Diamond Harbour Sub- Division, of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/000069/2025-2026 | 2258/AD | 14/05/2025 | 13/06/2025 | SRIJON ENTERPRISE | 39.56 | 0 | 0 | 0
12 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-IX OF KULPI BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOUTH 24 | SM/18551 | Augmentation | Land Development and beautification within the head works site under Zone No-X of Kulpi Block under Mega Surface Water Based Water Supply Scheme , Dist. South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/002490/2024-2025 | 781/AD | 25/02/2025 | 27/03/2025 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 21.59 | 0 | 0 | 0
Total | [13 empty] | 1107.15 | 391.49 | 35.36