## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-VIII(A) OF KULPI BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOU | SM/18552 | Augmentation | Improvement of water as an interim measure by interconnection from Tubewells to OHR within Zone No-VIII(A) of Kulpi Block under Mega Surface Water Based Water Supply Scheme , Dist. South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. (2nd Call) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer | ORD/000666/2023-2024 | 2600/AD | 31/08/2023 | 15/09/2023 | GLOBUS CONSULTANCEY | 9.43 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-VIII(A) OF KULPI BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOU | SM/18552 | Augmentation | Special repairing and restoration of distribution system at different places (Rangafala, Patra para etc.) of Arunnagar Belpukuria PWSS under zone-VIIIA at Kulpi Block for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer | ORD/001152/2023-2024 | 3198/AD | 04/10/2023 | 03/11/2023 | M/S. SUMAN ENTERPRISE | 26.48 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-VIII(A) OF KULPI BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOU | SM/18552 | Augmentation | Support service for detail surveying, cross checking of available LOP with making permission drawings for other department by using Survey Instruments like Remotly Piloted Aircraft System/ DGPS / Total Station etc. and detailed design of pipeline by using Watergems Software on the basis of the population density within the Zone-VIII(A) of Kulpi Block under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division |  | ORD/001020/2022-2023 | 293/DHSD | 15/09/2022 | 15/10/2022 | GEO SOLUTION | 4.41 | 3.69 | 83.62 | 99
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-VIII(A) OF KULPI BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOU | SM/18552 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000369/2023-2024 | 3233/AD | 04/10/2023 | 04/10/2023 | Resource Division | 0.21 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-VIII(A) OF KULPI BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOU | SM/18552 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000210/2023-2024 | 2019/AD | 05/08/2023 | 05/08/2023 | Resource Division | 25.17 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-VIII(A) OF KULPI BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOU | SM/18552 | Augmentation | Preparation of design, drawing for foundation for the proposed R.C.C. Over Head Reservoir at Zone-VIII(A) (Arunnagar, OHR Size-1500 ) within Kulpi Block under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer,Junior Engineer 2 DHSD | ORD/002099/2022-2023 | 338/DHSD | 17/11/2022 | 24/11/2022 | ASTER CONSULTANCY | 0.5 | 0.5 | 100 | 100
7 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-VIII(A) OF KULPI BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOU | SM/18552 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000625/2023-2024 | 286/AD | 15/01/2024 | 15/01/2024 | Resource Division | 9.24 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-VIII(A) OF KULPI BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOU | SM/18552 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000672/2023-2024 | 425/AD | 22/01/2024 | 22/01/2024 | Resource Division | 244.27 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-VIII(A) OF KULPI BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOU | SM/18552 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000938/2023-2024 | 1280/AD | 02/03/2024 | 02/03/2024 | Resource Division | 0.62 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-VIII(A) OF KULPI BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOU | SM/18552 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000859/2023-2024 | 766/AD | 03/02/2024 | 03/02/2024 | Resource Division | 45.26 | 0 | 0 | 0
11 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-VIII(A) OF KULPI BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOU | SM/18552 | Augmentation | Additional laying of pipeline under the Augmentation Scheme of Kulpi Zone-VIIIA for providing 100% FHTC under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. [SM/18552] | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/001456/2024-2025 | 14/AD | 03/01/2025 | 04/03/2025 | SUBHO CONSTRUCTION | 361.14 | 0 | 0 | 0
12 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-VIII(A) OF KULPI BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOU | SM/18552 | Augmentation | Augmentation of laying distribution system including construction of 1500 m3 capacity OHR to extend the benefit of 100% household by Providing Functional Household Tap Connection (FHTC) from distribution system in Zone-VIII(A) at Kulpi block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. [No of FHTC-8848] . | Assistant Engineer, Diamond Harbour sub division | Junior Engineer | ORD/000478/2023-2024 | 1991/AD | 04/08/2023 | 02/01/2026 | M/S. S.S. ENTERPRISE | 2077.27 | 1109.01 | 53.39 | 30
13 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-VIII(A) OF KULPI BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOU | SM/18552 | Augmentation | Land Developement and other allied works within the head works site under Zone No-VIIIA of Kulpi Block under "Mega Surface Water Based Water Supply Scheme , Dist. South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. [SM/18552] | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD,Junior Engineer 4 DHSD | ORD/001397/2024-2025 | 5543/AD | 30/12/2024 | 13/02/2025 | M/S. S.S. ENTERPRISE | 100.84 | 0 | 0 | 30
Total | [13 empty] | 2904.84 | 1113.2 | 38.32