## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS | Patharpratima | S24 Pgns Mechanical | GROUND WATER BASED KSHETRA MOHANPUR (ZONE I & II), PIPE WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, BLOCK PATHARPRATIMA DISTRICT SOUTH 24 PARGANAS | SM/18673 | New | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2,3 & 4 ( Zone-I & II) of Kshetra Mohanpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Patharpratima] | Assistant Engineer -I | Junior Engineer | ORD/000117/2023-2024 | 1024/SMD | 12/04/2023 | 11/07/2023 | NITESH MANAGEMENT | 38.11 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED KSHETRA MOHANPUR (ZONE I & II), PIPE WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, BLOCK PATHARPRATIMA DISTRICT SOUTH 24 PARGANAS | SM/18673 | New | Construction of 150 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of foundation after soil investagation including O & M of Laying distribution, Rising Main & FHTC for 1 year after completion of FHTC works for Kshetra Mohanpur (Zone - I & II) Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-II) (Part-A) [No. of FHTC = 350] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000534/2023-2024 | 2147/AD | 09/08/2023 | 20/01/2026 | RELIABLE CONSTRUCTIONS | 169.85 | 31.75 | 18.69 | 20
3 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED KSHETRA MOHANPUR (ZONE I & II), PIPE WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, BLOCK PATHARPRATIMA DISTRICT SOUTH 24 PARGANAS | SM/18673 | New | Laying distribution system, Functional Household Tap Connection (FHTC) to all households including construction of 02 nos, Pump House for Kshetra Mohanpur (Zone - I & II) Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone - II) (Part-B) [No. of FHTC = 800] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000535/2023-2024 | 2148/AD | 09/08/2023 | 12/01/2026 | RELIABLE CONSTRUCTIONS | 169.24 | 93.05 | 54.98 | 55
4 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED KSHETRA MOHANPUR (ZONE I & II), PIPE WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, BLOCK PATHARPRATIMA DISTRICT SOUTH 24 PARGANAS | SM/18673 | New | Construction of 100 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of foundation after soil investagation including O & M of Laying distribution, Rising Main & FHTC for 1 year after completion of FHTC works for Kshetra Mohanpur (Zone - I & II) Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (Part-A) [No. of FHTC = 350] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000542/2023-2024 | 3729/AD | 03/11/2023 | 01/04/2026 | CHAKRABORTTI ENTERPRISE | 168.05 | 34.02 | 20.24 | 20
5 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED KSHETRA MOHANPUR (ZONE I & II), PIPE WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, BLOCK PATHARPRATIMA DISTRICT SOUTH 24 PARGANAS | SM/18673 | New | Laying distribution system, Functional Household Tap Connection (FHTC) to all households including construction of 02 nos, Pump House for Kshetra Mohanpur (Zone - I & II) Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone - I) (Part-B) [No. of FHTC = 455] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000536/2023-2024 | 3738/AD | 03/11/2023 | 23/04/2025 | CHAKRABORTTI ENTERPRISE | 128.72 | 84.82 | 65.89 | 50
6 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED KSHETRA MOHANPUR (ZONE I & II), PIPE WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, BLOCK PATHARPRATIMA DISTRICT SOUTH 24 PARGANAS | SM/18673 | New | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Kshetra Mohanpur (Zone - I & II) W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-II) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000555/2023-2024 | 2237/AD | 11/08/2023 | 21/09/2024 | GOLDEN GROUPS | 49.2 | 0 | 0 | 100
7 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED KSHETRA MOHANPUR (ZONE I & II), PIPE WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, BLOCK PATHARPRATIMA DISTRICT SOUTH 24 PARGANAS | SM/18673 | New | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Kshetra Mohanpur (Zone-I & II)W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000554/2023-2024 | 2236/AD | 11/08/2023 | 25/09/2023 | GOLDEN GROUPS | 49.2 | 12.27 | 24.93 | 90
8 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED KSHETRA MOHANPUR (ZONE I & II), PIPE WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, BLOCK PATHARPRATIMA DISTRICT SOUTH 24 PARGANAS | SM/18673 | New | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (Kshetra mohanpur (Zone - I & II)PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000639/2023-2024 | 2032/AD | 05/08/2023 | 19/09/2023 | INDRANIL DUTTA & ASSOCIATES | 8.71 | 8.71 | 100 | 100
9 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED KSHETRA MOHANPUR (ZONE I & II), PIPE WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, BLOCK PATHARPRATIMA DISTRICT SOUTH 24 PARGANAS | SM/18673 | New | Making and fixing of permanent display board at headwork site of Kshetramohanpur Zone - I & II, Brojoballavpur Zone - I & II PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/002112/2023-2024 | 932/KSD | 19/12/2023 | 24/12/2023 | BIMALENDU GIRI | 0.81 | 0.4 | 49.99 | 100
10 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED KSHETRA MOHANPUR (ZONE I & II), PIPE WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, BLOCK PATHARPRATIMA DISTRICT SOUTH 24 PARGANAS | SM/18673 | New | Material Requisition To Resource Division |  |  | RTOR000109/2023-2024 | 645/AD | 17/05/2023 | 17/05/2023 | Resource Division | 10.74 | 0 | 0 | 0
11 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED KSHETRA MOHANPUR (ZONE I & II), PIPE WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, BLOCK PATHARPRATIMA DISTRICT SOUTH 24 PARGANAS | SM/18673 | New | Material Requisition To Resource Division |  |  | RTOR000487/2023-2024 | 4753/AD | 19/12/2023 | 19/12/2023 | Resource Division | 52.84 | 0 | 0 | 0
12 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED KSHETRA MOHANPUR (ZONE I & II), PIPE WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, BLOCK PATHARPRATIMA DISTRICT SOUTH 24 PARGANAS | SM/18673 | New | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections etc. at Kshetra Mohanpur (Zone-I &II) W/S Scheme, Block -Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (Zone-II) (SM/18673) | Assistant Engineer, Canning sub division,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,1 CSD,Juniour Engineer_1, Kakdwip Sub Division | ORD/000353/2024-2025 | 2798/AD | 02/07/2024 | 16/07/2025 | RELIABLE CONSTRUCTIONS | 129.53 | 0 | 0 | 0
13 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED KSHETRA MOHANPUR (ZONE I & II), PIPE WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, BLOCK PATHARPRATIMA DISTRICT SOUTH 24 PARGANAS | SM/18673 | New | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections etc. at Kshetra Mohanpur (Zone-I &II) W/S Scheme, Block -Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (Zone-I) (SM/18673) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000398/2024-2025 | 3181/AD | 31/07/2024 | 29/09/2024 | CHAKRABORTTI ENTERPRISE | 54.18 | 0 | 0 | 0
14 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED KSHETRA MOHANPUR (ZONE I & II), PIPE WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, BLOCK PATHARPRATIMA DISTRICT SOUTH 24 PARGANAS | SM/18673 | New | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Kshetra Mohanpur (Zone - I & II) PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (for Zone-I) (SM/18673) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/003207/2023-2024 | 160/KSD | 05/01/2024 | 15/01/2024 | CONSTEEL CONSULTANCY & SERVICES | 0.48 | 0 | 0 | 0
15 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED KSHETRA MOHANPUR (ZONE I & II), PIPE WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, BLOCK PATHARPRATIMA DISTRICT SOUTH 24 PARGANAS | SM/18673 | New | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Kshetra Mohanpur (Zone - I & II) PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (for Zone-II) (SM/18673) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/003208/2023-2024 | 159/KSD | 05/01/2024 | 15/01/2024 | CONSTEEL CONSULTANCY & SERVICES | 0.48 | 0 | 0 | 100
16 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED KSHETRA MOHANPUR (ZONE I & II), PIPE WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, BLOCK PATHARPRATIMA DISTRICT SOUTH 24 PARGANAS | SM/18673 | New | Material Requisition To Resource Division |  |  | RTOR000766/2023-2024 | 600/AD | 29/01/2024 | 29/01/2024 | Resource Division | 4.05 | 0 | 0 | 0
17 | SOUTH 24 PARGANAS | Patharpratima | S24 Pgns Mechanical | GROUND WATER BASED KSHETRA MOHANPUR (ZONE I & II), PIPE WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, BLOCK PATHARPRATIMA DISTRICT SOUTH 24 PARGANAS | SM/18673 | New | Khetra Mohanpur (Zone-I) PH-2 Water supply scheme Application No- 1008061551 Reference ID- 106731405 |  |  | BILL/02902/2024-2025 | BP-2024-25-582 | 20/03/2025 | 20/03/2025 | WBSEDCL | 8.97 | 0 | 0 | 0
18 | SOUTH 24 PARGANAS | Patharpratima | S24 Pgns Mechanical | GROUND WATER BASED KSHETRA MOHANPUR (ZONE I & II), PIPE WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, BLOCK PATHARPRATIMA DISTRICT SOUTH 24 PARGANAS | SM/18673 | New | New Service connection and security deposit for Khetromohanpur PH-1 Zone-I under JJM Application No-1008101013 Ref ID- 106755054 |  |  | BILL/00253/2025-2026 | 42152 | 01/08/2025 | 01/08/2025 | WBSEDCL | 4.31 | 0 | 0 | 0
19 | SOUTH 24 PARGANAS | Patharpratima | S24 Pgns Mechanical | GROUND WATER BASED KSHETRA MOHANPUR (ZONE I & II), PIPE WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, BLOCK PATHARPRATIMA DISTRICT SOUTH 24 PARGANAS | SM/18673 | New | Khetra Mohanpur (Zone-II) PH-1 Water supply scheme Application No- 1007907826 Reference ID- 106657685 |  |  | BILL/02900/2024-2025 | BP-2024-25-580 | 20/03/2025 | 20/03/2025 | WBSEDCL | 4.98 | 0 | 0 | 0
20 | SOUTH 24 PARGANAS | Patharpratima | S24 Pgns Mechanical | GROUND WATER BASED KSHETRA MOHANPUR (ZONE I & II), PIPE WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, BLOCK PATHARPRATIMA DISTRICT SOUTH 24 PARGANAS | SM/18673 | New | Khetra Mohanpur (Zone-II) PH-2 Water supply scheme Application No- 1007907891 Reference ID- 106657688 |  |  | BILL/02901/2024-2025 | BP-2024-25-581 | 20/03/2025 | 20/03/2025 | WBSEDCL | 3.58 | 0 | 0 | 0
Total | [13 empty] | 1056.01 | 265.01 | 25.1