## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED GOSABA (ZONE - II) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE.IN THE DISTRICT OF SOUTH 24 PARGANAS | SM/18674 | Augmentation | Sinking of 03 (three) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Gosaba W/S Scheme (Zone-II), Block - Gosaba under Canning Sub Division of Alipore Division, PHE Dte. (Tubewell No. 1, 2, 3) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000546/2023-2024 | 2078/AD | 07/08/2023 | 06/10/2023 | DOLY CONSTRUCTION | 67.35 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED GOSABA (ZONE - II) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE.IN THE DISTRICT OF SOUTH 24 PARGANAS | SM/18674 | Augmentation | Construction of 01 (one) nos. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site Augmentation of Gosaba (Zone-II) W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. (Pump House No.-IX) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000515/2023-2024 | 2070/AD | 07/08/2023 | 21/09/2023 | A.M.ENTERPRISE (I) | 8.64 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED GOSABA (ZONE - II) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE.IN THE DISTRICT OF SOUTH 24 PARGANAS | SM/18674 | Augmentation | Construction of 01 (one) nos. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site Augmentation of Gosaba (Zone-II) W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. (Pump House No.-II) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000508/2023-2024 | 2063/AD | 07/08/2023 | 21/09/2023 | S.B. ENTERPRISE | 8.64 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED GOSABA (ZONE - II) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE.IN THE DISTRICT OF SOUTH 24 PARGANAS | SM/18674 | Augmentation | Construction of 01 (one) nos. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site Agumentation of Gosaba (Zone-II) W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House No.VIII] | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000514/2023-2024 | 2069/AD | 07/08/2023 | 21/09/2023 | SUPER CONSTRUCTION | 8.59 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED GOSABA (ZONE - II) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE.IN THE DISTRICT OF SOUTH 24 PARGANAS | SM/18674 | Augmentation | Construction of 01 (one) nos. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site Augmentation of Gosaba (Zone-II) W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. (Pump House No.-XIII) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000519/2023-2024 | 2074/AD | 07/08/2023 | 21/09/2023 | KAMALA ENTERPRISE (I) | 8.64 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED GOSABA (ZONE - II) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE.IN THE DISTRICT OF SOUTH 24 PARGANAS | SM/18674 | Augmentation | Sinking of 04 (four) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Gosaba W/S Scheme (Zone-II), Block - Gosaba under Canning Sub Division of Alipore Division, PHE Dte. (Tubewell No. 10, 11, 12, 13) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000549/2023-2024 | 2081/AD | 07/08/2023 | 05/11/2023 | SETABUR RAHAMAN | 89.78 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED GOSABA (ZONE - II) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE.IN THE DISTRICT OF SOUTH 24 PARGANAS | SM/18674 | Augmentation | Construction of 01 (one) nos. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site Agumentation of Gosaba (Zone-II) W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. (Pump House No.III) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000509/2023-2024 | 2064/AD | 07/08/2023 | 21/09/2023 | M/S. GANGA ENTERPRISE | 8.64 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED GOSABA (ZONE - II) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE.IN THE DISTRICT OF SOUTH 24 PARGANAS | SM/18674 | Augmentation | Construction of 01 (one) nos. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site Augmentation of Gosaba (Zone-II) W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. (Pump House No.-IV) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000510/2023-2024 | 2065/AD | 07/08/2023 | 21/09/2023 | M/S. GANGA ENTERPRISE | 8.63 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED GOSABA (ZONE - II) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE.IN THE DISTRICT OF SOUTH 24 PARGANAS | SM/18674 | Augmentation | Construction of 01 (one) nos. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site Augmentation of Gosaba (Zone-II) W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. (Pump House No.XII) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000518/2023-2024 | 2073/AD | 07/08/2023 | 21/09/2023 | RAJLAKSHMI ENTERPRISE | 8.64 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED GOSABA (ZONE - II) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE.IN THE DISTRICT OF SOUTH 24 PARGANAS | SM/18674 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at 13 Nos Pump House of Gosaba Zone-II water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Gosaba] | Assistant Engineer | Junior Engineer | ORD/000807/2023-2024 | 2997/SMD | 14/09/2023 | 14/09/2024 | M/S. S.S. ENTERPRISE | 172.29 | 0 | 0 | 0
11 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED GOSABA (ZONE - II) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE.IN THE DISTRICT OF SOUTH 24 PARGANAS | SM/18674 | Augmentation | Conducting route survey, design distribution network and preparation & submission of DPR for Gosaba (Zone-II) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Gosaba Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000615/2023-2024 | 2270/AD | 14/08/2023 | 28/09/2023 | M/S R.DUTTA & CO. | 35.42 | 0 | 0 | 98
12 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED GOSABA (ZONE - II) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE.IN THE DISTRICT OF SOUTH 24 PARGANAS | SM/18674 | Augmentation | Construction of OHR (250 Cum), Construction of OHR (600 Cum), Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water based Augmentation Piped Water Supply Scheme for the Gosaba (Zone-II), Block-Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [TSM/018435] | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000563/2023-2024 | 2255/AD | 14/08/2023 | 09/06/2024 | J.D.J. ENTERPRISE (A UNIT OF JDJ TRADERS PVT. LTD.) | 2050.6 | 0 | 0 | 25
13 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED GOSABA (ZONE - II) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE.IN THE DISTRICT OF SOUTH 24 PARGANAS | SM/18674 | Augmentation | Hiring Motor launch for Canning Sub Division under Alipore Division,PHE Dte. in connection with execution and maintenance of different piped water supply schemes at different island in the district of South 24 Parganas. (for 365 days) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001336/2024-2025 | 5442/AD | 26/12/2024 | 26/12/2025 | RAJKUMAR MANNA | 40.7 | 0 | 0 | 0
14 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED GOSABA (ZONE - II) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE.IN THE DISTRICT OF SOUTH 24 PARGANAS | SM/18674 | Augmentation | Construction of boundary wall at Pump House No. - 12 for Augmentation of Ground Water Based Gosaba (Zone-II) Piped Water Supply Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000767/2024-2025 | 4468/AD | 11/11/2024 | 11/12/2024 | A 8 T CONSTRUCTION | 13.68 | 0 | 0 | 0
15 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED GOSABA (ZONE - II) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE.IN THE DISTRICT OF SOUTH 24 PARGANAS | SM/18674 | Augmentation | Construction of boundary wall at Pump House No. - 10 for Augmentation of Ground Water Based Gosaba (Zone-II) Piped Water Supply Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000769/2024-2025 | 4470/AD | 11/11/2024 | 11/12/2024 | BANGA NIRMAN | 13.35 | 0 | 0 | 0
16 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED GOSABA (ZONE - II) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE.IN THE DISTRICT OF SOUTH 24 PARGANAS | SM/18674 | Augmentation | Construction of boundary wall at Pump House No. - 1 for Augmentation of Ground Water Based Gosaba (Zone-II) Piped Water Supply Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000677/2024-2025 | 4250/AD | 26/10/2024 | 25/11/2024 | NEPAL CHANDRA PRADHAN | 11.97 | 0 | 0 | 0
17 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED GOSABA (ZONE - II) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE.IN THE DISTRICT OF SOUTH 24 PARGANAS | SM/18674 | Augmentation | Construction of boundary wall at Pump House No. - 2 for Augmentation of Ground Water Based Gosaba (Zone-II) Piped Water Supply Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000676/2024-2025 | 4249/AD | 26/10/2024 | 25/11/2024 | S.B. ENTERPRISE | 14.29 | 0 | 0 | 0
18 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED GOSABA (ZONE - II) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE.IN THE DISTRICT OF SOUTH 24 PARGANAS | SM/18674 | Augmentation | Construction of boundary wall at Pump House No. - 8 for Augmentation of Ground Water Based Gosaba (Zone-II) Piped Water Supply Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001243/2024-2025 | 5241/AD | 17/12/2024 | 16/01/2025 | ASHIS ENTERPRISE | 14.16 | 0 | 0 | 0
19 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED GOSABA (ZONE - II) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE.IN THE DISTRICT OF SOUTH 24 PARGANAS | SM/18674 | Augmentation | Construction of boundary wall at Pump House No. - 11 for Augmentation of Ground Water Based Gosaba (Zone-II) Piped Water Supply Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000768/2024-2025 | 4469/AD | 11/11/2024 | 11/12/2024 | BANGA NIRMAN | 13.35 | 0 | 0 | 0
20 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED GOSABA (ZONE - II) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE.IN THE DISTRICT OF SOUTH 24 PARGANAS | SM/18674 | Augmentation | Construction of boundary wall at Pump House No. - 7 for Augmentation of Ground Water Based Gosaba (Zone-II) Piped Water Supply Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000770/2024-2025 | 4471/AD | 11/11/2024 | 11/12/2024 | SUBHO CONSTRUCTION | 14.16 | 0 | 0 | 0
21 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED GOSABA (ZONE - II) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE.IN THE DISTRICT OF SOUTH 24 PARGANAS | SM/18674 | Augmentation | Construction of boundary wall at Pump House No. - 5 for Augmentation of Ground Water Based Gosaba (Zone-II) Piped Water Supply Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000771/2024-2025 | 4472/AD | 11/11/2024 | 11/12/2024 | CHATTERJEE ENTERPRISES | 13.85 | 0 | 0 | 0
22 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED GOSABA (ZONE - II) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE.IN THE DISTRICT OF SOUTH 24 PARGANAS | SM/18674 | Augmentation | Construction of boundary wall at CWR for Augmentation of Ground water Based at Gosaba (Zone- II)Piped Water Supply Scheme Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000742/2024-2025 | 4399/AD | 05/11/2024 | 20/12/2024 | SWASTIK CONSTRUCTION | 37.17 | 0 | 0 | 0
23 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED GOSABA (ZONE - II) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE.IN THE DISTRICT OF SOUTH 24 PARGANAS | SM/18674 | Augmentation | Construction of 01 (one) nos. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site Augmentation of Gosaba (Zone-II) W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. (Pump House No.-X) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000516/2023-2024 | 2071/AD | 07/08/2023 | 01/11/2024 | A.M.ENTERPRISE (I) | 8.64 | 0 | 0 | 100
24 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED GOSABA (ZONE - II) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE.IN THE DISTRICT OF SOUTH 24 PARGANAS | SM/18674 | Augmentation | Construction of 01 (one) nos. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site Augmentation of Gosaba (Zone-II) W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. (Pump House No.-XI) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000517/2023-2024 | 2072/AD | 07/08/2023 | 21/09/2023 | B.S.ENTERPRISE | 8.62 | 0 | 0 | 100
25 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED GOSABA (ZONE - II) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE.IN THE DISTRICT OF SOUTH 24 PARGANAS | SM/18674 | Augmentation | Survey, Soil Investigation/Geo-technical survey, preparation of design and drawing, making service corridor for installation of 315 mm (Nominal OD) HDPE Pipe by HDD method under the river bed of Durga Doani River at Gosaba Island for Gosaba Zone -II WS Scheme. The works include transportation of machineries and mobilization, supply of 315 mm (Nominal OD) HDPE pipe (PE80, PN10) including laying / installation, pressure testing of laid pipe, hire charges of all machine and tools, expenses of consumables (Bentonite /Polymer, Diesel, hydraulic machine, water etc.) including transportation all type of man power, HDD operation cost, Electric / Lighting arrangement at site, insurance for staff, labour, materials and machine including GST @18%, cess @1% and riverine @22.50% and all other charges including site clearance. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001033/2023-2024 | 3188/AD | 03/10/2023 | 17/12/2023 | ATINDRA CONSTRUCTION PRIVATE LIMITED | 449.89 | 0 | 0 | 100
26 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED GOSABA (ZONE - II) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE.IN THE DISTRICT OF SOUTH 24 PARGANAS | SM/18674 | Augmentation | Laying DI pipe line and other allied works at Kalir Khal of Pond Based Surface Water Supply Scheme of Block- Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001929/2023-2024 | 1173/CSD | 06/11/2023 | 16/11/2023 | MOHANA ENTERPRISES | 0.97 | 0 | 0 | 100
27 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED GOSABA (ZONE - II) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE.IN THE DISTRICT OF SOUTH 24 PARGANAS | SM/18674 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000407/2023-2024 | 361/AD | 19/01/2024 | 19/01/2024 | Resource Division | 60.32 | 0 | 0 | 0
28 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED GOSABA (ZONE - II) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE.IN THE DISTRICT OF SOUTH 24 PARGANAS | SM/18674 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000721/2023-2024 | 543/AD | 25/01/2024 | 25/01/2024 | Resource Division | 1057.58 | 0 | 0 | 0
29 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED GOSABA (ZONE - II) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE.IN THE DISTRICT OF SOUTH 24 PARGANAS | SM/18674 | Augmentation | Sinking of 03 (three) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Gosaba W/S Scheme (Zone-II), Block - Gosaba under Canning Sub Division of Alipore Division, PHE Dte. (Tubewell No. 4, 5, 6) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000547/2023-2024 | 2079/AD | 07/08/2023 | 01/09/2025 | SUNDARBAN CONSTRUCTION | 67.23 | 0 | 0 | 90
30 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED GOSABA (ZONE - II) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE.IN THE DISTRICT OF SOUTH 24 PARGANAS | SM/18674 | Augmentation | Construction of 01 (one) nos. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site Augmentation of Gosaba (Zone-II) W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. (Pump House No.-V) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000511/2023-2024 | 2066/AD | 07/08/2023 | 01/08/2024 | JYOTI ENTERPRISES | 8.64 | 0 | 0 | 100
31 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED GOSABA (ZONE - II) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE.IN THE DISTRICT OF SOUTH 24 PARGANAS | SM/18674 | Augmentation | Construction of 01 (one) nos. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site Augmentation of Gosaba (Zone-II) W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. (Pump House No.-VI) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000512/2023-2024 | 2067/AD | 07/08/2023 | 01/08/2024 | JYOTI ENTERPRISES | 8.64 | 0 | 0 | 100
32 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED GOSABA (ZONE - II) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE.IN THE DISTRICT OF SOUTH 24 PARGANAS | SM/18674 | Augmentation | Sinking of 03 (three) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Gosaba W/S Scheme (Zone-II), Block - Gosaba under Canning Sub Division of Alipore Division, PHE Dte. (Tubewell No. 7, 8, 9) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000548/2023-2024 | 2080/AD | 07/08/2023 | 01/09/2025 | SUNDARBAN CONSTRUCTION | 67.23 | 0 | 0 | 100
33 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED GOSABA (ZONE - II) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE.IN THE DISTRICT OF SOUTH 24 PARGANAS | SM/18674 | Augmentation | Construction of 02 (two) nos. 100 Cum. Clear Water Reservoir (CWR) at Gosaba (Zone-II) Water Supply Scheme of Gosaba Block under Canning Sub- Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000299/2024-2025 | 2679AD | 24/06/2024 | 01/05/2025 | SWASTIK CONSTRUCTION | 67.49 | 0 | 0 | 40
34 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED GOSABA (ZONE - II) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE.IN THE DISTRICT OF SOUTH 24 PARGANAS | SM/18674 | Augmentation | Laying pipe line from C.W.R. - 2 to O.H.R. point of Augmentation of Ground Water Based at Gosaba (Zone-II) W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000092/2025-2026 | 2521/AD | 30/05/2025 | 14/07/2025 | S.P. CONSTRUCTION (I) | 25.17 | 0 | 0 | 0
35 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED GOSABA (ZONE - II) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE.IN THE DISTRICT OF SOUTH 24 PARGANAS | SM/18674 | Augmentation | Construction of boundary wall at Pump House No. - 9 for Augmentation of Ground Water Based Gosaba (Zone-II) Piped Water Supply Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000024/2025-2026 | 2010/AD | 28/04/2025 | 28/05/2025 | SUBHASISH SAU | 12.97 | 0 | 0 | 0
36 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED GOSABA (ZONE - II) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE.IN THE DISTRICT OF SOUTH 24 PARGANAS | SM/18674 | Augmentation | Construction of 01 (one) nos. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site Augmentation of Gosaba (Zone-II) W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. (Pump House No.VII) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000513/2023-2024 | 2068/AD | 07/08/2023 | 01/01/2025 | SUPER CONSTRUCTION | 8.59 | 0 | 0 | 100
37 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED GOSABA (ZONE - II) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE.IN THE DISTRICT OF SOUTH 24 PARGANAS | SM/18674 | Augmentation | Construction of 01 (one) nos. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site Augmentation of Gosaba (Zone-II) W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. (Pump House No. I) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000507/2023-2024 | 2062/AD | 07/08/2023 | 01/02/2025 | S.B. ENTERPRISE | 8.64 | 0 | 0 | 100
Total | [13 empty] | 4523.14 | 0 | 0