## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF SONAKHALI (ZONE-III) PIPED WATER SUPPLY SCHEME, BLOCK-BASANTI,DISTRICT-SOUTH 24 PARGANAS | SM/18675 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, Zone-III for Augmentation of Sonakhali water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Basanti] | Assistant Engineer | Junior Engineer | ORD/001512/2022-2023 | 888/SMD | 24/03/2023 | 22/06/2023 | MAA TARA ENTERPRISE | 10.41 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF SONAKHALI (ZONE-III) PIPED WATER SUPPLY SCHEME, BLOCK-BASANTI,DISTRICT-SOUTH 24 PARGANAS | SM/18675 | Augmentation | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Sonakhali W/S Scheme (Zone-III) , Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000502/2023-2024 | 2060/AD | 07/08/2023 | 21/09/2023 | MAA SOLAR ENTERPRISE | 7.11 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF SONAKHALI (ZONE-III) PIPED WATER SUPPLY SCHEME, BLOCK-BASANTI,DISTRICT-SOUTH 24 PARGANAS | SM/18675 | Augmentation | Sinking of 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Sonakhali (Zone - III) W/S Scheme, Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000559/2023-2024 | 2246/AD | 11/08/2023 | 10/09/2023 | SAMIR GIRI | 19.56 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF SONAKHALI (ZONE-III) PIPED WATER SUPPLY SCHEME, BLOCK-BASANTI,DISTRICT-SOUTH 24 PARGANAS | SM/18675 | Augmentation | Inter connection and rising main with supply of specials of Augmentation of Sonakhali (Zone-III) W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division |  | ORD/001081/2023-2024 | 3540/AD | 17/10/2023 | 01/11/2023 | ARBINA ENTERPRISE | 27.69 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF SONAKHALI (ZONE-III) PIPED WATER SUPPLY SCHEME, BLOCK-BASANTI,DISTRICT-SOUTH 24 PARGANAS | SM/18675 | Augmentation | Conducting route survey, design distribution network and preparation & submission of DPR for Sonakhali (Zone-III) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Basanti Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000606/2023-2024 | 2269/AD | 14/08/2023 | 28/09/2023 | TECH VISION | 6.39 | 6.39 | 100 | 99
6 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF SONAKHALI (ZONE-III) PIPED WATER SUPPLY SCHEME, BLOCK-BASANTI,DISTRICT-SOUTH 24 PARGANAS | SM/18675 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000037/2023-2024 | 243/AD | 24/04/2023 | 24/04/2023 | Resource Division | 82.44 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF SONAKHALI (ZONE-III) PIPED WATER SUPPLY SCHEME, BLOCK-BASANTI,DISTRICT-SOUTH 24 PARGANAS | SM/18675 | Augmentation | Laying Distribution System, Providing Functional Household Tap Connection for Ground Water Based Augmentation Piped Water Supply Scheme for the Sonakhali (Zone-III), Block-Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [No. of FHTC = 1981] | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000632/2023-2024 | 2156/AD | 09/08/2023 | 07/11/2023 | M/S SHIBAM ENTERPRISE | 450.06 | 95.91 | 21.31 | 65
8 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF SONAKHALI (ZONE-III) PIPED WATER SUPPLY SCHEME, BLOCK-BASANTI,DISTRICT-SOUTH 24 PARGANAS | SM/18675 | Augmentation | Construction of 1 (one) no. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Sonakhali W/S Scheme (Zone-III), Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House No. III] | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000314/2024-2025 | 2695/AD | 24/06/2024 | 08/08/2024 | GANGA TUBEWELL AND HARDWARE | 7.05 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF SONAKHALI (ZONE-III) PIPED WATER SUPPLY SCHEME, BLOCK-BASANTI,DISTRICT-SOUTH 24 PARGANAS | SM/18675 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000394/2023-2024 | 335/AD | 19/01/2024 | 19/01/2024 | Resource Division | 12.2 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF SONAKHALI (ZONE-III) PIPED WATER SUPPLY SCHEME, BLOCK-BASANTI,DISTRICT-SOUTH 24 PARGANAS | SM/18675 | Augmentation | Construction of 23 Nos. different capacity R.C.C OHR (based on Departmental Design & Drawing ) with 20 mtr. staging height including Geo-Technical investigation, foundation, pipeline connection and cost of pipes , specials etc. for augmentation of different piped water supply scheme of Canning-I, Canning-II & Basanti Block under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD,Junior Engineer,1 CSD | ORD/002461/2023-2024 | 1512/AD | 13/03/2024 | 03/11/2025 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LTD | 2624.49 | 0 | 0 | 30
11 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF SONAKHALI (ZONE-III) PIPED WATER SUPPLY SCHEME, BLOCK-BASANTI,DISTRICT-SOUTH 24 PARGANAS | SM/18675 | Augmentation | Repairing & renovation of Pump House no. - 1 of Sonakhali (Zone-III) W/S Scheme Block - Basanti under Canning Sub- Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000287/2025-2026 | 690/CSD | 26/05/2025 | 25/06/2025 | ARANYA ENTERPRISE | 2.92 | 0 | 0 | 0
Total | [13 empty] | 3250.31 | 102.3 | 3.15