## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF KALARIA (ZONE-IA & IB) PIPED WATER SUPPLY SCHEME, BLOCK-CANNING-I,DISTRICT-SOUTH 24 PARGANAS | SM/18676 | Augmentation | Sinking of 03 (three) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Augmentation of Kalaria (Zone-IB) W/S Scheme, Block - Canning-I under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000558/2023-2024 | 2245/AD | 11/08/2023 | 10/10/2023 | B.K. ENTERPRISE. | 60 | 55.95 | 93.26 | 98
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF KALARIA (ZONE-IA & IB) PIPED WATER SUPPLY SCHEME, BLOCK-CANNING-I,DISTRICT-SOUTH 24 PARGANAS | SM/18676 | Augmentation | Conducting route survey, design distribution network and preparation & submission of DPR for Kalaria (Zone-IA & IB) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Canning-I Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000616/2023-2024 | 2271/AD | 14/08/2023 | 28/09/2023 | INDRANIL DUTTA & ASSOCIATES | 7.51 | 7.51 | 100 | 98
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF KALARIA (ZONE-IA & IB) PIPED WATER SUPPLY SCHEME, BLOCK-CANNING-I,DISTRICT-SOUTH 24 PARGANAS | SM/18676 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000065/2023-2024 | 268/AD | 24/04/2023 | 24/04/2023 | Resource Division | 42.51 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF KALARIA (ZONE-IA & IB) PIPED WATER SUPPLY SCHEME, BLOCK-CANNING-I,DISTRICT-SOUTH 24 PARGANAS | SM/18676 | Augmentation | Providing Functional Household Tap Connection (FHTC) of Ground Water Based Augmentation Piped Water Supply Scheme for Kalaria (Zone-IA), Block-Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. [No. of FHTC = 2133] (TSM/017465) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000528/2023-2024 | 2143/AD | 09/08/2023 | 30/01/2025 | PUTUL RANI MAITY | 127.34 | 65.94 | 51.78 | 70
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF KALARIA (ZONE-IA & IB) PIPED WATER SUPPLY SCHEME, BLOCK-CANNING-I,DISTRICT-SOUTH 24 PARGANAS | SM/18676 | Augmentation | Laying additional pipe line to connect the uncovered habitation for Augmentation of Kalaria (Zone-IB) W/S Scheme, Block-Canning-I under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000488/2024-2025 | 3547/AD | 02/09/2024 | 17/10/2024 | SUPRITI ENTERPRISE | 34.28 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF KALARIA (ZONE-IA & IB) PIPED WATER SUPPLY SCHEME, BLOCK-CANNING-I,DISTRICT-SOUTH 24 PARGANAS | SM/18676 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2 & 3 Zone-IA & IB for Augmentation of Kalaria Water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Canning-I] | Assistant Engineer | Junior Engineer | ORD/000268/2023-2024 | 1128/SMD | 24/04/2023 | 23/07/2023 | PADMA ENGINEERING CO. | 26.98 | 26.83 | 99.45 | 100
7 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF KALARIA (ZONE-IA & IB) PIPED WATER SUPPLY SCHEME, BLOCK-CANNING-I,DISTRICT-SOUTH 24 PARGANAS | SM/18676 | Augmentation | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Kalaria W/S Scheme (Zone-IB), Block - Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-II] | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000521/2023-2024 | 2076/AD | 07/08/2023 | 21/09/2023 | ASHIS ENTERPRISE | 7.06 | 6.73 | 95.34 | 100
8 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF KALARIA (ZONE-IA & IB) PIPED WATER SUPPLY SCHEME, BLOCK-CANNING-I,DISTRICT-SOUTH 24 PARGANAS | SM/18676 | Augmentation | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Kalaria W/S Scheme (Zone-IB), Block - Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. (Pump House-III) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000523/2023-2024 | 2077/AD | 07/08/2023 | 21/09/2023 | ASHIS ENTERPRISE | 7.05 | 6.86 | 97.26 | 100
9 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF KALARIA (ZONE-IA & IB) PIPED WATER SUPPLY SCHEME, BLOCK-CANNING-I,DISTRICT-SOUTH 24 PARGANAS | SM/18676 | Augmentation | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Kalaria W/S Scheme (Zone-IB), Block - Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-I] | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000520/2023-2024 | 2075/AD | 07/08/2023 | 21/09/2023 | S.M. ENTERPRISE | 7.33 | 7.16 | 97.69 | 100
10 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF KALARIA (ZONE-IA & IB) PIPED WATER SUPPLY SCHEME, BLOCK-CANNING-I,DISTRICT-SOUTH 24 PARGANAS | SM/18676 | Augmentation | Supply & installation of LED board at Zone-I B PH-I of Kalaria water supply scheme under South 24 Pgs Mechanical Division PHE Dte.[ Block- [ Block- Canning-I ] | Assistant Engineer | Junior Engineer | ORD/002426/2023-2024 | 371/SMSD | 21/03/2024 | 05/04/2024 | KUSHANI ENTERPRISES | 0.39 | 0.39 | 100 | 100
11 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF KALARIA (ZONE-IA & IB) PIPED WATER SUPPLY SCHEME, BLOCK-CANNING-I,DISTRICT-SOUTH 24 PARGANAS | SM/18676 | Augmentation | Supply & installation of LED board at Zone-I A PH-I & 2 of Kalaria water supply scheme under South 24 Pgs Mechanical Division PHE Dte.[ Block- Canning-I ] | Assistant Engineer | Junior Engineer | ORD/002428/2023-2024 | 372/SMSD | 21/03/2024 | 05/04/2024 | S.B.ENTERPRISE | 0.78 | 0.78 | 100 | 100
12 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF KALARIA (ZONE-IA & IB) PIPED WATER SUPPLY SCHEME, BLOCK-CANNING-I,DISTRICT-SOUTH 24 PARGANAS | SM/18676 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/03869/2023-2024 | BP-2023-24-396 | 02/12/2023 | 02/12/2023 | WBSEDCL | 4.09 | 0 | 0 | 0
13 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF KALARIA (ZONE-IA & IB) PIPED WATER SUPPLY SCHEME, BLOCK-CANNING-I,DISTRICT-SOUTH 24 PARGANAS | SM/18676 | Augmentation | Quotation for 25 KVA DTR Shifting at Kalaria Zone-IA, PH-2 Water supply scheme under canning-I block. Reference ID-860304112. Application ID-100000111622. |  |  | BILL/00648/2024-2025 | BP-2024-25-154 | 10/07/2024 | 10/07/2024 | WBSEDCL | 1.81 | 0 | 0 | 0
14 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF KALARIA (ZONE-IA & IB) PIPED WATER SUPPLY SCHEME, BLOCK-CANNING-I,DISTRICT-SOUTH 24 PARGANAS | SM/18676 | Augmentation | Laying of Distribution System, Providing Functional Household Tap Connection (FHTC) etc. of Ground Water Based Augmentation Piped Water Supply Scheme for Kalaria (Zone-IB), Block-Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. [No. of FHTC = 1422] (TSM/017465) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000525/2023-2024 | 2141/AD | 09/08/2023 | 30/04/2025 | SUPRITI ENTERPRISE | 270.46 | 216.32 | 79.98 | 85
15 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF KALARIA (ZONE-IA & IB) PIPED WATER SUPPLY SCHEME, BLOCK-CANNING-I,DISTRICT-SOUTH 24 PARGANAS | SM/18676 | Augmentation | Laying of Distribution System of Ground Water Based Augmentation Piped Water Supply Scheme for Kalaria (Zone-IA), Block-Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. (TSM/017465) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000527/2023-2024 | 2142/AD | 09/08/2023 | 30/04/2025 | PUTUL RANI MAITY | 217.06 | 144.36 | 66.51 | 97
16 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF KALARIA (ZONE-IA & IB) PIPED WATER SUPPLY SCHEME, BLOCK-CANNING-I,DISTRICT-SOUTH 24 PARGANAS | SM/18676 | Augmentation | Construction of 23 Nos. different capacity R.C.C OHR (based on Departmental Design & Drawing ) with 20 mtr. staging height including Geo-Technical investigation, foundation, pipeline connection and cost of pipes , specials etc. for augmentation of different piped water supply scheme of Canning-I, Canning-II & Basanti Block under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD,Junior Engineer,1 CSD | ORD/002461/2023-2024 | 1512/AD | 13/03/2024 | 03/11/2025 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LTD | 2624.49 | 0 | 0 | 30
17 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF KALARIA (ZONE-IA & IB) PIPED WATER SUPPLY SCHEME, BLOCK-CANNING-I,DISTRICT-SOUTH 24 PARGANAS | SM/18676 | Augmentation | Hiring of 1 (One) No. Diesel Car / Luxury Taxi for supervision of different works Under JJM at Canning Sub-Division of Alipore Division, PHE Dte. for 1 (one) Year from the issuance of work order. (Perid from 16.03.2025 to 14.03.2026) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/003373/2024-2025 | 309/CSD | 13/03/2025 | 13/03/2026 | SAILEN CHANDRA DAS | 4.8 | 0 | 0 | 0
18 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF KALARIA (ZONE-IA & IB) PIPED WATER SUPPLY SCHEME, BLOCK-CANNING-I,DISTRICT-SOUTH 24 PARGANAS | SM/18676 | Augmentation | Hiring of Diesel Car / Luxury Taxi for official use of Assistant Engineer, Canning Sub-Division, PHE Dte. for the period from 01.03.2024 to 15.03.2024 | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/003235/2023-2024 | 1568/CSD | 21/02/2024 | 07/03/2024 | SAILEN CHANDRA DAS | 0.07 | 0 | 0 | 0
19 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF KALARIA (ZONE-IA & IB) PIPED WATER SUPPLY SCHEME, BLOCK-CANNING-I,DISTRICT-SOUTH 24 PARGANAS | SM/18676 | Augmentation | Construction of street stand post and valve chamber, damaged due to widening of road from Piali Station to Nawbhasan More at Kalaria W/S Scheme (Zone-I), Block-Canning-I under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/001029/2022-2023 | 866/CSD | 26/08/2022 | 01/07/2024 | ASHIS ENTERPRISE | 2.53 | 0 | 0 | 100
20 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF KALARIA (ZONE-IA & IB) PIPED WATER SUPPLY SCHEME, BLOCK-CANNING-I,DISTRICT-SOUTH 24 PARGANAS | SM/18676 | Augmentation | Inter connection and rising main with supply of specials of Augmentation of Kalaria (Zone- IB) W/S Scheme, Block-Canning- I under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000492/2023-2024 | 1792/AD | 26/07/2023 | 16/01/2025 | S.B. ENTERPRISE | 8.75 | 3.54 | 40.49 | 100
21 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF KALARIA (ZONE-IA & IB) PIPED WATER SUPPLY SCHEME, BLOCK-CANNING-I,DISTRICT-SOUTH 24 PARGANAS | SM/18676 | Augmentation | Improvement of outdoor illumination arrangement with allied works at Kalaria Zone-1A PH-1 under Canning-I Block water supply scheme under SMD,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002646/2023-2024 | 195/SMSD | 12/02/2024 | 27/02/2024 | PADMA ENGINEERING CO. | 0.89 | 0 | 0 | 100
22 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF KALARIA (ZONE-IA & IB) PIPED WATER SUPPLY SCHEME, BLOCK-CANNING-I,DISTRICT-SOUTH 24 PARGANAS | SM/18676 | Augmentation | Improvement of outdoor illumination arrangement with allied works at Kalaria Zone-1A PH-2 under Canning-I Block water supply scheme under SMD,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002647/2023-2024 | 190/SMSD | 09/02/2024 | 24/02/2024 | PADMA ENGINEERING CO. | 0.89 | 0 | 0 | 100
23 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF KALARIA (ZONE-IA & IB) PIPED WATER SUPPLY SCHEME, BLOCK-CANNING-I,DISTRICT-SOUTH 24 PARGANAS | SM/18676 | Augmentation | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-I) Name of PWSS - Bhaleya, Kalaria (Zone-IA), Kalaria (Zone-IB), Kalaria (Zone-IIA), Kalaria (Zone-IIB), Devis Abad, Duttababur Abad, Bayarsing, Narayangar (Part -B), Narayangar, Bansra (Zone-I), Bansra (Zone-II), Dharmatala (Part-B) and Dharmatala. (For 14 (Fourteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000965/2024-2025 | 1177/CSD | 24/10/2024 | 13/11/2024 | GANGA TUBEWELL AND HARDWARE | 3.37 | 0 | 0 | 100
24 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF KALARIA (ZONE-IA & IB) PIPED WATER SUPPLY SCHEME, BLOCK-CANNING-I,DISTRICT-SOUTH 24 PARGANAS | SM/18676 | Augmentation | Hiring of 1 (One) No. Diesel Car / Luxury Taxi for supervision of different works Under JJM at Canning Sub-Division of Alipore Division, PHE Dte. for 1 (one) Year from the issuance of work order. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/003141/2023-2024 | 1701/CSD | 15/03/2024 | 15/03/2025 | SAILEN CHANDRA DAS | 4.8 | 0 | 0 | 100
Total | [13 empty] | 3465.23 | 542.37 | 15.65