## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED KAKDWIP PIPE WATER SUPPLY SCHEME, BLOCK KAKDWIP UNDER ALIPORE DIVISION, DISTRICT SOUTH 24 PARGANAS. | SM/18682 | New | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (Kakdwip PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000643/2023-2024 | 2035/AD | 05/08/2023 | 19/09/2023 | LEMNISCATE | 12.08 | 0 | 0 | 100
2 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED KAKDWIP PIPE WATER SUPPLY SCHEME, BLOCK KAKDWIP UNDER ALIPORE DIVISION, DISTRICT SOUTH 24 PARGANAS. | SM/18682 | New | Material Requisition To Resource Division |  |  | RTOR000454/2023-2024 | 4718/AD | 18/12/2023 | 18/12/2023 | Resource Division | 40.56 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED KAKDWIP PIPE WATER SUPPLY SCHEME, BLOCK KAKDWIP UNDER ALIPORE DIVISION, DISTRICT SOUTH 24 PARGANAS. | SM/18682 | New | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Kakdwip Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) [No. of FHTC = 2582] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000194/2023-2024 | 2103/AD | 08/08/2023 | 06/11/2023 | M/S. JHARNA ENTERPRISE | 259.33 | 0 | 0 | 40
4 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED KAKDWIP PIPE WATER SUPPLY SCHEME, BLOCK KAKDWIP UNDER ALIPORE DIVISION, DISTRICT SOUTH 24 PARGANAS. | SM/18682 | New | Sinking of 03 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st, 2nd and 3rd Tubewell Site of Kakdwip W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000421/2023-2024 | 2152/AD | 09/08/2023 | 08/10/2023 | IQBAL CONSTRUCTION | 57.38 | 0 | 0 | 66
5 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED KAKDWIP PIPE WATER SUPPLY SCHEME, BLOCK KAKDWIP UNDER ALIPORE DIVISION, DISTRICT SOUTH 24 PARGANAS. | SM/18682 | New | Hiring of 1 (One) No. Diesel Car / Luxury Taxi for supervision of different works Under JJM at Kakdwip, Namkhana, Sagar and Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, PHE Dte. for the period from 01.09.2023 to 29.02.2024. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/001385/2023-2024 | 379/KSD | 17/08/2023 | 17/02/2024 | ANAMIKA BERA | 2.4 | 0 | 0 | 100
6 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED KAKDWIP PIPE WATER SUPPLY SCHEME, BLOCK KAKDWIP UNDER ALIPORE DIVISION, DISTRICT SOUTH 24 PARGANAS. | SM/18682 | New | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Kakdwip Water Supply Scheme, Block - Kakdwip under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-C) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/002286/2023-2024 | 1003/AD | 16/02/2024 | 16/05/2024 | M/S. JHARNA ENTERPRISE | 128.24 | 0 | 0 | 60
7 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED KAKDWIP PIPE WATER SUPPLY SCHEME, BLOCK KAKDWIP UNDER ALIPORE DIVISION, DISTRICT SOUTH 24 PARGANAS. | SM/18682 | New | Construction, placing and fixing of FHTC Platform at every individual beneficiary, pump connections etc for Kakdwip W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/18682) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000302/2024-2025 | 2709/AD | 24/06/2024 | 23/08/2024 | M/S. JHARNA ENTERPRISE | 163.39 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS | Kakdwip | S24 Pgns Mechanical | GROUND WATER BASED KAKDWIP PIPE WATER SUPPLY SCHEME, BLOCK KAKDWIP UNDER ALIPORE DIVISION, DISTRICT SOUTH 24 PARGANAS. | SM/18682 | New | Supply & installation of LED board at P.H. No-1 & 2 of Kakdwip water supply scheme, under South 24-Pgs Mechanical Division PHE Dte.[Block-Kakdwip] | Assistant Engineer -I | Junior Engineer | ORD/000562/2024-2025 | 794-AE-I-SMD | 11/06/2024 | 26/06/2024 | PS & ASSOCIATES | 0.78 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED KAKDWIP PIPE WATER SUPPLY SCHEME, BLOCK KAKDWIP UNDER ALIPORE DIVISION, DISTRICT SOUTH 24 PARGANAS. | SM/18682 | New | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Kakdwip W/S scheme, Block : Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/18682) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000415/2024-2025 | 3066/AD | 25/07/2024 | 08/09/2024 | M/S. JHARNA ENTERPRISE | 28.68 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS | Kakdwip | S24 Pgns Mechanical | GROUND WATER BASED KAKDWIP PIPE WATER SUPPLY SCHEME, BLOCK KAKDWIP UNDER ALIPORE DIVISION, DISTRICT SOUTH 24 PARGANAS. | SM/18682 | New | Improvement of outdoor illumination arrangement with allied works at PH-1 of Kakdwip W/S Scheme under JJM under South 24-Pgs Mechanical Division,PHE Dte. [Block-Kakdwip] | Assistant Engineer -I | Junior Engineer | ORD/000366/2024-2025 | 634/AE-I/SMD | 23/04/2024 | 08/05/2024 | KARUNAMOY ENGINEERING | 0.89 | 0 | 0 | 0
11 | SOUTH 24 PARGANAS | Kakdwip | S24 Pgns Mechanical | GROUND WATER BASED KAKDWIP PIPE WATER SUPPLY SCHEME, BLOCK KAKDWIP UNDER ALIPORE DIVISION, DISTRICT SOUTH 24 PARGANAS. | SM/18682 | New | Improvement of outdoor illumination arrangement with allied works at PH-2 of Kakdwip W/S Scheme under JJM under South 24-Pgs Mechanical Division,PHE Dte. [Block-Kakdwip] | Assistant Engineer -I | Junior Engineer | ORD/000367/2024-2025 | 633/AE-I/SMD | 23/04/2024 | 08/05/2024 | KARUNAMOY ENGINEERING | 0.89 | 0 | 0 | 0
12 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED KAKDWIP PIPE WATER SUPPLY SCHEME, BLOCK KAKDWIP UNDER ALIPORE DIVISION, DISTRICT SOUTH 24 PARGANAS. | SM/18682 | New | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 3rd Tubewell Site of Kakdwip W/S scheme, Block : Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000443/2024-2025 | 3294/AD | 09/08/2024 | 08/09/2024 | KHAN CONSTRUCTION (HASNABAD) | 9.31 | 0 | 0 | 0
13 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED KAKDWIP PIPE WATER SUPPLY SCHEME, BLOCK KAKDWIP UNDER ALIPORE DIVISION, DISTRICT SOUTH 24 PARGANAS. | SM/18682 | New | Making and fixing of permanent display board at headwork site of Mrinalnagar, Koaberia, Hesamabad, Kakdwip, Kakdwip & Akshaynagar Zone - I & II PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/002144/2023-2024 | 944/KSD | 19/12/2023 | 24/12/2023 | M/S B. ENTERPRISE | 0.94 | 0 | 0 | 100
14 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED KAKDWIP PIPE WATER SUPPLY SCHEME, BLOCK KAKDWIP UNDER ALIPORE DIVISION, DISTRICT SOUTH 24 PARGANAS. | SM/18682 | New | Preparation of design (Pile and Pile Cap) drawing for foundation of 600 cum. capacity OHR of Kakdwip PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/002233/2023-2024 | 719/KSD | 01/12/2023 | 11/12/2023 | CONSTEEL CONSULTANCY & SERVICES | 0.48 | 0 | 0 | 100
15 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED KAKDWIP PIPE WATER SUPPLY SCHEME, BLOCK KAKDWIP UNDER ALIPORE DIVISION, DISTRICT SOUTH 24 PARGANAS. | SM/18682 | New | Material Requisition To Resource Division |  |  | RTOR000590/2023-2024 | 89/AD | 03/01/2024 | 03/01/2024 | Resource Division | 14.85 | 0 | 0 | 0
16 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED KAKDWIP PIPE WATER SUPPLY SCHEME, BLOCK KAKDWIP UNDER ALIPORE DIVISION, DISTRICT SOUTH 24 PARGANAS. | SM/18682 | New | Material Requisition To Resource Division |  |  | RTOR000821/2023-2024 | 666/AD | 30/01/2024 | 30/01/2024 | Resource Division | 15.91 | 0 | 0 | 0
17 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED KAKDWIP PIPE WATER SUPPLY SCHEME, BLOCK KAKDWIP UNDER ALIPORE DIVISION, DISTRICT SOUTH 24 PARGANAS. | SM/18682 | New | Material Requisition To Resource Division |  |  | RTOR000908/2023-2024 | 896/AD | 07/02/2024 | 07/02/2024 | Resource Division | 0.75 | 0 | 0 | 0
18 | SOUTH 24 PARGANAS | Kakdwip | S24 Pgns Mechanical | GROUND WATER BASED KAKDWIP PIPE WATER SUPPLY SCHEME, BLOCK KAKDWIP UNDER ALIPORE DIVISION, DISTRICT SOUTH 24 PARGANAS. | SM/18682 | New | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/05173/2023-2024 | BP-2023-24-591 | 13/03/2024 | 13/03/2024 | WBSEDCL | 6.83 | 0 | 0 | 0
19 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED KAKDWIP PIPE WATER SUPPLY SCHEME, BLOCK KAKDWIP UNDER ALIPORE DIVISION, DISTRICT SOUTH 24 PARGANAS. | SM/18682 | New | Construction of 600 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of foundation after soil investagation including O & M of Laying distribution, Rising Main & FHTC for 1 year after completion of FHTC works for Kakdwip Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) [No. of FHTC = 2500] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000545/2023-2024 | 2211/AD | 10/08/2023 | 26/01/2026 | M/S. JHARNA ENTERPRISE | 369.23 | 0 | 0 | 70
20 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED KAKDWIP PIPE WATER SUPPLY SCHEME, BLOCK KAKDWIP UNDER ALIPORE DIVISION, DISTRICT SOUTH 24 PARGANAS. | SM/18682 | New | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Kakdwip W/S scheme, Block : Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/18682) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000470/2024-2025 | 3456/AD | 23/08/2024 | 17/09/2025 | JOYJIT MUKHERJEE | 8.93 | 0 | 0 | 100
21 | SOUTH 24 PARGANAS | Kakdwip | S24 Pgns Mechanical | GROUND WATER BASED KAKDWIP PIPE WATER SUPPLY SCHEME, BLOCK KAKDWIP UNDER ALIPORE DIVISION, DISTRICT SOUTH 24 PARGANAS. | SM/18682 | New | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 3 for Augmentation of Kakdwip water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block:Kakdwip]. (SM/18682) | Assistant Engineer -II | Junior Engineer | ORD/000026/2025-2026 | 1025/SMD | 16/04/2025 | 15/07/2025 | NITESH MANAGEMENT | 12.4 | 0 | 0 | 0
Total | [13 empty] | 1134.25 | 0 | 0