## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | UTTAR CHANDANPIRI & ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18683 | New | Laying distribution system, Functional Household Tap Connection (FHTC) to all households and Construction 02 nos. Pump House (5.40m. x 3.60m) for Uttar Chandanpiri Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000581/2023-2024 | 2268/AD | 14/08/2023 | 28/09/2023 | NATURAL RESOURCES CONSORTIUM | 60.84 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | UTTAR CHANDANPIRI & ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18683 | New | Material Requisition To Resource Division |  |  | RTOR000474/2023-2024 | 4779/AD | 19/12/2023 | 19/12/2023 | Resource Division | 16.05 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | UTTAR CHANDANPIRI & ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18683 | New | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Uttar Chandanpiri Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-C) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000568/2023-2024 | 2258/AD | 14/08/2023 | 13/10/2023 | M/S ARPAN ENTERPRISE | 16.9 | 9.26 | 54.77 | 70
4 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | UTTAR CHANDANPIRI & ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18683 | New | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Uttar Chandanpiri Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-D) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000569/2023-2024 | 2084/AD | 07/08/2023 | 06/09/2023 | AROMA INC | 12.09 | 5.93 | 49.04 | 50
5 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | UTTAR CHANDANPIRI & ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18683 | New | Construction of 1 nos. Pump House of size 5.40 mtr. x 3.60 mtr. at 3rd tubewell Site for Uttar Chandanpiri Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/18683) (2nd call) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000467/2024-2025 | 3462/AD | 23/08/2024 | 07/10/2024 | M/S R.K.ENTERPRISE | 5.62 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | UTTAR CHANDANPIRI & ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18683 | New | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Uttar Chandanpiri W/S Scheme, Block - Namkhana under JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/18683) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000160/2024-2025 | 2511/AD | 15/06/2024 | 30/07/2024 | DEV AND COMPANY | 40.82 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | UTTAR CHANDANPIRI & ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18683 | New | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Uttar Chandanpiri W/S scheme, Block : Namkhana under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/18683) (2nd Call) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000509/2024-2025 | 3609/AD | 06/09/2024 | 06/10/2024 | KAMALA ENTERPRISE | 9.61 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS | Namkhana | S24 Pgns Mechanical | UTTAR CHANDANPIRI & ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18683 | New | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 &2 of Uttar Chandanpiri water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Namkhana] | Assistant Engineer -I | Junior Engineer | ORD/001964/2023-2024 | 4870/SMD | 14/12/2023 | 14/03/2024 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 22.2 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | UTTAR CHANDANPIRI & ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18683 | New | Construction of 1 no. Pump House of size 5.40 mtr. x 3.60 mtr. at 4th tubewell Site for Uttar Chandanpiri Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/18683) (2nd Call) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000468/2024-2025 | 3463/AD | 23/08/2024 | 07/10/2024 | M/S. TARA MAA CONSTRUCTION | 5.6 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | UTTAR CHANDANPIRI & ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18683 | New | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 3rd Tubewell Site of Uttar Chandanpiri W/S scheme, Block : Namkhana under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/18683) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000228/2024-2025 | 2558/AD | 18/06/2024 | 18/07/2024 | M/S R.K.ENTERPRISE | 9.66 | 0 | 0 | 0
11 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | UTTAR CHANDANPIRI & ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18683 | New | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 4th Tubewell Site of Uttar Chandanpiri W/S scheme, Block : Namkhana under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/18683) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000229/2024-2025 | 2559/AD | 18/06/2024 | 18/07/2024 | PRADIP KUMAR MONDAL | 9.65 | 0 | 0 | 0
12 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | UTTAR CHANDANPIRI & ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18683 | New | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Uttar Chandanpiri W/S scheme, Block : Namkhana under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/18683) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000221/2024-2025 | 2604/AD | 19/06/2024 | 03/08/2024 | MODERN CONSTRUCTION | 28.84 | 0 | 0 | 0
13 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | UTTAR CHANDANPIRI & ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18683 | New | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Uttar Chandanpiri Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000571/2023-2024 | 2259/AD | 14/08/2023 | 28/09/2023 | AQUATECH ENGINEERS | 36.71 | 36.7 | 99.98 | 50
14 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | UTTAR CHANDANPIRI & ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18683 | New | Making and fixing of permanent display board at headwork site of Sibnagar Abad, Debnagar, Narayanganj, Dwariknagar, Namkhana, Uttar Chandanpiri PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/002130/2023-2024 | 936/KSD | 19/12/2023 | 24/12/2023 | ANANTA KUMAR GIRI | 0.94 | 0.16 | 16.5 | 100
15 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | UTTAR CHANDANPIRI & ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18683 | New | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Uttar Chandanpiri PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/002618/2023-2024 | 895/KSD | 18/12/2023 | 23/12/2023 | CONSTEEL CONSULTANCY & SERVICES | 0.48 | 0.48 | 100 | 100
16 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | UTTAR CHANDANPIRI & ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18683 | New | Material Requisition To Resource Division |  |  | RTOR000561/2023-2024 | 49/AD | 03/01/2024 | 03/01/2024 | Resource Division | 13.23 | 0 | 0 | 0
17 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | UTTAR CHANDANPIRI & ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18683 | New | Material Requisition To Resource Division |  |  | RTOR000978/2023-2024 | 1771/AD | 27/03/2024 | 27/03/2024 | Resource Division | 38.31 | 0 | 0 | 0
18 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | UTTAR CHANDANPIRI & ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18683 | New | Material Requisition To Resource Division |  |  | RTOR000790/2023-2024 | 635/AD | 30/01/2024 | 30/01/2024 | Resource Division | 0.5 | 0 | 0 | 0
19 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | UTTAR CHANDANPIRI & ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18683 | New | Construction of 250 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Uttar Chandanpiri Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) [No. of FHTC = 1577] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000633/2023-2024 | 2451/AD | 23/08/2023 | 01/04/2026 | SOMA CONSTRUCTION | 486 | 315.3 | 64.88 | 60
20 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | UTTAR CHANDANPIRI & ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18683 | New | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections etc. at Uttar Chandanpiri PWSS, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/18683) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000357/2024-2025 | 2841/AD | 05/07/2024 | 01/04/2026 | SOMA CONSTRUCTION | 117.46 | 0 | 0 | 50
Total | [13 empty] | 931.52 | 367.82 | 39.49