## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | DAKSHIN DURGAPUR & ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION PHE DTE. | SM/18684 | New | Laying distribution system, Functional Household Tap Connection (FHTC) to all households of Dakshin Durgapur Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-D) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000699/2023-2024 | 2527/AD | 28/08/2023 | 27/09/2023 | ABONTICA ENTERPRISE | 15.52 | 9.07 | 58.47 | 60
2 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | DAKSHIN DURGAPUR & ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION PHE DTE. | SM/18684 | New | Construction of 400 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Dakshin Durgapur Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000623/2023-2024 | 2432/AD | 22/08/2023 | 01/01/2026 | H T R CONSTRUCTION | 614.68 | 409.65 | 66.64 | 75
3 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | DAKSHIN DURGAPUR & ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION PHE DTE. | SM/18684 | New | Laying distribution system, Functional Household Tap Connection (FHTC) to all households of Dakshin Durgapur Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-G) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000705/2023-2024 | 2530/AD | 28/08/2023 | 27/09/2023 | AROMA INC | 13.31 | 7.89 | 59.28 | 20
4 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | DAKSHIN DURGAPUR & ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION PHE DTE. | SM/18684 | New | Laying distribution system, Functional Household Tap Connection (FHTC) to all households of Dakshin Durgapur Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-E) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000700/2023-2024 | 2528/AD | 28/08/2023 | 27/09/2023 | SWASTIK CONSTRUCTION | 14.73 | 11.34 | 76.98 | 25
5 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | DAKSHIN DURGAPUR & ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION PHE DTE. | SM/18684 | New | Laying distribution system, Functional Household Tap Connection (FHTC) to all households of Dakshin Durgapur Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-F) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000702/2023-2024 | 2529/AD | 28/08/2023 | 27/09/2023 | UNIVERSAL CONSTRUCTION (ULUBERIA) | 13.71 | 10.41 | 75.91 | 30
6 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | DAKSHIN DURGAPUR & ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION PHE DTE. | SM/18684 | New | Laying distribution system, Functional Household Tap Connection (FHTC) to all households including construction of 01 no. Pump House of Dakshin Durgapur Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-C) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/001451/2023-2024 | 4688/AD | 18/12/2023 | 16/04/2024 | MOINAK POREL | 91.33 | 81.01 | 88.7 | 40
7 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | DAKSHIN DURGAPUR & ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION PHE DTE. | SM/18684 | New | Laying distribution system, Functional Household Tap Connection (FHTC) to all households including construction of 01 no. Pump House of Dakshin Durgapur Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/001450/2023-2024 | 4687/AD | 18/12/2023 | 16/04/2024 | M/S. P. GIRI ENTERPRISE | 91.01 | 80.61 | 88.58 | 45
8 | SOUTH 24 PARGANAS | Namkhana | S24 Pgns Mechanical | DAKSHIN DURGAPUR & ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION PHE DTE. | SM/18684 | New | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 &2 of Dakshin Durgapur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Namkhana] | Assistant Engineer -I,Assistant Engineer -II | Junior Engineer | ORD/002753/2023-2024 | 4871/SMD | 14/12/2023 | 30/06/2025 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 22.19 | 0 | 0 | 40
9 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | DAKSHIN DURGAPUR & ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION PHE DTE. | SM/18684 | New | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households of Dakshin Durgapur Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-J) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000711/2023-2024 | 2533/AD | 28/08/2023 | 27/09/2023 | M/S SNEHALATA ENTERPRISE | 7.83 | 7.83 | 99.98 | 80
10 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | DAKSHIN DURGAPUR & ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION PHE DTE. | SM/18684 | New | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Dakshin Durgapur Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000573/2023-2024 | 2260/AD | 14/08/2023 | 28/09/2023 | MEGA SOLAR ENERGY | 36.66 | 35.96 | 98.1 | 100
11 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | DAKSHIN DURGAPUR & ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION PHE DTE. | SM/18684 | New | Laying distribution system, Functional Household Tap Connection (FHTC) to all households of Dakshin Durgapur Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-H) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000707/2023-2024 | 2531/AD | 28/08/2023 | 27/09/2023 | SAB ENGINEERING WORKS | 13.11 | 12.98 | 98.99 | 20
12 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | DAKSHIN DURGAPUR & ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION PHE DTE. | SM/18684 | New | Making and fixing of permanent display board at headwork site of Nadabhanga, Patibania, Dakshin Durgapur, Rajnagar, Budhakhali Zone - I (Part - I & II) PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/002128/2023-2024 | 935/KSD | 19/12/2023 | 24/12/2023 | M/S B. ENTERPRISE | 0.95 | 0.16 | 16.65 | 90
13 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | DAKSHIN DURGAPUR & ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION PHE DTE. | SM/18684 | New | Preparation of design (Pile and Pile Cap) drawing for foundation of 400 cum. capacity OHR of Dakshin Durgapur PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/002217/2023-2024 | 874/KSD | 14/12/2023 | 19/12/2023 | CONSTEEL CONSULTANCY & SERVICES | 0.48 | 0.48 | 100 | 100
14 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | DAKSHIN DURGAPUR & ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION PHE DTE. | SM/18684 | New | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households of Dakshin Durgapur Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-I) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000708/2023-2024 | 2532/AD | 28/08/2023 | 27/09/2023 | SUNIL ENTERPRISE | 8.16 | 8.13 | 99.69 | 90
15 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | DAKSHIN DURGAPUR & ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION PHE DTE. | SM/18684 | New | Material Requisition To Resource Division |  |  | RTOR000475/2023-2024 | 4780/AD | 19/12/2023 | 19/12/2023 | Resource Division | 26.31 | 0 | 0 | 0
16 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | DAKSHIN DURGAPUR & ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION PHE DTE. | SM/18684 | New | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 3rd and 4th Tubewell Site of Dakshin Durgapur W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/001837/2023-2024 | 125/AD | 05/01/2024 | 19/02/2024 | MEHAI TECHNOLOGY LIMITED | 39.91 | 0 | 0 | 40
17 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | DAKSHIN DURGAPUR & ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION PHE DTE. | SM/18684 | New | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 4th Tubewell Site of Dakshin Durgapur W/S scheme, Block : Namkhan under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/18684) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000390/2024-2025 | 3058/AD | 25/07/2024 | 24/08/2024 | SWASTIK CONSTRUCTION | 9.59 | 0 | 0 | 0
18 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | DAKSHIN DURGAPUR & ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION PHE DTE. | SM/18684 | New | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connection etc. for Dakshin Durgapur W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/18684) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/001044/2024-2025 | 4965/AD | 04/12/2024 | 30/09/2025 | H T R CONSTRUCTION | 74.15 | 0 | 0 | 20
19 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | DAKSHIN DURGAPUR & ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION PHE DTE. | SM/18684 | New | Continuation order for the work of Construction of 400 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Dakshin Durgapur Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000424/2024-2025 | 3202/AD | 01/08/2024 | 29/03/2025 | H T R CONSTRUCTION | 47.47 | 0 | 0 | 30
20 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | DAKSHIN DURGAPUR & ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION PHE DTE. | SM/18684 | New | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Dakshin Durgapur W/S scheme, Block - Namkhana under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/18684) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000223/2024-2025 | 2606/AD | 19/06/2024 | 19/07/2024 | NEPAL CHANDRA PRADHAN | 9.59 | 0 | 0 | 0
21 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | DAKSHIN DURGAPUR & ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION PHE DTE. | SM/18684 | New | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 3rd Tubewell Site of Dakshin Durgapur W/S scheme, Block : Namkhan under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/18684) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000389/2024-2025 | 3057/AD | 25/07/2024 | 24/08/2024 | M/S BABUSONA ENTERPRISE | 9.58 | 0 | 0 | 0
22 | SOUTH 24 PARGANAS | Namkhana | S24 Pgns Mechanical | DAKSHIN DURGAPUR & ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION PHE DTE. | SM/18684 | New | Improvement of outdoor illumination arrangement with allied works at PH-1 of Dakshin Durgapur W/S Scheme under JJM under South 24-Pgs Mechanical Division,PHE Dte. [Block-Namkhana] (SM/18684) | Assistant Engineer -I,Assistant Engineer -II | Junior Engineer | ORD/002214/2024-2025 | 1347-AE-II-SMD | 14/11/2024 | 29/11/2024 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 0.9 | 0 | 0 | 100
23 | SOUTH 24 PARGANAS | Namkhana | S24 Pgns Mechanical | DAKSHIN DURGAPUR & ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION PHE DTE. | SM/18684 | New | Improvement of outdoor illumination arrangement with allied works at PH-2 of Dakshin Durgapur W/S Scheme under JJM under South 24-Pgs Mechanical Division,PHE Dte. [Block-Namkhana] (SM/18684) | Assistant Engineer -I,Assistant Engineer -II | Junior Engineer | ORD/002215/2024-2025 | 1348-AE-II-SMD | 14/11/2024 | 29/11/2024 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 0.9 | 0 | 0 | 100
24 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | DAKSHIN DURGAPUR & ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION PHE DTE. | SM/18684 | New | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Dakshin Durgapur W/S Scheme, Block - Namkhana under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/18684) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000222/2024-2025 | 2605/AD | 19/06/2024 | 30/01/2025 | M/S KHAJABABA ENTERPRISE | 28.53 | 6.3 | 22.08 | 95
25 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | DAKSHIN DURGAPUR & ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION PHE DTE. | SM/18684 | New | Material Requisition To Resource Division |  |  | RTOR000910/2023-2024 | 893/AD | 07/02/2024 | 07/02/2024 | Resource Division | 10.67 | 0 | 0 | 0
26 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | DAKSHIN DURGAPUR & ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION PHE DTE. | SM/18684 | New | Material Requisition To Resource Division |  |  | RTOR000979/2023-2024 | 1772/AD | 27/03/2024 | 27/03/2024 | Resource Division | 14.69 | 0 | 0 | 0
27 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | DAKSHIN DURGAPUR & ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION PHE DTE. | SM/18684 | New | Material Requisition To Resource Division |  |  | RTOR000793/2023-2024 | 638/AD | 30/01/2024 | 30/01/2024 | Resource Division | 18.6 | 0 | 0 | 0
28 | SOUTH 24 PARGANAS | Namkhana | S24 Pgns Mechanical | DAKSHIN DURGAPUR & ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION PHE DTE. | SM/18684 | New | Payment for New Service connection of Dakshin Durgapur PH-1 W/S Scheme JL No- 007, Khatian-2375, Plot-2482, Mouza Dakshin Durgapur Application No:- 1007514926 Reference ID:- 106460089 |  |  | BILL/00207/2024-2025 | BP-2024-25-65 | 16/05/2024 | 16/05/2024 | WBSEDCL | 5.31 | 0 | 0 | 0
29 | SOUTH 24 PARGANAS | Namkhana | S24 Pgns Mechanical | DAKSHIN DURGAPUR & ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION PHE DTE. | SM/18684 | New | Payment for New Service connection of Dakshin Durgapur PH-2 W/S Scheme Mouza- Dakshin Durgapur, JL No- 007, Khatian- 3270, Plot- 1425 Application No:- 1007551348 Reference ID:- 106484817 |  |  | BILL/00208/2024-2025 | BP-2024-25-65 | 16/05/2024 | 16/05/2024 | WBSEDCL | 3.36 | 0 | 0 | 0
Total | [13 empty] | 1243.23 | 681.82 | 54.84