## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED DAKSHIN GANGADHARPUR , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/18697 | Augmentation | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Dakshin Gangadharpur Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-C) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000577/2023-2024 | 2263/AD | 14/08/2023 | 13/09/2023 | M/S. SIKHA ENTERPRISE | 30.66 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED DAKSHIN GANGADHARPUR , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/18697 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H-1, Zone- I of Augmentation of Dakshin Gangadarpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Patharpratima] | Assistant Engineer -I | Junior Engineer | ORD/000758/2023-2024 | 2688/SMD | 16/08/2023 | 14/11/2023 | MAA TARA CONSTRUCTION | 10.52 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED DAKSHIN GANGADHARPUR , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/18697 | Augmentation | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (Dakshin Gangadharpur PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000641/2023-2024 | 2033/AD | 05/08/2023 | 19/09/2023 | INDRANIL DUTTA & ASSOCIATES | 8.84 | 0 | 0 | 100
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED DAKSHIN GANGADHARPUR , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/18697 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000308/2023-2024 | 3117/AD | 29/09/2023 | 29/09/2023 | Resource Division | 0.3 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED DAKSHIN GANGADHARPUR , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/18697 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000304/2023-2024 | 3099/AD | 28/09/2023 | 28/09/2023 | Resource Division | 133.07 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED DAKSHIN GANGADHARPUR , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/18697 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000526/2023-2024 | 4986/AD | 26/12/2023 | 26/12/2023 | Resource Division | 16.64 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED DAKSHIN GANGADHARPUR , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/18697 | Augmentation | Construction of 700 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Laying distribution system, Rising Main, construction of 1 no. 5.40m x 3.60m. Pump House, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Dakshin Gangadharpur Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000532/2023-2024 | 3740/AD | 03/11/2023 | 29/08/2024 | J.D.J. ENTERPRISE (A UNIT OF JDJ TRADERS PVT. LTD.) | 489.98 | 0 | 0 | 20
8 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED DAKSHIN GANGADHARPUR , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/18697 | Augmentation | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections etc at Dakshin Gangadharpur PWSS, Block - Patharpratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/18697) (Part-B) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000359/2024-2025 | 2872/AD | 08/07/2024 | 21/09/2024 | SUPER SKILL | 178.53 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED DAKSHIN GANGADHARPUR , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/18697 | Augmentation | Preparation of design (Pile and Pile Cap) drawing for foundation of 700 cum. capacity OHR of Dakshin Gangadharpur PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/002071/2023-2024 | 767(A)/KSD | 08/12/2023 | 13/12/2023 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 0 | 100
10 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED DAKSHIN GANGADHARPUR , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/18697 | Augmentation | Making and fixing of permanent display board at headwork site of Bhajna, Dakshin Madhusudanpur, Ramdebpur, Dakshin Gangadharpur, Gayadham, Indraprastha PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/002089/2023-2024 | 921/KSD | 19/12/2023 | 24/12/2023 | M/S B. ENTERPRISE | 0.95 | 0 | 0 | 100
11 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED DAKSHIN GANGADHARPUR , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/18697 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000568/2023-2024 | 79/AD | 03/01/2024 | 03/01/2024 | Resource Division | 5.35 | 0 | 0 | 0
12 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED DAKSHIN GANGADHARPUR , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/18697 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000767/2023-2024 | 601/AD | 29/01/2024 | 29/01/2024 | Resource Division | 5.56 | 0 | 0 | 0
13 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED DAKSHIN GANGADHARPUR , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/18697 | Augmentation | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Dakshin Gangadharpur Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) [No. of FHTC = 400] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000533/2023-2024 | 2146/AD | 09/08/2023 | 01/04/2025 | SUPER SKILL | 312.7 | 0 | 0 | 30
14 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED DAKSHIN GANGADHARPUR , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/18697 | Augmentation | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Augmentation at Dakshin Gangadharpur W/S Scheme, Block - Pathar Pratima for implementing of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000556/2023-2024 | 2238/AD | 11/08/2023 | 16/12/2024 | S.M. ENTERPRISE | 18.81 | 0 | 0 | 100
Total | [13 empty] | 1212.4 | 0 | 0