## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION FOR GROUND WATER BASED HARIPUR (ZONE- I & II), PIPED WATER SUPPLY SCHEME, Phase-B, UNDER ALIPORE DIVISION, BLOCK : NAMKHANA, DISTRICT : SOUTH 24 PARGANAS | SM/18698 | Augmentation | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (Haripur (Zone - I & II)) including Functional Household Tap Connection (FHTC) for implementation of JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000642/2023-2024 | 2034/AD | 05/08/2023 | 19/09/2023 | M/S R.DUTTA & CO. | 7.87 | 7.87 | 100 | 100
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION FOR GROUND WATER BASED HARIPUR (ZONE- I & II), PIPED WATER SUPPLY SCHEME, Phase-B, UNDER ALIPORE DIVISION, BLOCK : NAMKHANA, DISTRICT : SOUTH 24 PARGANAS | SM/18698 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000490/2023-2024 | 4789/AD | 19/12/2023 | 19/12/2023 | Resource Division | 29.51 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION FOR GROUND WATER BASED HARIPUR (ZONE- I & II), PIPED WATER SUPPLY SCHEME, Phase-B, UNDER ALIPORE DIVISION, BLOCK : NAMKHANA, DISTRICT : SOUTH 24 PARGANAS | SM/18698 | Augmentation | Construction of 250 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with 1 no. Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Haripur (Zone-I & II) Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-II) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000531/2023-2024 | 2144/AD | 09/08/2023 | 31/12/2025 | MALLICK ENTERPRISE | 286.52 | 135.98 | 47.46 | 80
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION FOR GROUND WATER BASED HARIPUR (ZONE- I & II), PIPED WATER SUPPLY SCHEME, Phase-B, UNDER ALIPORE DIVISION, BLOCK : NAMKHANA, DISTRICT : SOUTH 24 PARGANAS | SM/18698 | Augmentation | Laying distribution system for Providing FHTC of Haripur (Zone- I and II) W/S Scheme under JJM, Block - Namkhana under Kakdwip Sub Division of Alipore Division, PHED. (Zone-II) (Part-C) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/002127/2023-2024 | 818/AD | 05/02/2024 | 21/03/2024 | JOY GURU TRADING | 43.99 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION FOR GROUND WATER BASED HARIPUR (ZONE- I & II), PIPED WATER SUPPLY SCHEME, Phase-B, UNDER ALIPORE DIVISION, BLOCK : NAMKHANA, DISTRICT : SOUTH 24 PARGANAS | SM/18698 | Augmentation | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Replacement Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 2nd Tubewell Site of Haripur (Zone - I and II) W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-II) (SM/18698) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/002133/2023-2024 | 821/AD | 05/02/2024 | 06/03/2024 | MEGA SOLAR ENERGY | 19.93 | 18.97 | 95.2 | 100
6 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION FOR GROUND WATER BASED HARIPUR (ZONE- I & II), PIPED WATER SUPPLY SCHEME, Phase-B, UNDER ALIPORE DIVISION, BLOCK : NAMKHANA, DISTRICT : SOUTH 24 PARGANAS | SM/18698 | Augmentation | Making and fixing of permanent display board at headwork site of Dakshin Chandranagar, Haripur Zone - I & II, Amarabati PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/002131/2023-2024 | 937/KSD | 19/12/2023 | 24/12/2023 | M/S B. ENTERPRISE | 0.63 | 0.31 | 49.83 | 100
7 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION FOR GROUND WATER BASED HARIPUR (ZONE- I & II), PIPED WATER SUPPLY SCHEME, Phase-B, UNDER ALIPORE DIVISION, BLOCK : NAMKHANA, DISTRICT : SOUTH 24 PARGANAS | SM/18698 | Augmentation | Laying distribution system for Providing FHTC (Retrofitting) of Haripur (Zone- I and II) W/S Scheme under JJM, Block - Namkhana under Kakdwip Sub Division of Alipore Division, PHED. (Zone-II) (Part-B) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/002125/2023-2024 | 817/AD | 05/02/2024 | 21/03/2024 | ASHIS ENTERPRISE | 40.55 | 39.6 | 97.66 | 50
8 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION FOR GROUND WATER BASED HARIPUR (ZONE- I & II), PIPED WATER SUPPLY SCHEME, Phase-B, UNDER ALIPORE DIVISION, BLOCK : NAMKHANA, DISTRICT : SOUTH 24 PARGANAS | SM/18698 | Augmentation | Preparation of design (Pile and Pile Cap) drawing for foundation of 250 cum. capacity OHR of Haripur (Zone - I & II) PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/002232/2023-2024 | 718/KSD | 01/12/2023 | 11/12/2023 | CONSTEEL CONSULTANCY & SERVICES | 0.48 | 0.48 | 100 | 100
9 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION FOR GROUND WATER BASED HARIPUR (ZONE- I & II), PIPED WATER SUPPLY SCHEME, Phase-B, UNDER ALIPORE DIVISION, BLOCK : NAMKHANA, DISTRICT : SOUTH 24 PARGANAS | SM/18698 | Augmentation | Additional Work related to Supply & delivery of Submersible pumping machinery along with allied accessories at Augmentation PH-1 Zone-I of Haripur W/S Schemes under South 24-Pgs Mechanical Division, PHE Dte. [Block-Namkhana] | Assistant Engineer -I,Assistant Engineer -II | Junior Engineer | ORD/001901/2023-2024 | 1186/SMD | 22/03/2024 | 12/04/2024 | MASSK ENGINEERING WORKS | 10.74 | 10.02 | 93.21 | 95
10 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION FOR GROUND WATER BASED HARIPUR (ZONE- I & II), PIPED WATER SUPPLY SCHEME, Phase-B, UNDER ALIPORE DIVISION, BLOCK : NAMKHANA, DISTRICT : SOUTH 24 PARGANAS | SM/18698 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000791/2023-2024 | 636/AD | 30/01/2024 | 30/01/2024 | Resource Division | 4.68 | 0 | 0 | 0
11 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION FOR GROUND WATER BASED HARIPUR (ZONE- I & II), PIPED WATER SUPPLY SCHEME, Phase-B, UNDER ALIPORE DIVISION, BLOCK : NAMKHANA, DISTRICT : SOUTH 24 PARGANAS | SM/18698 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000550/2023-2024 | 33/AD | 02/01/2024 | 02/01/2024 | Resource Division | 2.97 | 0 | 0 | 0
12 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION FOR GROUND WATER BASED HARIPUR (ZONE- I & II), PIPED WATER SUPPLY SCHEME, Phase-B, UNDER ALIPORE DIVISION, BLOCK : NAMKHANA, DISTRICT : SOUTH 24 PARGANAS | SM/18698 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/03866/2023-2024 | BP-2023-24-395 | 02/12/2023 | 02/12/2023 | WBSEDCL | 4 | 0 | 0 | 0
13 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION FOR GROUND WATER BASED HARIPUR (ZONE- I & II), PIPED WATER SUPPLY SCHEME, Phase-B, UNDER ALIPORE DIVISION, BLOCK : NAMKHANA, DISTRICT : SOUTH 24 PARGANAS | SM/18698 | Augmentation | Sinking of 02 (two) Nos. 250mm x 150mm dia. 390 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for implementing of JJM of Haripur (Zone-II) W/S Scheme (Augmentation), Block - Namkhana under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000575/2023-2024 | 2261/AD | 14/08/2023 | 28/09/2023 | AQUATECH ENGINEERS | 39.53 | 23.41 | 59.22 | 100
14 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION FOR GROUND WATER BASED HARIPUR (ZONE- I & II), PIPED WATER SUPPLY SCHEME, Phase-B, UNDER ALIPORE DIVISION, BLOCK : NAMKHANA, DISTRICT : SOUTH 24 PARGANAS | SM/18698 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, Zone-I for Augmentation of Haripur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Namkhana] | Assistant Engineer -I,Assistant Engineer -II | Junior Engineer | ORD/003117/2023-2024 | 2643/SMD | 11/08/2023 | 29/12/2025 | MASSK ENGINEERING WORKS | 19.27 | 0 | 0 | 90
15 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION FOR GROUND WATER BASED HARIPUR (ZONE- I & II), PIPED WATER SUPPLY SCHEME, Phase-B, UNDER ALIPORE DIVISION, BLOCK : NAMKHANA, DISTRICT : SOUTH 24 PARGANAS | SM/18698 | Augmentation | Payment for New Service connection of Haripur Zone-II, PH-2 W/S Scheme Application No- 1008007196 Reference ID:- 106706026 |  |  | BILL/02491/2024-2025 | BP-2024-25-531 | 24/01/2025 | 24/01/2025 | WBSEDCL | 6.1 | 0 | 0 | 0
Total | [13 empty] | 516.76 | 236.63 | 45.79