## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS | Patharpratima | S24 Pgns Mechanical | GROUND WATER BASED BROJABALLAVPUR (ZONE-I & II) PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-PATHARPRATIMA,DISTRICT - SOUTH 24 PARGANAS | SM/18718 | New | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2,3 & 4 ( Zone-I & II) of Brojaballavpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Patharpratima] | Assistant Engineer -I | Junior Engineer | ORD/000604/2023-2024 | 1023/SMD | 12/04/2023 | 11/07/2023 | M.S.ENTERPRISE | 35.47 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED BROJABALLAVPUR (ZONE-I & II) PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-PATHARPRATIMA,DISTRICT - SOUTH 24 PARGANAS | SM/18718 | New | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (Brojaballavpur PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000640/2023-2024 | 2272/AD | 14/08/2023 | 28/09/2023 | INDRANIL DUTTA & ASSOCIATES | 9.35 | 9.35 | 100 | 100
3 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED BROJABALLAVPUR (ZONE-I & II) PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-PATHARPRATIMA,DISTRICT - SOUTH 24 PARGANAS | SM/18718 | New | Material Requisition To Resource Division |  |  | RTOR000110/2023-2024 | 646/AD | 17/05/2023 | 17/05/2023 | Resource Division | 14.14 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED BROJABALLAVPUR (ZONE-I & II) PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-PATHARPRATIMA,DISTRICT - SOUTH 24 PARGANAS | SM/18718 | New | Material Requisition To Resource Division |  |  | RTOR000486/2023-2024 | 4754/AD | 19/12/2023 | 19/12/2023 | Resource Division | 43.79 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED BROJABALLAVPUR (ZONE-I & II) PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-PATHARPRATIMA,DISTRICT - SOUTH 24 PARGANAS | SM/18718 | New | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Brojaballavpur (Zone - I & II) Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (Part-B) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000376/2023-2024 | 3501/AD | 16/10/2023 | 15/12/2023 | PIJUSH KANTI TRIPATHI | 77.26 | 28.62 | 37.04 | 20
6 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED BROJABALLAVPUR (ZONE-I & II) PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-PATHARPRATIMA,DISTRICT - SOUTH 24 PARGANAS | SM/18718 | New | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Brojaballavpur (Zone-I & II)W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000552/2023-2024 | 2234/AD | 11/08/2023 | 25/09/2023 | KANAN CONSTRUCTION | 49.16 | 46.51 | 94.6 | 90
7 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED BROJABALLAVPUR (ZONE-I & II) PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-PATHARPRATIMA,DISTRICT - SOUTH 24 PARGANAS | SM/18718 | New | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Brojaballavpur (Zone - I & II) W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-II) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000553/2023-2024 | 2235/AD | 11/08/2023 | 25/09/2023 | KANAN CONSTRUCTION | 49.14 | 47.55 | 96.76 | 90
8 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED BROJABALLAVPUR (ZONE-I & II) PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-PATHARPRATIMA,DISTRICT - SOUTH 24 PARGANAS | SM/18718 | New | Making and fixing of permanent display board at headwork site of Kshetramohanpur Zone - I & II, Brojoballavpur Zone - I & II PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/002112/2023-2024 | 932/KSD | 19/12/2023 | 24/12/2023 | BIMALENDU GIRI | 0.81 | 0.4 | 49.99 | 100
9 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED BROJABALLAVPUR (ZONE-I & II) PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-PATHARPRATIMA,DISTRICT - SOUTH 24 PARGANAS | SM/18718 | New | Material Requisition To Resource Division |  |  | RTOR000768/2023-2024 | 602/AD | 29/01/2024 | 29/01/2024 | Resource Division | 2.54 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED BROJABALLAVPUR (ZONE-I & II) PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-PATHARPRATIMA,DISTRICT - SOUTH 24 PARGANAS | SM/18718 | New | Construction of 100 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of foundation after soil investagation including O & M of Laying distribution, Rising Main & FHTC for 1 year after completion of FHTC works for Brojoballavpur (Zone - I & II) Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (Part-A) [No. of FHTC = 500] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000564/2023-2024 | 2256/AD | 14/08/2023 | 28/10/2026 | M/S B.N.ENTERPRISE | 249.59 | 85.94 | 34.43 | 35
11 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED BROJABALLAVPUR (ZONE-I & II) PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-PATHARPRATIMA,DISTRICT - SOUTH 24 PARGANAS | SM/18718 | New | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Brojaballavpur (Zone - I & II) Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-II) (Part-B) [No. of FHTC = 1145] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000565/2023-2024 | 2257/AD | 14/08/2023 | 31/08/2025 | TANMAY ROY CHOWDHURY | 217.83 | 165.96 | 76.19 | 20
12 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED BROJABALLAVPUR (ZONE-I & II) PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-PATHARPRATIMA,DISTRICT - SOUTH 24 PARGANAS | SM/18718 | New | Construction of 150 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of foundation after soil investagation including O & M of Laying distribution, Rising Main & FHTC for 1 year after completion of FHTC works for Brojoballavpur (Zone - I & II) Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-II) (Part-A) [No. of FHTC = 400] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000790/2023-2024 | 3734/AD | 03/11/2023 | 22/04/2026 | M/S B.N.ENTERPRISES | 266.67 | 108.59 | 40.72 | 41
13 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED BROJABALLAVPUR (ZONE-I & II) PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-PATHARPRATIMA,DISTRICT - SOUTH 24 PARGANAS | SM/18718 | New | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connection etc. at Brojaballavpur (Zone-I &II) W/S Scheme, Block -Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-II) (Part-I) (SM/18718) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000435/2024-2025 | 3074/AD | 25/07/2024 | 22/05/2026 | SHYAM DEVELOPER | 60.73 | 0 | 0 | 0
14 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED BROJABALLAVPUR (ZONE-I & II) PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-PATHARPRATIMA,DISTRICT - SOUTH 24 PARGANAS | SM/18718 | New | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Brojaballavpur (Zone - I & II) PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (for Zone-II) (SM/18718) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/003205/2023-2024 | 162/KSD | 05/01/2024 | 15/01/2024 | CONSTEEL CONSULTANCY & SERVICES | 0.48 | 0 | 0 | 100
15 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED BROJABALLAVPUR (ZONE-I & II) PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-PATHARPRATIMA,DISTRICT - SOUTH 24 PARGANAS | SM/18718 | New | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Brojaballavpur (Zone - I & II) PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (for Zone-I) (SM/18718) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/003206/2023-2024 | 161/KSD | 05/01/2024 | 15/01/2024 | CONSTEEL CONSULTANCY & SERVICES | 0.48 | 0 | 0 | 100
16 | SOUTH 24 PARGANAS | Patharpratima | S24 Pgns Mechanical | GROUND WATER BASED BROJABALLAVPUR (ZONE-I & II) PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-PATHARPRATIMA,DISTRICT - SOUTH 24 PARGANAS | SM/18718 | New | Brajaballabpur Zone-II PH-2 Water supply scheme Application No- 1008101055 Reference ID- 106755055 |  |  | BILL/00741/2025-2026 | 42152 | 01/08/2025 | 01/08/2025 | WBSEDCL | 6.15 | 0 | 0 | 0
17 | SOUTH 24 PARGANAS | Patharpratima | S24 Pgns Mechanical | GROUND WATER BASED BROJABALLAVPUR (ZONE-I & II) PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-PATHARPRATIMA,DISTRICT - SOUTH 24 PARGANAS | SM/18718 | New | Brajaballabpur Zone-II PH-1 Water supply scheme Application No- 1008101366 Reference ID- 106755053 |  |  | BILL/00740/2025-2026 |  | 18/06/2025 | 18/06/2025 | WBSEDCL | 6.28 | 0 | 0 | 0
18 | SOUTH 24 PARGANAS | Patharpratima | S24 Pgns Mechanical | GROUND WATER BASED BROJABALLAVPUR (ZONE-I & II) PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-PATHARPRATIMA,DISTRICT - SOUTH 24 PARGANAS | SM/18718 | New | Brajaballabpur Zone-I PH-1 Water supply scheme Application No- 1008101086 Reference ID- 106755051 |  |  | BILL/00745/2025-2026 |  | 18/06/2025 | 18/06/2025 | WBSEDCL | 6.77 | 0 | 0 | 0
19 | SOUTH 24 PARGANAS | Patharpratima | S24 Pgns Mechanical | GROUND WATER BASED BROJABALLAVPUR (ZONE-I & II) PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-PATHARPRATIMA,DISTRICT - SOUTH 24 PARGANAS | SM/18718 | New | Brajaballabpur Zone-I PH-2 Water supply scheme Application No- 1008293406 Reference ID- 106877834 |  |  | BILL/00747/2025-2026 |  | 18/06/2025 | 18/06/2025 | WBSEDCL | 5.27 | 0 | 0 | 0
Total | [13 empty] | 1101.9 | 492.92 | 44.73