## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SABEK MAHISAHARA AND ADJOINING MOUZA (CHUNPURI) | SM/18863 | Augmentation | Construction of 1 (one) no. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site for the Augmentation of Sabek Mahisahara & Adjoining Mouzas (Chunpuri) W/S Scheme, Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. [ Pump House No. - I] (3rd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000538/2024-2025 | 3709/AD | 12/09/2024 | 27/10/2024 | NIJAMUDDIN ENTERPRISE | 6.97 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SABEK MAHISAHARA AND ADJOINING MOUZA (CHUNPURI) | SM/18863 | Augmentation | Laying distribution system with supply of specials for Augmentation of Ground Water Based Piped Water Supply Scheme for Sabek Mahisahara and Adjoining Mouzas (Chunpuri), Block - Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000279/2024-2025 | 2494/AD | 14/06/2024 | 02/06/2025 | TARUN KUMAR LAHA | 48.15 | 0 | 0 | 15
3 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SABEK MAHISAHARA AND ADJOINING MOUZA (CHUNPURI) | SM/18863 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 for Augmentation of Sabek Mahisahara water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Canning-II] (SM/18863) | Assistant Engineer | Junior Engineer | ORD/000100/2025-2026 | 1179/SMD | 28/04/2025 | 10/09/2025 | PS & ASSOCIATES | 11.2 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SABEK MAHISAHARA AND ADJOINING MOUZA (CHUNPURI) | SM/18863 | Augmentation | Sinking of 01 (one) no. 250mm x 150mm dia. 300 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter for the Augmentation of Sabek Mahisahara & Adjoining Mouzas (Chunpuri) W/S Scheme, Block - Canning-II under Canning Sub Division of Alipore Division, PHE Dte. (TW. No. 1) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/002376/2023-2024 | 1200/AD | 29/02/2024 | 24/05/2025 | PADMA ENGINEERING CO | 17.31 | 0 | 0 | 100
Total | [13 empty] | 83.64 | 0 | 0