## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAORAKHALI AND ADJOINING MOUZAS (BAKULTALA). | SM/18864 | Augmentation | Laying distribution system with supply of specials for Augmentation of Ground Water Based Piped Water Supply Scheme for Kaorakhali & Adjoining Mouzas (Bakultala), Block - Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000372/2024-2025 | 2967/AD | 15/07/2024 | 01/05/2025 | CREATIVE | 137.23 | 0 | 0 | 60
2 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAORAKHALI AND ADJOINING MOUZAS (BAKULTALA). | SM/18864 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 for Augmentation of Kaorakhali water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block:Canning-II]. (SM/18864) | Assistant Engineer | Junior Engineer | ORD/000045/2025-2026 | 1430/SMD | 21/05/2025 | 03/10/2025 | S.S. ENTERPRISES | 19.1 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAORAKHALI AND ADJOINING MOUZAS (BAKULTALA). | SM/18864 | Augmentation | Sinking of 02 (two) nos. 250mm x 150mm dia. 300 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter for the Augmentation of Kaorakhali & Adjoining Mouzas (Bakultala) W/S Scheme, Block - Canning-II under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000345/2024-2025 | 2786/AD | 01/07/2024 | 11/01/2025 | AQUATECH ENGINEERS | 34.47 | 0 | 0 | 98
Total | [13 empty] | 190.81 | 0 | 0